## Financial Dashboard
Band 2 (€0.5 - €10 Million) & Band 3 (> €10 Million) Construction Phase Monthly Financial Dashboard
Construction Phase Financial Dashboard
Project Name:
Report No:
Date:
Value of Works Carried Out To Date:
The certified value excluding VAT is:
Total gross amount applied to date
Less Retention
Total nett amount certified to date
Current Contract Sum:
Original Contract Sum |  |  | 0
Value of Agreed Change Orders |  |  | 0
Value of Agreed Compensation & Delay Events |  |  | 0
Value of Agreed Employer Claims |  |  | 0
Revised Contract Sum (after adjustments) |  |  | 0
Situation Notifications
Situations Notifications raised to date |  |  | 0 | nr
Situation Notifications resulting in Compensation Events |  |  | 0 | nr
Situations Notifications not agreed as Compensation Events |  |  | 0 | nr
Situation Notifications yet to be determined |  |  | 0 | nr
Change Orders
Change Orders |  |  | 0 | nr
Change Orders agreed |  |  | 0 | nr
Change Orders yet to be agreed |  |  | 0 | nr
Compensation & Delay Events
Compensation & Delay Events |  |  | 0 | nr
Compensation & Delay Events agreed |  |  | 0 | nr
Compensation & Delay Events yet to be agreed |  |  | 0 | nr
Employer Claims
Employer Claims |  |  | 0 | nr
Employer Claims agreed |  |  | 0 | nr
Employer Claims yet to be agreed |  |  | 0 | nr
Forecast Out-turn Cost
Original Contract Sum |  |  | 0
Value of agreed Change Orders |  |  | 0
Estimated value of Change Orders yet to be agreed |  |  | 0
Value of agreed Compensation & Delay Events |  |  | 0
Estimated value of Compensation & Delay Events yet to be agreed |  |  | 0
Value of agreed Employer Claims |  |  | 0
Estimated value of Employer Claims yet to be agreed |  |  | 0
Situation Notifications |  |  | 0
Other liabilities |  |  | 0
Forecast Final Contract Sum (Out-turn Cost) |  |  | 0
Programme
Contract Date
Starting Date
Original Date for Substantial Completion of the Works
Current Forecast Date for Substantial Completion of the Works
Cost and Schedule Performance Indicators
CPI | SPI | 1
Key Risks / Opportunities (Please provide a brief summary on the live key project risks and opportunities)
Risk Description | Risk Owner |  | Likely Impact
|  |  | € | Time

## Progress & Expenditure Matters
1.0 Progress & Expenditure Matters Template
Project Name:
Project / Contract Code:
Report No:
Date:
Change Orders
Provide details of the change orders raised that have/may give rise to cost and time implications
Reference | Description | Anticipated Impact |  | Status | Current Actions
|  | € | Time (weeks)
Pending
Agreed
Rejected
Total Anticipated Impact: |  | 0 | 0
Compensation & Delay Events
Provide details of any Compensation & Delay Events in the table below
Reference | Description | Anticipated Impact |  | Status | Current Actions
|  | € | Time (weeks)
Pending
Agreed
Rejected
Total Anticipated Impact: |  | 0 | 0
Other Potential Liabilities
Provide details of any other potential liabilities that may present cost or time implications to the project
Reference | Description | Anticipated Impact |  | Status | Current Actions
|  | € | Time (weeks)
Open
Closed
Total Anticipated Impact: |  | 0 | 0
Revision | Status |  |  | Prepared By | Date | Checked By | Date

## Forecast Expenditure Profile
2.0 CONSTRUCTION EXPENDITURE PROFILE
Project Name:
NTA Approval Year:
Report No:
Date:
Contract Sum:
Agreed Change Orders:
Agreed Compensation & Delay Events:
Agreed Employer Claims:
Revised Contract Sum:
Payment No. | Month | Forecast Payment | Forecasted Cumulative Value | Amount Certified | Cumulative Value
1 | Jan | 0 | 0 | 0 | 0
2 | Feb | 0 | 0 | 0 | 0
3 | Mar | 0 | 0 | 0 | 0
4 | Apr | 0 | 0 | 0 | 0
5 | May | 0 | 0 | 0 | 0
6 | Jun | 0 | 0 | 0 | 0
7 | Jul | 0 | 0 | 0 | 0
8 | Aug | 0 | 0 | 0 | 0
9 | Sep | 0 | 0 | 0 | 0
10 | Oct | 0 | 0 | 0 | 0
11 | Nov | 0 | 0 | 0 | 0
12 | Dec | 0 | 0 | 0 | 0
13 | Jan | 0 | 0 | 0 | 0
14 | Feb | 0 | 0 | 0 | 0
15 | Mar | 0 | 0 | 0 | 0
16 | Apr | 0 | 0 | 0 | 0
17 | May | 0 | 0 | 0 | 0