## Cover
Construction Phase Financial Report
Band 2 (€0.5-10 Million) & Band 3 (€10 Million+) Projects
Enter Project Name
Enter Approving Authority
Enter Sponsoring Agency
Enter Partnering Organisation
Enter Main Contractor
Enter Report Date

## Contents Page
CONTENTS PAGE
Project Name:
Report No.
Date:
1 | Executive Summary
2 | Contract Information
3 | Schedule of Payment Certificates
4 | Change Orders Summary
5 | Compensation & Delay Event Summary
6 | Employer Claims Summary
7 | Situation Notification Summary
8 | Other liabilities Summary
9 | Employer's Comparison Data Sheet
10 | Construction Expenditure Profile
Revision | Status | Prepared by | Checked by | Date
Cost and Schedule Performance Indicators
CPI |  |  | SPI | 1

## 1. Executive Summary
1. PROJECT DASHBOARD SUMMARY
Project Name:
Report No:
Date:
Value of Works Carried Out To Date:
The certified value excluding VAT is:
Total gross amount certified to date (to be manually inserted)
Less Retention (to be manually inserted)
Total nett amount certified to date (to be manually inserted)
Current Contract Sum:
Original Contract Sum |  |  | 0
Value of Agreed Change Orders |  |  | 0
Value of Agreed Compensation & Delay Events |  |  | 0
Value of Agreed Employer Claims |  |  | 0
Revised Contract Sum (after adjustments) |  |  | 0
Situation Notifications
Situations Notifications raised to date (to be manually inserted) |  |  | 0 | nr
Situation Notifications resulting in Compensation Events (to be manually inserted) |  |  | 0 | nr
Situations Notifications not agreed as Compensation Events (to be manually inserted) |  |  | 0 | nr
Situation Notifications yet to be determined (to be manually inserted) |  |  | 0 | nr
Change Orders
Change Orders (to be manually inserted) |  |  | 0 | nr
Change Orders agreed (to be manually inserted) |  |  | 0 | nr
Change Orders yet to be agreed (to be manually inserted) |  |  | 0 | nr
Compensation & Delay Events
Compensation & Delay Events (to be manually inserted) |  |  | 0 | nr
Compensation & Delay Events agreed (to be manually inserted) |  |  | 0 | nr
Compensation & Delay Events yet to be agreed (to be manually inserted) |  |  | 0 | nr
Employer Claims
Employer Claims (to be manually inserted) |  |  | 0 | nr
Employer Claims agreed (to be manually inserted) |  |  | 0 | nr
Employer Claims yet to be agreed (to be manually inserted) |  |  | 0 | nr
Forecast Out-turn Cost
Original Contract Sum |  |  | 0
Value of agreed Change Orders |  |  | 0
Estimated value of Change Orders yet to be agreed |  |  | 0
Value of agreed Compensation & Delay Events |  |  | 0
Estimated value of Compensation & Delay Events yet to be agreed |  |  | 0
Value of agreed Contractor Claims |  |  | 0
Estimated value of Contractor Claims yet to be agreed |  |  | 0
Situation Notifications |  |  | 0
Other liabilities |  |  | 0
Forecast Final Contract Sum (Out-turn Cost) |  |  | 0
Programme
Contract Date (to be manually inserted)
Starting Date (to be manually inserted)
Original Date for Substantial Completion of the Works (to be manually inserted)
Current Forecast Date for Substantial Completion of the Works (to be manually inserted)
Cost and Schedule Performance Indicators
CPI | SPI | 1
Key Risks / Opportunities (Please provide a brief summary on the live key project risks and opportunities)
Risk Description | Risk Owner |  | Likely Impact
|  |  | € | Time

## 2. Contract Information
2. CONTRACT INFORMATION
Project Name:
Report No:
Date:
Employer | Name
Address
Employer's Representative | Name
Address
Contractor | Name
Address
Contractor's Representative | Name
Address
Key people | Name | Role
Conditions of contract:
Contract Date:
Starting Date:
Original Date for Substantial Completion of the Works:
Original Contract Sum: |  |  | 0

## 3. Schedule of Certificates
3. SCHEDULE OF PAYMENT CERTIFICATES
Project Name:
Report No:
Date:
Original Contract Sum: |  |  |  |  | 0
Agreed value of Change Orders: |  |  |  |  | 0
Agreed value of Compensation & Delays Events: |  |  |  |  | 0
Agreed value of Contractor Claims: |  |  |  |  | 0
Current Contract Sum (after adjustments): |  |  |  |  | 0
Certificate No. | Gross Amount Certified | Net Amount Certified | VAT | Payment Due Date | Cumulative
[5 empty] | Certified | VAT | Current VAT Rate
1 |  |  |  |  | 0 | 0 | 13%
2 |  |  |  |  | 0 | 0
3 |  |  |  |  | 0 | 0
4 |  |  |  |  | 0 | 0
5 |  |  |  |  | 0 | 0
6 |  |  |  |  | 0 | 0
7 |  |  |  |  | 0 | 0
8 |  |  |  |  | 0 | 0
9 |  |  |  |  | 0 | 0
10 |  |  |  |  | 0 | 0
11 |  |  |  |  | 0 | 0

## 4. CO Summary
4. CHANGE ORDER SUMMARY
Project Name:
Report No:
Date:
Ref | Description of Change Order | Contractor Estimated Impact |  | Employer's Budget Impact |  | Agreed Impact |  | Agreed Value (Complete)
|  | Cost | Time | Cost | Time | Cost | Time | Cost | Time
TOTALS: |  | 0 |  | 0 |  | 0 |  | 0

## 5. CE Summary
5. COMPENSATION & DELAY EVENT SUMMARY
Project Name:
Report No:
Date:
Ref | Description of Event | Contractor Estimated Impact |  | Employer's Budget Impact |  | Agreed Impact |  | Agreed Value (Complete)
|  | Cost | Time | Cost | Time | Cost | Time | Cost | Time
TOTALS: |  | 0 |  | 0 |  | 0 |  | 0

## 6. EC Summary
6. EMPLOYER CLAIM SUMMARY
Project Name:
Report No:
Date:
Ref | Description of Claim | Contractor Estimated Impact |  | Employer's Budget Impact |  | Agreed Impact |  | Agreed Value (Complete)
|  | Cost | Time | Cost | Time | Cost | Time | Cost | Time
TOTALS: |  | 0 |  | 0 |  | 0 |  | 0

## 7. SN Summary
7. SITUATION NOTIFICATION SUMMARY
Project Name:
Report No:
Date:
Ref | Description of Event | Date Notified | Raised by | Status | Closure Date | Estimated Impact (if not already agreed as a CE)
[6 empty] | Cost | Time
Open
Closed
TOTALS | [5 empty] | 0

## 8. Potential Liabilities
8. OTHER LIABILITIES SUMMARY
Project Name:
Report No:
Date:
Ref | Description of Event | Potential Impact |  | Liability Status
|  | Cost | Time
Open
Closed
TOTALS |  | 0

## 9. Employer's Data Sheet
9. EMPLOYER'S COMPARISON DATA SHEET
Project Name:
Report No:
Date:
Project Costs | Tender (€) | Previous Assessment (€) (Manually Inserted) | Current Assessment (€) | Variance in Period (%)
Original Contract Sum | 0 | 0 | 0 | 0%
Change Orders |  | 0 | 0 | #DIV/0!
Compensation & Delay Events |  | 0 | 0 | #DIV/0!
Employer Claims |  | 0 | 0 | #DIV/0!
Situation Notifications & Potential Liabilities |  | 0 | 0 | #DIV/0!
Total estimated cost of Project | 0 | 0 | 0 | #DIV/0!
Narrative explanation required for variances which exceed set parameters agreed with NTA

## 10. Expenditure Profile R1
10. CONSTRUCTION EXPENDITURE PROFILE
Project Name:
NTA Approval Year:
Report No:
Date:
Contract Sum:
Agreed Change Orders:
Agreed Compensation & Delay Events:
Agreed Employer Claims:
Revised Contract Sum:
Payment No. | Month | Forecast Payment | Forecasted Cumulative Value | Amount Certified | Cumulative Value
1 | Jan | 0 | 0 | 0 | 0
2 | Feb | 0 | 0 | 0 | 0
3 | Mar | 0 | 0 | 0 | 0
4 | Apr | 0 | 0 | 0 | 0
5 | May | 0 | 0 | 0 | 0
6 | Jun | 0 | 0 | 0 | 0
7 | Jul | 0 | 0 | 0 | 0
8 | Aug | 0 | 0 | 0 | 0
9 | Sep | 0 | 0 | 0 | 0
10 | Oct | 0 | 0 | 0 | 0
11 | Nov | 0 | 0 | 0 | 0
12 | Dec | 0 | 0 | 0 | 0
13 | Jan | 0 | 0 | 0 | 0
14 | Feb | 0 | 0 | 0 | 0
15 | Mar | 0 | 0 | 0 | 0
16 | Apr | 0 | 0 | 0 | 0
17 | May | 0 | 0 | 0 | 0