## NTA Contingency Matrix
Contingency Calculator
[9 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: | R5*** Navan Road - Dublin | [7 empty] | Sponoring Agency (SA) to list out the project title
Project / Contract Code: | DLR/22/0015G | [7 empty] | SA confirm the project code
NTA Project Phase: | Phase 3 - Preliminary Design |  | Work Classification: |  | 'Standard' project |  |  |  | SA to confirm the project phase (see drop when you click on the cell C7)
SA to confirm the classification (see drop when you click on the cell H7) - non standard would be working in a City centre
Contingency Factors: | 'Non-standard' project |  | 'Standard' project |  | Quantitative Risk Assessment (QRA) |  |  |  | This section is guidance only
NTA Project Phase | Upper bound Contingency (%) | Lower bound Contingency (%) | Upper bound Contingency (%) | Lower bound Contingency (%) | QRA Required | Band 1 | Band 2 | Band 3
Phase 1 - Scope and Purpose | 66 | 50 | 44 | 30 | No | N/A | N/A | N/A
Phase 2 - Concept Development and Option Selection | 66 | 50 | 44 | 30 | No | N/A | N/A | N/A
Phase 3 - Preliminary Design | 50 | 30 | 35 | 20 | Yes | 004_B1_QRA_CMG | 013_B23_QRA_CMG | 013_B23_QRA_CMG
Phase 4 - Statutory Processes | 50 | 30 | 30 | 20 | Yes | 004_B1_QRA_CMG | 013_B23_QRA_CMG | 013_B23_QRA_CMG
Phase 5 - Detailed Design and Procurement | 30 | 10 | 20 | 10 | Yes | 004_B1_QRA_CMG | 013_B23_QRA_CMG | 013_B23_QRA_CMG
Contributory Factors | Mitigation Action |  |  |  | % Weighting | % Completed | % Mitigation |  | SA to confirm the % complete
Land / Planning | Proposed works confined to land within NTA ownership / control |  |  |  | 5% | 90 | 4.5%
| Additional land values confirmed / land acquired |  |  |  | 2.5% | 90 | 2.25%
| Liaison with Planning Authority / Planning commenced or awarded |  |  |  | 2.5% | 90 | 2.25%
Design development / complexity | Design developed beyond stated NTA Project Phase |  |  |  | 5% | 75 | 3.75%
| Design comprises standard construction elements |  |  |  | 2.5% | 75 | 1.875%
| NTA / Contractor has a proven track record of delivering similar solutions |  |  |  | 2.5% | 25 | 0.625%
Risk management | Key Project risks identified and mitigation measures defined |  |  |  | 2.5% | 75 | 1.875%
| Key Project risks allocated appropriate cost and time allowances / QRA produced |  |  |  | 20% | 75 | 15%
Estimates / costs independently verified | Cost build-up independently checked and verified |  |  |  | 5% | 75 | 3.75%
| Alignment of costs with NTA benchmarks |  |  |  | 7.5% | 75 | 5.625%
Scope of Proposal | Scope of works is well defined and robust |  |  |  | 5% | 90 | 4.5%
Project intelligence / surveys and investigations | Surveys and investigations undertaken to inform the design |  |  |  | 5% | 75 | 3.75%
Stakeholders | Affected stakeholders identified, consulted and key requirements documented |  |  |  | 15% | 100 | 15%
Environmental impact | Proposed solution has minimal environmental impact |  |  |  | 2.5% | 100 | 2.5%
| Base price and delivery programme includes appropriate allowance for environmental / ecological mitigation |  |  |  | 5% | 100 | 5%
Health & Safety | Methodology mitigates serious incident occurrence |  |  |  | 5% | 100 | 5%
Procurement | Procurement strategy concluded / tried and tested solution recommended |  |  |  | 2.5% | 50 | 1.25%
| Procurement successfully completed |  |  |  | 5% | 0 | 0%
[5 empty] | 100% |  | 78.5%
Mitigated Contingency Calculation
Upper Bound = | 35% |  | Example of Applying Percentage Completion of Mitigating Action Contingency Calculator Categories Contributory Factor: Estimates / costs independently verified Mitigation Action: Cost build-up independently checked and verified Example of Using the Calculator: % Completed: 100% Why: A peer review was undertaken on all projects costs (not just construction related costs). Comments from the peer review were incorporated where deemed appropriate.
Lower Bound = | 20%
Difference = | 15%
Mitigation % = | 78.5%
Mitigation Value = | 11.77%
Applicable Contingency Percentage | 23.23% | [7 empty] | Sponsoring Agency note - a contingency allowance should always be used
SA note - the % allowance reduces when you select above the phase (in this case - Phase 3 - refer to excel cell C7 above)
'Standard' project
'Non-standard' project