## Cost Estimate
Grant Application Cost Estimate Template
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional line etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: the activity cost heads presented are indicative for a linear project, if the project being reported (undertaken/developed) is not a linear project, activity cost heads are to be discussed and agreed in writing with NTA prior to the production of the cost estimate. | [9 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
Project Title: |  |  | Highways Improvement for Urban Environment | [6 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/12/0015A | Prepared By (Individual & Organisation) |  |  | Sally Gate - South Dublin Council |  |  | SA confirm the project code
Approving Authority: |  |  | NTA | Date Estimate Prepared: |  |  | 2016-02-01 |  |  | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin Council | Base Date of Estimate: |  |  | Q 2016 |  |  | SA = local authority (or Irish Rail / Bus Éireann etc ...) submitting the application: Base date is the quarter period (Q1 = Jan / Feb / march: Q2 = Apr / May / June: Q3 = July / Aug / Sept: Q4 = Oct / Nov / Dec)
Project Information | [8 empty] | 1
2
Mainline Cross-Section Type: |  |  | Dual | Location: |  | ****** City Centre |  |  | 3 | Identify location - include co-ordinates if available
4
Total Mainline Length (m): |  |  | 2700 | Traffic Impact Rating (DCC Only): |  |  |  |  | 5 | SA to confirm the total length of construction: List impact rating on scale 1 to 5 (5 been the highest - click the cell for dropdown if applicable) - leave blank if N/A
Total Mainline Width (m): |  |  | 6 | Land take Required: | [5 empty] | SA to confirm width: SA to confirm if land take is required
Potential Construction Works Start Date: |  |  | Q3 2017 | Anticipated Construction Period: |  | 24 | Months |  |  | SA to confirm potential start on site (Quarter): SA to confirm estimated construction period
Other Relevant Project Information: |  |  | New Dual Carriageway | [6 empty] | SA to outline (brief) project scope of works
1 | Grant Application Cost Estimate
| Ref | Description |  | Quantity | Unit | Rate | Total (€)
| 1.1 | Construction Costs |  | 2.7 | Km | 7037000 | 18999900 |  | Item | If backup is available - use the Calculation sheet tab - If no back-up give explanation to costing source as per excel line B62 below
| Sub-Total A - Construction Costs | [5 empty] | 18999900 |  | Km
| Add-On Costs | [7 empty] | M
| 1.2 | Preparation and Administration Costs |  |  |  |  | 2850000 |  | Nr | SA to confirm admin costs (design teams etc …)
| 1.2.1 | Scope & Purpose |  | 1 | Item | 0 | 0
| 1.2.2 | Concept, Development & Option Selection |  | 1 | Item | 125000 | 125000
| 1.2.3 | Preliminary Design |  | 1 | Item | 500000 | 500000
| 1.2.4 | Statutory Processes |  | 1 | Item | 400000 | 400000
| 1.2.5 | Detailed Design & Procurement |  | 1 | Item | 75000 | 75000
| 1.2.6 | Construction & Implementation |  | 1 | Item | 1500000 | 1500000
| 1.2.7 | Close Out & Review |  | 1 | Item | 250000 | 250000
| 1.3 | Traffic Management (TM) Related Costs |  | 5% | % | 18999900 | 949995 |  | M2 | SA to allow costs (estimate) for TM (if applicable to there project)
| 1.4 | Land and Property Costs (inclusive of inflation) |  | 1 | Item | 125000 | 125000 |  |  | SA to estimate the costs - confirm in assumptions tab the m2 take and the estimated rate
| Sub-Total B - Add-ons | [5 empty] | 3924995
Adjustments
| 1.5 | Inflation (Band 2 & 3 Projects Only) |  | 25% | % | 22799895 | 5699973.75 |  | % | SA to confirm if inflation needs to be applied - example, if works were not to happen until Q2 2018, NTA would recommend applying % cost. Refer to the NTA bulletin for guidance on inflation allowances.
| 1.6 | Add Contingency Allowance (001_B123_CC_CMG) |  | 64.8% | % | 28499868.75 | 18467914.95 |  | Item | SA to confirm - refer to contingency calculator (form 001) -36% is as per the worked example (note, contingency allownce should always be included)
| 1.7 | Per Cent for Art Scheme https://publicart.ie/main/commissioning/funding/per-cent-for-art-scheme/ |  | 1% | % | 28499868.75 | 284998.6875 |  | Item | SA to review web link for proposed maximum limits
| Sub-Total C - Adjustments | [5 empty] | 24452887.3875
| Total Grant Application Cost Estimate (excluding VAT) | [5 empty] | 47377782.3875
| VAT on Construction and TM Costs (including Contingency & Inflation) |  |  | 13.5% | % | 44117783.7 | 5955900.7995 |  |  | 13.5% VAT is applied to the construction estimate / Traffic MGT / inflation allowance / contingency allowance
| VAT on Preparation & Administration Costs |  |  | 23% | % | 2850000 | 655500 |  |  | 23% applies to preparation costs (design teams as an example): No VAT should be applied if design is in-house with the SA
| VAT on Land and Property |  |  | 1 | Item
| https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [8 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line C54 to determine if VAT is applicable to your project
| Total Grant Application Cost Estimate (Including VAT) | [5 empty] | 53989183.187
| Mainline Length |  | 2.7 | Km |  | Rate Per Km (Excluding VAT) | 17547326.8102 |  |  | SA to insert mainline length = this will automatically confirm the € / KM
[6 empty] | Rate Per Km (Including VAT) | 19995993.773
Source of Cost Data (Please provide a brief narrative on the source of cost data in the box below)
| Cost estimate is based on works of similar nature where we have a contractor on site. It will be the sponsoring agencies proposal to use a contractor (framework) to carry out the works based on tender return | [8 empty] | SA to confirm where costs have dererived from (example, similar works on site with contractor price per m applied to the current cost estimate). Refer to the Calculation tab if there is a breakdown available (example, if quantities known, apply QTY x Rates
2 | Risk
| Please include details of known key project risks. (Additional rows to be added as required) Please rank risks in order of severity with 5 being most severe. |  |  | Risk |  |  |  | Rank |  | SA to list as noted below
(no Risk Register (form 004) is required
Revision | Title |  |  | Prepared By | Checked By |  | Issue Date
|  |  |  | Sally Gates | Michael Bunny |  | 2016-02-01 |  |  | SA to sign off (2 parties within their organisation)
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered include allowances for overheads and profit. VAT is not applicable to all land and property therefore it is not appropriate to apply a uniform percentage. The value associated with VAT on land and property is to be determined on an individual basis and included as a lump sum.
Check Box If Yes
Note on J14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)
Note on I52: Estimating Methodology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on I53: Estimating Methodology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on I54: Estimating Methodology The applicable VAT rate is to be determined by each user individually. A hyperlink to applicable rules/laws relating to the applicability of VAT is included for reference and assessment purposes.

## Assumptions
Estimate Assumptions, Exclusions and Inclusions
[7 empty] | Guidance Notes | * All cells in purple - input is required
| Project Title: |  | Highways Improvement for Urban Environment |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Project / Contract Code: |  | DLR/12/0015A |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Approving Authority: |  | NTA |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Sponsoring Agency: |  | South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Prepared By (Individual/Organisation): |  | Sally Gate - South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1 | Construction Costs
Cost estimate is on the basis of similar schemes completed by the South Dublin Council. We have allowed up-dated costs using indicies which is included in the €/Km on the cost estimate summary
SA to give as much information as possible
Potential Start Date:
| 2 | Delivery and Construction Programme
Estimated programme on site is 24 months. Programme estimate is based on projects completed of similar nature
SA to give programme information as per dates in Cost Estimate tab
| 3 | Preparation and Administration Costs
|  | Any assumptions, exclusions or inclusions that have been made in relation to preparation and administration (design & supervision) shall be clearly identified in this section. Substantiation/justification of the percentage applied in the cost estimate shall be provided in this section. |  |  |  |  | SA to include costs for design / administration costs
(example purposes - the cost estimate includes for design team / consultant)
| 4 | Traffic Management Related Costs
We have inlcued traffic management costs so as to expediate works on site and also eliminate risks (traffic accidents)
SA to confirm if traffic management (TM) is included or not (not required) - If TM was not required, state TM is not required on site
| 5 | Land and Property Costs
|  | We confirm there is 100m2 of land take required. We estimate the cost to be €1,250 per m2 to include any remedial works on the land take. We are in discussion with the effected parties and no main concerns to report. |  |  |  |  | SA to give information on estimated costs / quantity if land take (m2) / negotiations if any that have occurred / flag any issues
| 6 | Other Relevant Information |  |  |  |  | SA to provide if any additional information is required to be completed
Any other relevant information, general assumptions, exclusions or inclusions that have been used to develop the cost estimate shall be included in this section.
| Revision | Title |  | Prepared By | Checked By | Issue Date
|  |  |  | Sally Gates | Michael Bunny | 2016-02-01 | SA to sign off (2 parties within their organisation)

## Grant Application Summary
Grant Application Cost Estimate Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the grant application form. | [7 empty] | Guidance Notes
Project Title: |  |  | Highways Improvement for Urban Environment |  |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  |  | DLR/12/0015A | Prepared By (Individual & Organisation) |  |  | Sally Gate - South Dublin Council | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  |  | NTA | Date Estimate Prepared: |  |  | 2016-02-01 | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  |  | South Dublin Council | Base Date of Estimate: |  |  | Q 2016 | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | Grant Application Cost Estimate - Summary
| 1.2.1 | Scope & Purpose |  | 1 | Item | 0 | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.2 | Concept, Development & Option Selection |  | 1 | Item | 125000 | 125000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.3 | Preliminary Design |  | 1 | Item | 500000 | 500000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.4 | Statutory Processes |  | 1 | Item | 400000 | 400000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.5 | Detailed Design & Procurement |  | 1 | Item | 75000 | 75000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.6 | Construction & Implementation |  | 1 | Item | 45742783.7 | 45742783.7 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.7 | Close Out & Review |  | 1 | Item | 250000 | 250000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Total Grant Application Cost Estimate (excluding VAT) | [5 empty] | 47092783.7
| Add VAT @ 13.5% | [5 empty] | 5955900.7995 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Add VAT @ 23% | [5 empty] | 655500 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Add VAT on Land (If Applicable) | [6 empty] | SA to include if applicable pending Revenue rules
| Total Grant Application Cost Estimate (Including VAT) | [5 empty] | 53704184.4995
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.
Note on J14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## Expenditure Profile
Expenditure Profile
|  |  |  | Guidance Notes | * All cells in purple - input is required | *** Figures & spend per quarter is illustrative only ***
Project Title: |  | Highways Improvement for Urban Environment |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/12/0015A |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Preliminary Cost Estimate: |  | 53989183.187 |  | No action required - the text is carried forward automatically from the Cost Estimate tab - Include figure with VAT
Anticipated Programme Duration: |  | 24 | Months | No action required - the text is carried forward automatically from the Cost Estimate tab
Grant Application Cost Estimate
Year | Quarter | Total Quarterly Expenditure (€) | Total Cumulative Expenditure (€) | Note - Year 1 is from the date of the Grant Application submission
Year 1 | Q1 |  | 0 | SA to include the expenditure per quarter
| Q2 | 80000 | 80000
| Q3 | 175000 | 255000
| Q4 | 175000 | 430000
Year 2 | Q1 | 450000 | 880000
| Q2 | 1800000 | 2680000
| Q3 | 4500000 | 7180000
| Q4 | 4500000 | 11680000
Year 3 | Q1 | 6000000 | 17680000
| Q2 | 6000000 | 23680000
| Q3 | 7500000 | 31180000
| Q4 | 7500000 | 38680000
Year 4 | Q1 | 7500000 | 46180000
| Q2 | 6000000 | 52180000
| Q3 | 1524184.5 | 53704184.5
| Q4 |  | 53704184.5
Revision | Title
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Calculation Sheet
Guidance Notes
Ref | Description | QTY | Unit | Rate | Total | *** Figures are illustrative only ***
** Example headings **
| Preliminaries | 1 | item |  | 0
| Road Works | 1 | item |  | 0
| Structures | 1 | item |  | 0
| Structures Designed by the Contractor | 1 | item |  | 0
0