## Risk Register
Risk Analysis; Risk Register (Live Risks) |  |  |  |  | Guidance Notes | * NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
Project Title: |  | R2 - Galway Road - Dublin |  |  | Snorsoring Agency (SA) to include project details
Project / Contract Code: |  | DLR/22/0015G |  |  | Snorsoring Agency (SA) to include project details
Phase 3 - Preliminary Design
Current Project Phase: |  | Phase 5 - Detailed Design and Procurement |  |  | Click on the cell - it gives the option to select what phase you are currently at | [8 empty] | Phase 4 - Statutory Process
Phase 5 - Detailed Design and Procurement
Project Cost (Construction, Preparation & Admin and TM): |  | 420462.74 |  |  | This is the figure from the Grant Application Cost Estimate (form 005_B1) | [8 empty] | Phase 4 - Statutory Process
Date Risk Register Updated: |  | 2022-12-12 |  |  | SA to include the date the register was prepared (issue date to NTA)
Risk Register
[5 empty] | Probability (Most Likely) |  | Impact (Most Likely) |  | Risk Rating | Overall Risk
ID | Description / Cause |  |  | Risk Owner (Individual & Organisation) | (Ranking 1-5) | % | (Ranking 1-5) | Cost as % of project cost | (PxI) | Project Cost | Risk Response / Mitigation |  |  |  | Guidance Notes
1 | Archaelogy - the project is near an old monastery |  |  |  | 1 | 2.5% | 1 | 2102.3137 | 1 | 52.5578 |  |  |  |  | SA to list out all the risks - see category below (ranking 1-5) Risk owner should also be identified. Any poteential mitigations for risk should be highlighted if known at this stage.
2 | Delays due to Public Opposition when construction commences, there have been similar protest in the area recently due to traffic management |  |  |  | 2 | 13% | 2 | 4204.6274 | 4 | 546.6016
3 | Potential Damage to existing services during works. Delay to programme and associated costs. |  |  |  | 3 | 35.5% | 2 | 4204.6274 | 6 | 1492.6427
4 | Materials costs may continue to suffer significant inflationary pressure resulting in increased cost. |  |  |  | 1 | 2.5% | 1 | 2102.3137 | 1 | 52.5578
5 | Quote from specialsit contractor is 5 months old - they cannot give a final fixed price until the local authority confirm a final state date |  |  |  | 3 | 35.5% | 2 | 4204.6274 | 6 | 1492.6427
6 | Discussion with Irish Water has indicated their may be a water line below the works area and if located thay may wish to investigate and expose and install a new duct over for future proof |  |  |  | 5 | 90% | 5 | 42046.274 | 25 | 37841.6466
7
8
9
10
| Current Risk Assessment of Construction, Preparation & Administration and Traffic Management Costs (Risk to be applied in cost estimating templates) | [8 empty] | 41478.6493 |  |  |  |  | The final cost is based on the rankings applied and the cost estimate above
Risk Matrix | [9 empty] | Probability / Impact Schedule
HIGH RISK |  |  |  | PROBABILITY (RANK) | [5 empty] | CAT | Probability / Impact | Prob (Average) | Impact (Cost)
MEDIUM RISK |  |  |  | Negligible | Unlikely | Possible | Probable | Almost Certain |  | 5 | VH | 90% | 10%
LOW RISK |  |  |  | Very Low | Low | Medium | High | Very High |  | 4 | H | 65.5% | 5%
|  |  |  | 3% | 13% | 36% | 66% | 90% |  | 3 | M | 35.5% | 3%
|  |  |  | ① | ② | ③ | ④ | ⑤ |  | 2 | L | 13% | 1%
IMPACT | 10% | Major | ⑤ | 5 | 10 | 15 | 20 | 25 |  | 1 | VL | 2.5% | 0.5%
| 5% | Large | ④ | 4 | 8 | 12 | 16 | 20 |  | Notes: 1. Should a forecast impact category of 5 (10%) be selected, the risk shall be reviewed in conjunction with the Sponsoring Agency to determine if the impact cost percentage is sufficient. If it is deemed insufficient, the impact cost shall be adjusted manually to percentage that is agreeable to the Sponsoring Agency.
| 3% | Moderate | ③ | 3 | 6 | 9 | 12 | 15
| 1% | Minor | ② | 2 | 4 | 6 | 8 | 10
| 0.5% | Minimal | ① | 1 | 2 | 3 | 4 | 5
| Cost as % of Project cost (not just fees) | Quality | CAT | Cost / time and quality may be affected differently by a single risk. If overall risk is required, use the most severe affected component or give consideration to managing each separately.

## Cost Matrix (hidden)
COST MATRIX
Phase Specific Cost Esimate
CAT | IMPACT | Prob (Average) | Most Likely Cost
5 | VH | 90% | 10%
4 | H | 65.5% | 5%
3 | M | 35.5% | 3%
2 | L | 13% | 1%
1 | VL | 2.5% | 0.5%
0 | VL | 0% | 0%