## Cost Estimate
Total Project Cost - Estimate Template
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: For Band 1 Projects the activity cost heads presented are indicative for a linear project, if the project being reported (undertaken/developed) is not a linear project, activity cost heads are to be discussed and agreed in writing with NTA prior to the production of the cost estimate. | [11 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative only ***
Project Title: |  |  | R2 - Galway Road - Dublin | [8 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/22/0015G |  |  |  |  | Prepared By (Individual/Organisation): |  |  | Sally Gate - SDC | SA confirm the project code
Approving Authority: |  |  | MTA |  |  |  |  | Date Estimate Prepared: |  |  | 2022-12-12 | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin Council |  |  |  |  | Base Date of Estimate: |  |  | Q4 2022 | SA, local authority submitting the application: Base date is the quarter period (Q1 = Jan / Feb / march: Q2 = Apr / May / June: Q3 = July / Aug / Sept: Q4 = Oct / Nov / Dec)
Project Information
Location: |  |  | ****** Galway Road (Co-ordinates ***********,***********) | [8 empty] | SA to identify the location - if co-ordinates are availble please include
Potential Construction Works Start Date: |  |  | 2023-02-06 | [8 empty] | SA to include estimated start date
Anticipated Construction Works Duration (Months): |  |  | 2 | [8 empty] | SA to include estimated time period / programme duration
Other Relevant Project Information: |  |  | New Footpath & Public Lighting | [8 empty] | SA to outline (brief) project scope of works
1 | Construction Costs
| Ref | Description |  |  |  |  | Incurred Costs |  | Forecast Costs (Including Tender Prices) |  | Total Cost (€)
| Main Contract(s) Costs (Please provide supplementary information giving detail of costs below) | [10 empty] | SA to give the elemental breakdown (summary) as per tender award
| 1.1 | Preliminaries (Includes Traffic Management) | [6 empty] | 18000 |  | 18000 | (SA to confirm source date in section below & assumptions tab)
| 1.2 | Site Clearance | [6 empty] | 5000 |  | 5000
| 1.3 | Fencing | [6 empty] | 3500 |  | 3500
| 1.4 | Drainage & Service Ducts | [6 empty] | 15000 |  | 15000
| 1.5 | Earth Works | [6 empty] | 35000 |  | 35000
| 1.6 | Pavements | [6 empty] | 65000 |  | 65000
| 1.7 | Kerbs, Footways & Paved Areas | [6 empty] | 22000 |  | 22000
| 1.8 | Traffic Signs & Road Markings | [6 empty] | 3500 |  | 3500
| 1.9 | Road Lighting Columns (Civils) | [6 empty] | 9500 |  | 9500
| 1.10 | CCTV Survey of Road Drainage Systems | [6 empty] | 4200 |  | 4200
| 1.11 | Specialist (Public Lighting Contractor) | [6 empty] | 17500 |  | 17500
| 1.12 | [9 empty] | 0
| 1.13 | [9 empty] | 0
| 1.14 | [9 empty] | 0
| 1.15 | [9 empty] | 0
| Sub-Total A - Project Base Costs | [9 empty] | 198200
2 | Preparation and Administration
| 2.1 | Preparation and Administration Costs | [8 empty] | 72100 | SA to confirm admin costs (design teams etc …)
| 2.1.1 | Scope & Purpose | [6 empty] | 5500 |  | 5500 | (for example purposes we have increased the fee amount - see assumptions tab for explanation)
| 2.1.2 | Concept, Development & Option Selection | [6 empty] | 7100 |  | 7100
| 2.1.3 | Preliminary Design | [6 empty] | 12000 |  | 12000
| 2.1.4 | Statutory Processes | [6 empty] | 15000 |  | 15000
| 2.1.5 | Detailed Design & Procurement | [6 empty] | 15000 |  | 15000
| 2.1.6 | Construction & Implementation | [6 empty] | 15000 |  | 15000
| 2.1.7 | Close Out & Review | [6 empty] | 2500 |  | 2500
| Sub-Total B - Preparation and Administration Costs | [9 empty] | 72100
3 | Traffic Management Related Costs
| 3.1 | Traffic Management Related Costs | [8 empty] | 0 | SA to confirm if cost is included in tender price - please state this in excel line C82 below
| Sub-Total C - Traffic Management Related Costs | [9 empty] | 0
4 | Land and Property Costs
| Ref | Description |  | Quantity | Unit | Rate | Incurred Costs |  | Forecast Costs to Complete |  | Total Cost (€)
| 4.1 | Land & Property Costs |  | 1 | Item | 47750 | 47750 |  |  |  | 47750 | SA to confirm final agreed land value price
| Sub-Total D - Land and Property Costs | [9 empty] | 47750
5 | Adjustments
| Add Project Specific Risk (Output From QRA-004_B1_QRA_CMG) | [5 empty] | 1 |  | Item | 41478.649 | 41478.649 | SA to include risk value (as completed in form 004) - If may be the same risk value (€) applies as per the Preliminary Cost Estimate
| Add Contingency (001_B123_CC_CMG) | [5 empty] | 10% |  | % | 198200 | 19820 | SA to include costs as per completed form 001
| Per Cent for Art Scheme https://publicart.ie/main/commissioning/funding/per-cent-for-art-scheme/ | [5 empty] | 1% |  | % | 198200 | 1982 | SA to review web link for proposed maximum limits. Figure to be amended in cell O67 if required.
| Sub-Total E - Adjustments | [9 empty] | 63280.649
Total Project Cost Estimate Exclusive of VAT | [10 empty] | 381330.649
VAT on Construction Costs, TM and Associated Adjustment Costs | [5 empty] | 13.5% |  | % | 261480.649 |  | 35299.8876 | 13.5% VAT is applied to the construction cost / risk allowance / contingency allowance
VAT on Preparation and Administration Costs and Associated Adjustment Costs | [5 empty] | 23% |  | % | 72100 |  | 16583 | 23% applies to preparation costs (design teams as an example): No VAT should be applied if design is in-house with the SA
VAT on Land and Property | [5 empty] | 1 |  | Item | 0 |  | 0
https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [11 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line B76 to determine if VAT is applicable
Total Project Cost Estimate Inclusive of VAT | [10 empty] | 433213.5366
Source of Cost Data (Please provide a brief narrative on the source of cost data in the box below)
Costs are based on tender return (MEAT) - consultants costs are also confirmed as previous (no increases)
Revision | Title | [5 empty] | Prepared By |  | Checked By |  | Issue Date
[7 empty] | Sally Gates |  | Michael Bunny |  | 2022-12-12 | SA to sign off (2 parties within their organisation)
NOTE: | Costs are considered to include allowances for overheads and profit. Costs are reflective of costs at the base date stated above. VAT is not applicable to all land and property therefore it is not appropriate to apply a uniform percentage. The value associated with VAT on land and property is to be determined on an individual basis and included as a lump sum.
Note on M74: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on M75: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on M76: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on O14: Estimating Methodology: Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## PCD Summary
Project Control Document Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document. | [7 empty] | Guidance Notes
Project Title: |  |  | R2 - Galway Road - Dublin |  |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  |  | DLR/22/0015G | Prepared By (Individual & Organisation) |  |  | Sally Gate - SDC | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  |  | MTA | Date Estimate Prepared: |  |  | 2022-12-12 | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  |  | South Dublin Council | Base Date of Estimate: |  |  | Q4 2022 | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | PCD Summary
| 1.1 | Scope & Purpose |  | 1 | Item | 5500 | 5500 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2 | Concept, Development & Option Selection |  | 1 | Item | 7100 | 7100 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.3 | Preliminary Design |  | 1 | Item | 12000 | 12000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.4 | Statutory Processes |  | 1 | Item | 15000 | 15000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.5 | Detailed Design & Procurement |  | 1 | Item | 15000 | 15000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.6 | Construction & Implementation |  | 1 | Item | 324230.649 | 324230.649 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.7 | Close Out & Review |  | 1 | Item | 2500 | 2500 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Total (excluding VAT) | [5 empty] | 381330.649
| Add VAT @ 13.5% | [5 empty] | 35299.8876 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Add VAT @ 23% | [5 empty] | 16583 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Add VAT on Land (If Applicable) | [5 empty] | 0 | SA to include if applicable pending Revenue rules
| Total Grant Application Cost Estimate (Including VAT) | [5 empty] | 433213.5366
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.
Note on J14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## Assumptions
Estimate Assumptions, Exclusions and Inclusions
[6 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/22/0015G |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  | MTA |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  | South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Prepared By (Individual/Organisation): |  | Sally Gate - SDC |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | Construction Costs
| Construction cost based on MEAT tender received in October 2022 |  |  |  |  | SA to confirm basis of the costs
2 | Delivery and Construction Programme
Tender process for construction has been completed in November 2022 and a contractor has be selected (MEAT) following receipt of 5 tender returns. Souht Dublin Council are seeking fuding Additional funding requested under active travel grant to commence scheme subject to approval of funding in Q4 of 2022 and complete scheme in quarter 1 of 2023
SA to give as much information as possible
3 | Preparation and Administration Costs
| Scheme has been designed in Q2 of 2022, the lead design team is ********* Ltd. There was an increase in fees (€12,100) as an Ecologist was required on site before main works commene due to a public complaint to investigate potential wildlifein the works area |  |  |  |  | SA to give as much information as possible
4 | Traffic Management Related Costs
| Traffic management costs are included in the main contractors price / tender |  |  |  |  | SA to give as much information as possible
5 | Land and Property Costs
| Costs are agreed in full €47,750 |  |  |  |  | SA to confirm if agreed or still estiamted - if agreed state agreed!
6 | Other Relevant Information
Any other relevant information, general assumptions, exclusions or inclusions that have been used to develop the cost estimate shall be included in this section.
Revision | Title |  | Prepared By | Checked By | Issue Date
|  |  | Sally Gate | Michael Bunny | 2022-12-12 | SA to sign off (2 parties within their organisation)

## Expenditure Profile
Expenditure Profile
[9 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin | [6 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/22/0015G | [6 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Tender Project Budget Cost Estimate: |  | 433213.5366 | [6 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab (Figure Includes VAT)
Anticipated Programme Duration: |  | 2 |  | Months |  |  |  |  | SA to confirm / imput programme
|  | Select Previous Cost Estimate |  | Total Project Cost - Estimate
Year | Quarter | Total Quarterly Expenditure (€) | Cumulative Expenditure (€) | Total Quarterly Expenditure (€) |  | Cumulative Expenditure (€)
Year 1 | Q1 |  | 0 |  |  | 0
| Q2 |  | 0 |  |  | 0
| Q3 |  | 0 |  |  | 0
| Q4 |  | 0 |  |  | 0
Year 2 | Q1 |  | 0 | 430963.97 |  | 430963.97 |  |  | SA to input the total cost (VAT inclusive)
| Q2 |  | 0 |  |  | 430963.97
| Q3 |  | 0 |  |  | 430963.97
| Q4 |  | 0 |  |  | 430963.97
Year 3 | Q1 |  | 0 |  |  | 430963.97
| Q2 |  | 0 |  |  | 430963.97
| Q3 |  | 0 |  |  | 430963.97
| Q4 |  | 0 |  |  | 430963.97
Year 4 | Q1 |  | 0 |  |  | 430963.97
| Q2 |  | 0 |  |  | 430963.97
| Q3 |  | 0 |  |  | 430963.97
| Q4 |  | 0 |  |  | 430963.97
Revision | Title |  |  |  | Prepared by | Checked by | Issue Date
[5 empty] | S Gate | M Bunny | 2022-12-12 | SA to sign off (2 parties within their organisation)
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Comparisons
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
Estimate Comparisons
[7 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin
Project / Contract Code: |  | DLR/22/0015G
Estimate Comparison
Ref | Item |  | Select Previous Cost Estimate | Total Project Cost | Variance
[5 empty] | € | %
1 | Construction Costs |  | 189115 | 198200 | 9085 | 4.804% | SA to complete - information from form 005 to be inserted (purple cells)
2 | Preparation and Administration Costs |  | 60000 | 72100 | 12100 | 20.17% | SA to complete - information from form 005 to be inserted (purple cells)
3 | Traffic Management Related Costs |  | 18911.5 | 0 | -18911.5 | -100% | Note - no cost in this example (see assumptions tab) - costs are included in main contractor price/tender
4 | Land and Property Costs |  | 47750 | 47750 | 0 | 0% | SA to complete - information from form 005 to be inserted (purple cells)
5 | Risk |  | 42567.45 | 41478.649 | -1088.801 | -2.558% | SA to complete - information from form 005 to be inserted (purple cells)
6 | Contingency |  | 62118.79 | 19820 | -42298.79 | -68.09% | SA to complete - information from form 005 to be inserted (purple cells)
7 | Per Cent for Art Scheme |  | 2000 | 1982 | -18 | -0.9% | SA to complete - information from form 005 to be inserted (purple cells)
8 | Total Costs (Cumulative) |  | 422462.74 | 381330.649 | -41132.091 | -9.736% | SA to complete - information from form 005 to be inserted (purple cells)
9 | Add VAT @ 13.5% |  | 42216.22 | 35299.8876 | -6916.3324 | -16.38%
10 | Add VAT @ 23% |  | 13800 | 16583 | 2783 | 20.17%
11 | Add VAT on Land (If Applicable) |  | 0 | 0 | 0 | 0%
12 | Total Costs (Including VAT) |  | 478478.96 | 433213.5366 | -45265.4234 | -9.46%
Programme Comparison
Ref | Item |  | Select Previous Cost Estimate | Total Project Budget | Variance
[5 empty] | Months | %
1 | Anticipated Programme Duration |  | 2 | 2 | 0 | 0% | SA to confirm (programme)
Commentary on Variances
If costs vary more than 10% or a value advised by NTA from the last cost estimate please provide a commentary in the space below:
If costs are greater than 10% (increase from Preliminary Cost Estimate) - a detailed explanation is required by the SA
Rev | Title |  |  | Prepared by | Checked by | Issue Date
|  |  |  | Sally Gates | Michael Bunny | 2022-12-12 | SA to sign off (2 parties within their organisation)

## Calculation Sheet
Calculation Sheet (Internal Use Only) | [5 empty] | Guidance Notes (If works carried out by direct labour - Example below) **** Figure are illustrative ****
Ref | Description | QTY | Unit | Rate | Total
| Labour |  |  |  |  | No VAT (13.5%) to be applied on SA direct labour costs
| - Supervisor (2 months) | 40 | day | 250 | 10000
| - General operative - 5 number (2 months) | 200 | day | 170 | 34000
| - Carpenter 2 number (1 months) | 40 | day | 200 | 8000
52000
Specialist Contractor (******** Utilities Limited)
| Public Lighting Works: -Supply & Installation of * No. 8m Octagonal Public Lighting Columns -Supply & Installation of * No. Fuse Units -Supply & Installation of * No. Urbis Axia LED Lanterns -Supply & Installation of * No. Photocell Units -Supply & Install * No. Unmetered Micro Pillar -* No. ESB Unmetered Connection Fees and Applications Complete -Supply & Install of PL Cable & Accessories as required -Testing and Commissioning included | 1 | item | 35000 | 35000
[5 empty] | 35000 | SA to include for VAT (13.5%) on specialist works contractor
| Materials |  |  |  |  | SA to include VAT on materials at 23%
| - Concrete | 200 | m3 | 135 | 27000
| - SR21 stone | 1500 | m3 | 25 | 37500
| - Timber 100 x 50mm (110 no 4.8m lengths) | 115 | no | 18 | 2070
| - Mesh A142 - 110 sheets | 110 | no | 50 | 5500
| - Kerbs | 560 | no | 20 | 11200
| - Lean mix | 50 | m3 | 120 | 6000
| - Nails | 1 | item | 3500 | 3500
| - Spray paint | 1 | item | 150 | 150
| - Ancillary hire tools | 1 | item | 4000 | 4000
| - PPE for staff (including signage) | 1 | item | 3500 | 3500
| - Portaloo hire for 2 months | 8 | weeks | 200 | 1600
102020
|  |  |  | 23% | 23464.6
125484.6