## Dashboard
Financial Dashboard - required on request from the NTA (not a specific requirement at all phases)
Pre-Construction Financial Dashboard | [8 empty] | * NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
SA, note form 008_B123 (Update) is only required if requested by the SPM / PM
Financial Reporting Template | [8 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
Project Title: |  | R5 - Navan Road - Dublin | [6 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  | DLR/22/001 5G | [5 empty] | Phase 1 - Scope and Purpose | SA confirm the project code
NTA Project Phase: |  | Phase 5 - Detailed Design and Procurement | [5 empty] | Phase 2 - Concept Development and Option Selection | SA to click cell - select from drop down menu
Report No: |  | 1 | [5 empty] | Phase 3 - Preliminary Design | Sa to confirm dash board number
Date: |  | 2023-03-14 | [5 empty] | Phase 4 - Statutory Processes | SA to confirm date of issue
Phase 5 - Detailed Design and Procurement
Description |  |  |  | Cost (€) - Excluding VAT |  | Construction Period (Weeks)
Current Cost Estimate |  |  |  | 1365180.19 |  | 16 |  |  | SA to include the current cost to date (form 016_B23) & estimated programme duration
Impact of Situation Notifications |  |  |  | 0 |  | 0 |  |  | Note - no actions for SA unless situation notices below are compiled
Forecast Revised Cost Estimate |  |  |  | 1365180.19 |  | 16
Situation Notifications
Provide details of the situation notifications raised that may give rise to cost and time implications
Reference | Description | Anticipated Impact |  | Status (Open / Closed) | Current Actions |  |  |  | SA to compile if they are aware of any situation notices
|  | € | Time (weeks) | [5 empty] | (note, at this stage (phase 5), known SN should be included in current cost above
Open
Closed
Total Anticipated Impact: |  | 0 | 0
Key Risks / Opportunities
Provide a brief summary on the live key project risks and opportunities
Reference | Risk / Opportunity Description | Risk Owner (Individual & Organisation) |  |  | Current Actions |  |  |  | SA to list out potential risks to the project
(for example purposes - risks are identified on the QRA register and costs are included into form 016_B23)
Revision | Status |  |  | Prepared By | Date | Checked By | Date
|  |  |  | Sally Gate | 2023-03-14 | Michael Bunny | 2023-03-14 |  | SA to sign off (2 parties within their organisation)