## Dashboard
Pre-Construction Financial Dashboard | [8 empty] | * NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional line etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
Financial Dashboard - required on request from the NTA (not a specific requirement at all phases)
Financial Reporting Template | [8 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment | [6 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  | DLR/12/0015A | [5 empty] | Phase 1 - Scope and Purpose | SA confirm the project code
NTA Project Phase: |  | Phase 3 - Preliminary Design | [5 empty] | Phase 2 - Concept Development and Option Selection | SA to click cell - select from drop down menu
Report No: |  | 1 | [5 empty] | Phase 3 - Preliminary Design | Sa to confirm dash board number
Date: |  | 2016-08-08 | [5 empty] | Phase 4 - Statutory Processes | SA to confirm date of issue
Phase 5 - Detailed Design and Procurement
Description |  |  |  | Cost (€) - Excluding VAT |  | Construction Period (Weeks)
Current Cost Estimate |  |  |  | 59946198.04 |  | 104 |  |  | SA to include the current cost to date & estimated programme duration
Impact of Situation Notifications |  |  |  | 0 |  | 0 |  |  | Note - no actions for SA unless situation notices below are compiled
Forecast Revised Cost Estimate |  |  |  | 59946198.04 |  | 104
Situation Notifications
Provide details of the situation notifications raised that may give rise to cost and time implications
Reference | Description | Anticipated Impact |  | Status (Open / Closed) | Current Actions |  |  |  | SA to compile if they are aware of any situation notices
|  | € | Time (weeks) | [5 empty] | (note, at this stage (phase 1), known SN should be included in current cost above
Open
Closed
Total Anticipated Impact: |  | 0 | 0
Key Risks / Opportunities
Provide a brief summary on the live key project risks and opportunities
Reference | Risk / Opportunity Description | Risk Owner (Individual & Organisation) |  |  | Current Actions |  |  |  | SA to list out potential risks to the project
1 | Irish Water | IW |  |  | SA & Design Team liaising with relevant contact
2 | ESB ducting | ESB |  |  | SA & Design Team liaising with relevant contact
3 | Unknown Utility (protections) | IW / ESB / Eir |  |  | SA & Design Team liaising with relevant contact
4 | Delays due to land take (possible CPO's) | SA |  |  | SA liaising with the effected parties to agree
Revision | Status |  |  | Prepared By | Date | Checked By | Date
|  |  |  | Sally Gate | 2016-08-08 | Michael Bunny | 2016-08-08 |  | SA to sign off (2 parties within their organisation)
Formulas:
Date = [Current Actions]