## Sheet1 (hidden)
COMPENSATION EVENT NOTIFICATION BY THE CONTRACTOR
Project number: |  |  |  | 20234
Description: |  |  |  | Abercynon Primary School, Rhondda Cynon Taf County Borough Council.
Contract number:
Compensation Event Number: | [6 empty] | 1 |  |  |  | EWN Ref No.: |  |  | 1
To: (The Project Manager) |  |  | CHANDLERKBS
Address: |  |  | Chandlers House, Terra Nova Way, Penarth Marina, Cardiff. CF64 1SA
Attention: |  |  | GERWYN BOWDEN
The compensation event is as per clause 60.1 sub-paragraph:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
The event started to occur on: | [7 empty] | Day |  |  |  | Month |  |  |  | Year
The details of the event are as follows:
The date of this notification is: (not more than eight weeks after the Contractor became aware of it) | [8 empty] | Day |  |  |  | Month |  |  |  | Year
Notified by Contractor:
|  | Signature | [5 empty] | Name | [5 empty] | Date
Distribution: |  |  |  | D. POWELL (RCT) |  |  |  | S. MANTLE (RCT) |  |  |  | W. GANDERTON (DL) |  |  |  | S. TREW (STD)
C.ARNOLD (AFPM) |  |  |  | P. GREEN (RCT) |  |  |  | A. KING (WYG) |  |  |  | G.GRAHAM (RCT) |  |  |  | G. NEALE (WD)

## Summary
Sheet is not locked to allow Sponsoring Agencies to add in additional tabs for additional situation notices
Situation Notices - only required where necessary (not a specific requirement at all phases unless they (situations of concern - cost / delays) arise)
[11 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
Situation Notification Summary
Project Title: |  | R5 - Navan Road - Dublin | [8 empty] | Sponsoring Agency (SA) to list out the project title
Phase 2 - Concept Development and Option Selection
Project / Contract Code: |  | DLR/22/0015G | [7 empty] | Phase 3 - Preliminary Design | SA confirm the project code
Phase 4 - Statutory Processes
Project Phase: |  | Phase 3 - Preliminary Design | [7 empty] | Phase 5 - Detailed Design and Procurement | SA to confirm current phase
Phase 6 - Construction and Implementation
SN Reference | Description |  | Status | Impact Current Project Band Categorisation | Impact Value for Money Assessment | Impact on Project Affordability | Delay to Project/Phase Completion or Meeting a Key Date | Cost | Delay
|  |  |  | Tick As Appropriate |  |  |  | € | Weeks
SN 01 | Irish Water & ESB requirements |  | Open |  |  |  |  | 40000 | 8 | Open | SA to list out the SN and tick as apprpiate
SN 02 | CPO - increased in land take | [6 empty] | 100000 | 0 | Closed
SN 03
SN 04
SN 05
Total Impact: | [7 empty] | 140000 | 8

## SN 01
[14 empty] | * All cells in purple - input is required | *** Figures are illustrative ***
Situation Notification
Project Title: |  |  |  |  | R5 - Navan Road - Dublin | [8 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  |  |  | DLR / 22 / 0015G | [8 empty] | SA confirm the project code
Phase 2 - Concept Development and Option Selection
Project Phase: |  |  |  |  | Phase 3 - Preliminary Design | [5 empty] | Phase 3 - Preliminary Design |  |  | SA to confirm current phase
Phase 4 - Statutory Processes
Description of the Situation: |  |  |  |  | Irish Water & ESB - Scope of Works | [5 empty] | Phase 5 - Detailed Design and Procurement |  |  | SA to confirm the description of the situation
Phase 6 - Construction and Implementation
Situation Notification Number: |  |  |  |  | 1 |  | Date of this Situation Notification: |  |  | 2018-07-04 |  |  |  | SA to confirm the SN number & date of the notice issue
To (Organisation): |  | National Transport Authority | [11 empty] | SA to confirm (if the works are been prepared by a consultant, then they are adressing the sponsoring agency)
Address: |  | ************
Attention (Individual): |  | Mrs ************
The matter notified is as follows:
Meeting required to finalsie Irish Water & ESB - early indications are proposing they both require services in the ground. The local authroity design team need specific requirements as the local authroity are at optinos selection stage (phase 2) | [13 empty] | SA to confirm the situation (more detail is preferred)
[12 empty] | 0 | 0
The Event Could |  |  |  | Impact Current Project Band Categorisation |  | Impact Value for Money Assessment | Impact on Project Affordability |  | Delay to Project/Phase Completion or Meeting a Key Date
Tick as Appropriate
SA to tick what is applicable
Measure of Impact |  |  |  | Cost |  | Delay
Measure of Impact |  |  |  | € |  | Weeks
Estimate of Impact (excluding VAT where applicable) |  |  |  | 40000 |  | 8
SA to confirm estimated value & delay time
|  |  |  | Contractor |  | Designer / Engineering Consultant | Sponsoring Agency |  | Approving Authority | Other(s)
Required to Attend Follow Up Meeting
SA to tick what is applicable
Individual(s) Required to Attend | [5 empty] | **** | **** |  | **** | Irish Water / ESB
| Sally Gate |  |  |  |  | Sally Gate |  |  | 2018-07-04
Notified by: | [13 empty] | SA (or consultant) to sign off
| Signature (Digitally Insert) |  |  |  |  | Name |  |  | Date
Distribution: |  |  | local Authority |  |  | Design Team |  | NTA | [5 empty] | SA to confirm distribution list

## SN 02
[12 empty] | * All cells in purple - input is required | *** Figures are illustrative ***
Situation Notification
Project Title: |  |  |  | R5 - Navan Road - Dublin | [7 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  |  | DLR / 22 / 0015G | [7 empty] | SA confirm the project code
Phase 2 - Concept Development and Option Selection
Project Phase: |  |  |  | Phase 3 - Preliminary Design |  |  |  |  | Phase 3 - Preliminary Design |  |  | SA to confirm current phase
Phase 4 - Statutory Processes
Description of the Situation: |  |  |  | Compulsory Purchase Orders - Agents are advising an increase in costs (potential - final costs TBA) |  |  |  |  | Phase 5 - Detailed Design and Procurement |  |  | SA to confirm the description of the situation
Phase 6 - Construction and Implementation
Situation Notification Number: |  |  |  | 2 |  | Date of this Situation Notification: |  | 2018-07-04 |  |  |  | SA to confirm the SN number & date of the notice issue
To (Organisation): |  | National Transport Authority | [9 empty] | SA to confirm (if the works are been prepared by a consultant, then they are adressing the sponsoring agency)
Address: |  | ************
Attention (Individual): |  | Mrs ************
The matter notified is as follows:
All parties are avtively in discussions ……… the estate agents are advising a potential €100,000 increase on previous estiamtes. Work is actively on going to agree costs. | [11 empty] | SA to confirm the situation (more detail is preferred)
[10 empty] | 0 | 0
The Event Could |  |  | Impact Current Project Band Categorisation |  | Impact Value for Money Assessment | Impact on Project Affordability | Delay to Project/Phase Completion or Meeting a Key Date
Tick as Appropriate
SA to tick what is applicable
Measure of Impact |  |  | Cost |  | Delay
Measure of Impact |  |  | € |  | Weeks
Estimate of Impact (excluding VAT where applicable) |  |  | 100000 |  | 0
SA to confirm estimated value & delay time
|  |  | Contractor |  | Designer / Engineering Consultant | Sponsoring Agency | Approving Authority | Other(s)
Required to Attend Follow Up Meeting
SA to tick what is applicable
Individual(s) Required to Attend |  |  |  |  | ***** | **** |  | Estate Agents
| Sally Gate |  |  |  | Sally Gate |  | 2018-07-04
Notified by: | [11 empty] | SA (or consultant) to sign off
| Signature (Digitally Insert) |  |  |  | Name |  | Date
Distribution: | [11 empty] | SA to confirm distribution list