## Band 2
Band 2 (€0.5 - €10 Million) Project Checklist | [5 empty] | * NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
[6 empty] | Guidance Notes | * All cells in purple - input is required
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 1 Scope and Purpose | Financial Reporting | 008_B23_FR_CMG |  | Sally Gate | 2022-05-04 | Sign off required by the SA
| Contingency Quantification | 001_B123_CC_CMG |  | Sally Gate | 2022-05-04 | Sign off required by the SA
| Grant Application Cost Estimate and Confirmation of Land Requirement | 002_B123_GACE_CMG |  | Sally Gate | 2022-05-04 | Sign off required by the SA
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
| Sponsoring Agency: |  | Sally Gate | Sally Gate | 2022-05-04 | Sign off required by the SA
| Approving Authority: |  | Joe Bloggs | Joe Bloggs | 2022-05-09 | Sign off by the NTA SPM or PM
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 2 Concept Development and Option Selection | Financial Reporting | 008_B23_FR_CMG |  |  |  | Note, if no update applicable - no need to include (agree with NTA SPM / PM prior)
| Contingency Quantification | 001_B123_CC_CMG |  | Sally Gate | 2022-07-09 | Sign off required by the SA
| Option Comparision Cost Estimates | 011_B23_OCCE_CMG |  | Sally Gate | 2022-07-09 | Sign off required by the SA
| Feasibility Working Cost Estimate for Preferred Route & Expenditure Profile | 012_B23_FWCE_CMG |  | Sally Gate | 2022-07-09 | Sign off required by the SA
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
| Sponsoring Agency: |  | Sally Gate | Sally Gate | 2022-07-09 | Sign off required by the SA
| Approving Authority: |  | Joe Bloggs | Joe Bloggs | 2022-07-16 | Sign off by the NTA SPM or PM
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 3 Preliminary Design | Financial Reporting | 008_B23_FR_CMG
| Contingency Quantification | 001_B123_CC_CMG |  |  | 2022-10-25
| Risk Quantification | 013_B23_QRA_CMG |  |  | 2022-10-25
| Preliminary Cost Estimate, Expenditure Profile & Cost Estimate Report | 014_B23_PCE_CMG/ 015_B23_CER_CMG |  |  | 2022-10-25
| Whole Life Cost Analysis | N/A
| Value Management, Value Engineering & Value Management Report | N/A
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
| Sponsoring Agency: |  | Sally Gate | Sally Gate | 2022-10-25 | Sign off required by the SA
| Approving Authority: |  | Joe Bloggs | Joe Bloggs | 2022-11-03 | Sign off by the NTA SPM or PM
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 4 Statutory Processes - If instructed on a project-by-project basis | Financial Reporting | 008_B23_FR_CMG
| Value Management, Value Engineering & Value Management Report | N/A
| Contingency Quantification | 001_B123_CC_CMG
| Risk Quantification | 013_B23_QRA_CMG
| Updated Preliminary Cost Estimate, Expenditure Profile & Cost Estimate Report | 016_B23_UPCE_CMG/ 015_B23_CER_CMG
| Independent Peer Report of Updated Preliminary Cost Estimate | N/A
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
Sponsoring Agency:
Approving Authority:
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 5 Detailed Design and Procurement | Financial Reporting | 008_B23_FR_CMG
| Pre-Tender Cost Estimate & Cost Estimate Report | 017_B23_PTCE_CMG/ 015_B23_CER_CMG
| Independent Peer Review of Pre-Tender Estimate | N/A
| Development of Commercial Tender Documentation | N/A
| Commercial Assessment of Tender Returns and Preparation of Commercial Tender Assessment Report | N/A
| Contingency Quantification | 001_B123_CC_CMG
| Risk Quantification | 013_B23_QRA_CMG
| Total Project Cost, Expenditure Profile & Cost Estimate Report | 018_B23_TPCE_CMG/ 015_B23_CER_CMG
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
Sponsoring Agency:
Approving Authority:

## Band 3
Band 3 (€10 Million+) Project Checklist
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 1 Scope and Purpose | Financial Reporting | 008_B23_FR_CMG
| Contingency Quantification | 001_B123_CC_CMG
| Grant Application Cost Estimate and Confirmation of Land Requirement | 002_B123_GACE_CMG
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
Sponsoring Agency:
Approving Authority:
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 2 Concept Development and Option Selection | Financial Reporting | 008_B23_FR_CMG
| Contingency Quantification | 001_B123_CC_CMG
| Option Comparision Cost Estimates | 011_B23_OCCE_CMG
| Feasibility Working Cost Estimate for Preferred Route & Expenditure Profile | 012_B23_FWCE_CMG
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
Sponsoring Agency:
Approving Authority:
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 3 Preliminary Design | Financial Reporting | 008_B23_FR_CMG
| Contingency Quantification | 001_B123_CC_CMG
| Risk Quantification | 013_B23_QRA_CMG
| Preliminary Cost Estimate, Expenditure Profile & Cost Estimate Report | 014_B23_PCE_CMG/ 015_B23_CER_CMG
| Whole Life Cost Analysis | N/A
| Value Management, Value Engineering & Value Management Report | N/A
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
Sponsoring Agency:
Approving Authority:
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 4 Statutory Processes | Financial Reporting | 008_B23_FR_CMG
| Value Management, Value Engineering & Value Management Report | N/A
| Contingency Quantification | 001_B123_CC_CMG
| Risk Quantification | 013_B23_QRA_CMG
| Updated Preliminary Cost Estimate, Expenditure Profile & Cost Estimate Report - Band 3 Only | 016_B23_UPCE_CMG/ 015_B23_CER_CMG
| Independent Peer Report of Updated Preliminary Cost Estimate | N/A
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
Sponsoring Agency:
Approving Authority:
Phase | Deliverable | Document Ref. | Complete | Completed By | Date Complete
Phase 5 Detailed Design and Procurement | Financial Reporting | 008_B23_FR_CMG
| Pre-Tender Cost Estimate & Cost Estimate Report | 017_B23_PTCE_CMG/ 015_B23_CER_CMG
| Independent Peer Review of Pre-Tender Estimate | N/A
| Development of Commercial Tender Documentation | N/A
| Commercial Assessment of Tender Returns and Preparation of Commercial Tender Assessment Report | N/A
| Contingency Quantification | 001_B123_CC_CMG
| Risk Quantification | 013_B23_QRA_CMG
| Total Project Cost, Expenditure Profile & Cost Estimate Report | 018_B23_TPCE_CMG/ 015_B23_CER_CMG
Phase Sign Off on Behalf Of: |  |  | Print Name | Signature (Digital) | Date
Sponsoring Agency:
Approving Authority: