## Risk Process_RR Explanation
RISK PROCESS
The process of project risk review follows a 3-step process:
Identification – what might go wrong?
Assessment – what is the likelihood and impact of each risk?
Management – What are the mitigation measures and who will own the risk, client or contractor?
What are the actions required?
RISK REGISTER EXPLANATION
Please note within TAB : Risk Register (RR) - there are comments added to the cells to provide additional guidance when completing
RISK MATRIX | [9 empty] | COST MATRIX
HIGH RISK | Overall Risk = Impact x Probability |  |  |  | PROBABILITY (RANK) |  |  |  |  | Project Risk Matrix
MEDIUM RISK |  |  |  |  | Negligible | Unlikely | Possible | Probable | Almost Certain | CAT | IMPACT | Prob (Average) | Min Cost | Min Cost % per CAT | Most Likely | Average Cost % per CAT | Max Cost | Max Cost % per CAT
LOW RISK |  |  |  |  | Very Low | Low | Medium | High | Very High | 5 | VH | 90% | 68259.0095 | 5% | 102388.5143 | 7.5% | 136518.019 | 10%
[5 empty] | <5% | 6-20% | 21-50% | 51-80% | >80% | 4 | H | 65.5% | 40955.4057 | 3% | 54607.2076 | 4% | 68259.0095 | 5%
[5 empty] | ① | ② | ③ | ④ | ⑤ | 3 | M | 35.5% | 13651.8019 | 1% | 27303.6038 | 2% | 40955.4057 | 3%
IMPACT | > 5% | Major | Very High / Showstopper | ⑤ | 5 | 10 | 15 | 20 | 25 | 2 | L | 13% | 6825.901 | 0.5% | 10238.8514 | 0.75% | 13651.8019 | 1%
| 3 to 5% | Large | High | ④ | 4 | 8 | 12 | 16 | 20 | 1 | VL | 2.5% | 1365.1802 | 0.1% | 4095.5406 | 0.3% | 6825.901 | 0.5%
| 1 to 3% | Moderate | Medium | ③ | 3 | 6 | 9 | 12 | 15
| 0.5 to 1% | Minor | Low | ② | 2 | 4 | 6 | 8 | 10 | 1365180.19 | Base Cost Estimate (Construction, Preparation & Administration and Traffic Management)
| < 0.5% | Minimal | Very Low | ① | 1 | 2 | 3 | 4 | 5
| Cost as % of Project cost (not just fees) | Quality | Overall IMPACT | CAT | Cost / time and quality may be affected differently by a single risk. If overall risk is required, use the most severe affected component or give consideration to managing each separately.
COMPLETION OF RISK REGISTER
STEP 1 | Define the project COST MATRIX and update the tables opposite accordingly. (Update U26)
STEP 2 | Identify Review Stages, when project risks will be reviewed and @Risk Run
STEP 3 | Identify the project Risk Owners and update TAB: RR_Drop Downs accordingly.
STEP 4 | Identify the project Categories to which each risk will be assigned and update TAB: RR_Drop Downs accordingly.
STEP 5 | Identify each risk and complete the RISK DESCRIPTION
STEP 6 | Review the INITIAL RISK EXPOSURE i.e. the worse case scenario pre- mitigation and continguency planning
utilising the Risk Matrix to assign the Probability RANK and the Cost Matrix to assign the CAT.
The applicable cells auto-populate and provide a COST IMPACT along with a RISK RATING.
STEP 7 | Complete the RESPONSE column which details the proposed Mitigation and Contingencies to be applied in order to reduce the Risk.
STEP 8 | Once the RESPONSE is completed review the RESIDUAL RISK EXPOSURE. Again using the Risk Matrix to assign the Probability RANK and the Cost Matrix to assign the CAT.
STEP 9 | Assign a RISK OWNER, who will be responsible for ensuring the applicable actions defined in the RESPONSE column are undertaken.
STEP 10 | Agree STATUS with Client and assign a REVIEW DATE for each Risk.

## Risk Register (RR)
Project Risk Register | [6 empty] | * All cells in purple - input is required
Guidance Notes
Project Title: |  |  | R5 - Navan Road - Dublin |  |  |  | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/22/001 5G |  |  |  | SA confirm the project code
Current Project Phase: |  |  | Phase 5 - Detailed Design and Procurement |  |  |  | SA to select from the drop down cell the current phase | [16 empty] | Phase 3 - Preliminary Design
Phase 4 - Statutory Process
Capital Cost Estimate (Construction, Preparation & Administration and Traffic Management): |  |  | 1365180.19 |  |  |  | SA to input the cost estimate amount from form 016_B23 (Updated Preliminary Cost Estimate) | [16 empty] | Phase 5 - Detailed Design and Procurement
Date: |  |  | 2023-03-14 | [5 empty] | SA to list probability rank (1-5: 5 been the highest) | [8 empty] | Note, Costs will default across once probability & risk exposure is confirmed
RISK | RISK | DATE | RISK | CATEGORY | RISK | TECHNICAL | RISK DESCRIPTION | RESPONSE | RISK EXPOSURE | [8 empty] | CONSTRUCTION RISK VALUE |  |  | Status | Register | REVIEW COMMENTS
RANK | ID | IDENTIFIED | OWNER |  | / OPPORTUNITY | DISCIPLINE | (Describe Cost, Programme & Quality Impacts) Note: Qualitative Costs associated with review contain within Initial Risk Exposure and Residual Risk Exposure | (Mitigation [M] and/or Contingency [C]) | PROBABILITY |  |  | COST IMPACT (£) |  |  |  |  | RISK RATING | 136.518 | 409.5541 | 682.5901 |  | Review Date
[9 empty] | RANK |  | % | CAT |  | Min | Most Likely | Max | (P x CI) | Min | Most Likely | Max
| R1 |  | Contractor | Tender Actions / Procurement | Risk | Construction | Loss or damage to materials/plant due to War, strikes, radioactive contamination etc. Delays and cost over-runs. |  | 1 | VL | 2.5% | 1 | VL | 1365.1802 | 4095.5406 | 6825.901 | 1 | 34.1295 | 102.3885 | 170.6475 | Residual |  | Contractor Risk
| R2 |  | Contractor | Tender Actions / Procurement | Risk | Construction | Shortage in availability of key materials. Disruption to work and delay to overall programme. | Early engagement with contractor - ensure that the risk is added to contractor risk register. | 1 | VL | 2.5% | 1 | VL | 1365.1802 | 4095.5406 | 6825.901 | 1 | 34.1295 | 102.3885 | 170.6475 | Residual |  | Contractor Risk
| R3 |  | Contractor | Construction | Risk | Contractor | Contractor causes damage to existing infrastructure - power, communication, damages assets. Delay claims from stakeholders. Cost Impact. |  | 1 | VL | 2.5% | 1 | VL | 1365.1802 | 4095.5406 | 6825.901 | 1 | 34.1295 | 102.3885 | 170.6475 | Residual |  | Contractor Risk
| R4 |  | SA | Construction | RISK | Contractor | Irish Water - additional scope | Continous engagement with IW engineers | 1 | VL | 2.5% | 1 | VL | 1365.1802 | 4095.5406 | 6825.901 | 1 | 34.1295 | 102.3885 | 170.6475 | Residual |  | SA Risk
[17 empty] | Cumulative Risk Value: | 136.518 | 409.5541 | 682.5901
[12 empty] | SA to list risk exposure rank (1-5: 5 been the highest) |  |  |  |  | Average Cumulative Risk: |  | 409.5541

## RR_Drop Downs
RISK REGISTER DROP DOWN MENUs TAB : Risk Register (RR)
RISK OWNER (Column D) | ROLE | CATEGORY (Column E) | SEVERITY CATEGORY (See TAB : Risk Process_RR Explanation) | RISK OR OPPORTUNITY (Column F) | TECHNICAL DISCIPLINE (Column G) | STATUS (Column AG)
TBC | TBC | Funding | Programme / Budget | Risk | Client | Pending
TBC | TBC | Programme | Programme / Budget | Opportunity | Project Management | Residual
TBC | TBC | Design / Scope Change | Technical |  | Highways | Closed
TBC | TBC | Environmental | Technical |  | Structures
TBC | TBC | Statutory Authorities (inc. Statutory Undertakers) | Technical |  | Environmental
TBC | TBC | Resources | Programme / Budget |  | Geotech
TBC | TBC | Procurement | Programme / Budget |  | Structures
|  | Approvals (Statutory / Overseeing Organisation) | Technical |  | Drainage & Flooding
|  | Products / Materials | Technical |  | Land Services
|  | Construction | Technical |  | Contractor
|  | Client | Programme / Budget
|  | Health & Safety | SHE
|  | Reputation | Reputation