## Risk Process_RR Explanation
RISK PROCESS
The process of project risk review follows a 3-step process:
Identification – what might go wrong?
Assessment – what is the likelihood and impact of each risk?
Management – What are the mitigation measures and who will own the risk, client or contractor?
What are the actions required?
RISK REGISTER EXPLANATION
Please note within TAB : Risk Register (RR) - there are comments added to the cells to provide additional guidance when completing
RISK MATRIX | [9 empty] | COST MATRIX
HIGH RISK | Overall Risk = Impact x Probability |  |  |  | PROBABILITY (RANK) |  |  |  |  | Project Risk Matrix
MEDIUM RISK |  |  |  |  | Negligible | Unlikely | Possible | Probable | Almost Certain | CAT | IMPACT | Prob (Average) | Min Cost | Min Cost % per CAT | Most Likely | Average Cost % per CAT | Max Cost | Max Cost % per CAT
LOW RISK |  |  |  |  | Very Low | Low | Medium | High | Very High | 5 | VH | 90% | 1884151.63 | 5% | 2826227.445 | 7.5% | 3768303.26 | 10%
[5 empty] | <5% | 6-20% | 21-50% | 51-80% | >80% | 4 | H | 65.5% | 1130490.978 | 3% | 1507321.304 | 4% | 1884151.63 | 5%
[5 empty] | ① | ② | ③ | ④ | ⑤ | 3 | M | 35.5% | 376830.326 | 1% | 753660.652 | 2% | 1130490.978 | 3%
IMPACT | > 5% | Major | Very High / Showstopper | ⑤ | 5 | 10 | 15 | 20 | 25 | 2 | L | 13% | 188415.163 | 0.5% | 282622.7445 | 0.75% | 376830.326 | 1%
| 3 to 5% | Large | High | ④ | 4 | 8 | 12 | 16 | 20 | 1 | VL | 2.5% | 37683.0326 | 0.1% | 113049.0978 | 0.3% | 188415.163 | 0.5%
| 1 to 3% | Moderate | Medium | ③ | 3 | 6 | 9 | 12 | 15
| 0.5 to 1% | Minor | Low | ② | 2 | 4 | 6 | 8 | 10 | 37683032.6 | Base Cost Estimate (Construction, Preparation & Administration and Traffic Management)
| < 0.5% | Minimal | Very Low | ① | 1 | 2 | 3 | 4 | 5
| Cost as % of Project cost (not just fees) | Quality | Overall IMPACT | CAT | Cost / time and quality may be affected differently by a single risk. If overall risk is required, use the most severe affected component or give consideration to managing each separately.
COMPLETION OF RISK REGISTER
STEP 1 | Define the project COST MATRIX and update the tables opposite accordingly. (Update U26)
STEP 2 | Identify Review Stages, when project risks will be reviewed and @Risk Run
STEP 3 | Identify the project Risk Owners and update TAB: RR_Drop Downs accordingly.
STEP 4 | Identify the project Categories to which each risk will be assigned and update TAB: RR_Drop Downs accordingly.
STEP 5 | Identify each risk and complete the RISK DESCRIPTION
STEP 6 | Review the INITIAL RISK EXPOSURE i.e. the worse case scenario pre- mitigation and continguency planning
utilising the Risk Matrix to assign the Probability RANK and the Cost Matrix to assign the CAT.
The applicable cells auto-populate and provide a COST IMPACT along with a RISK RATING.
STEP 7 | Complete the RESPONSE column which details the proposed Mitigation and Contingencies to be applied in order to reduce the Risk.
STEP 8 | Once the RESPONSE is completed review the RESIDUAL RISK EXPOSURE. Again using the Risk Matrix to assign the Probability RANK and the Cost Matrix to assign the CAT.
STEP 9 | Assign a RISK OWNER, who will be responsible for ensuring the applicable actions defined in the RESPONSE column are undertaken.
STEP 10 | Agree STATUS with Client and assign a REVIEW DATE for each Risk.

## Risk Register (RR)
Project Risk Register | [6 empty] | * All cells in purple - input is required
Guidance Notes
Project Title: |  |  | Highways Improvement for Urban Environment |  |  |  | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/22/001 5G |  |  |  | SA confirm the project code
Current Project Phase: |  |  | Phase 4 - Statutory Process |  |  |  | SA to select from the drop down cell the current phase | [16 empty] | Phase 3 - Preliminary Design
Phase 4 - Statutory Process
Capital Cost Estimate (Construction, Preparation & Administration and Traffic Management): |  |  | 37683032.6 |  |  |  | SA to input the cost estimate amount from form 014_B23 (Preliminary Cost Estimate) | [16 empty] | Phase 5 - Detailed Design and Procurement
Date: |  |  | 2021-07-06 | [5 empty] | SA to list probability rank (1-5: 5 been the highest) | [8 empty] | Note, Costs will default across once probability & risk exposure is confirmed
RISK | RISK | DATE | RISK | CATEGORY | RISK | TECHNICAL | RISK DESCRIPTION | RESPONSE | RISK EXPOSURE | [8 empty] | CONSTRUCTION RISK VALUE |  |  | Status | Register | REVIEW COMMENTS
RANK | ID | IDENTIFIED | OWNER |  | / OPPORTUNITY | DISCIPLINE | (Describe Cost, Programme & Quality Impacts) Note: Qualitative Costs associated with review contain within Initial Risk Exposure and Residual Risk Exposure | (Mitigation [M] and/or Contingency [C]) | PROBABILITY |  |  | COST IMPACT (£) |  |  |  |  | RISK RATING | 5185185.2858 | 8448064.871 | 11710944.4563 |  | Review Date
[9 empty] | RANK |  | % | CAT |  | Min | Most Likely | Max | (P x CI) | Min | Most Likely | Max
| 2.3 | 2019-01-02 | XXX CC | Project Organisation | Risk | Budgets / Finance | Inadequate Project Budget or Contingency Provision. Cost over-runs, reputational damage and need to seek additional funding. | Ongoing monitoring and reporting on budget, along with mitigation of specific risks. NTA cost management reports submitted and reviewed monthly. | 1 | VL | 2.5% | 1 | VL | 37683.0326 | 113049.0978 | 188415.163 | 1 | 942.0758 | 2826.2274 | 4710.3791 | Residual |  | Manageable cost impact
| 7.10 | 2019-01-02 | Contractor | Construction | Risk | Construction | Poor Quality Workmanship- Impact on construction output quality. |  | 4 | H | 65.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 12 |  |  |  | Residual |  | Contractor Risk
| 5.9 | 2019-01-02 | Contractor | Tender Actions / Procurement | Risk | Construction | Loss or damage to materials/plant due to War, strikes, radioactive contamination etc. Delays and cost over-runs. |  | 1 | VL | 2.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 5 |  |  |  | Residual |  | Contractor Risk
| 5.3 | 2019-01-02 | Contractor | Tender Actions / Procurement | Risk | Construction | Shortage in availability of key materials. Disruption to work and delay to overall programme. | Early engagement with contractor - ensure that the risk is added to contractor risk register. | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 |  |  |  | Residual |  | Contractor Risk
| 10.1 | 2019-01-02 | Contractor | Construction | Risk | Contractor | Contractor causes damage to existing infrastructure - power, communication, damages assets. Delay claims from stakeholders. Cost Impact. |  | 3 | M | 35.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 12 |  |  |  | Residual |  | Contractor Risk
| 7.16 | 2021-10-22 | XXX CC | Construction | Risk | Cost Estimation | Risk that covid outbreak causes increased H&S measures to be required. | Works issued via framework, utilising existing suppliers. | 2 | L | 13% | 2 | L | 188415.163 | 282622.7445 | 376830.326 | 4 | 24493.9712 | 36740.9568 | 48987.9424 | Residual
| 5.10 | 2021-10-22 | XXX CC | Tender Actions / Procurement | Risk | Cost Estimation | Materials costs may continue to suffer significant inflationary pressure resulting in increased cost. | Tender to be awarded prior to expiry of tender validity. Potential vesting and early procurement of materials. | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 | 48987.9424 | 97975.8848 | 146963.8271 | Residual
| 5.2 | 2019-01-02 | Contractor | Tender Actions / Procurement | Risk | Cost Estimation | Contractors Material / PDESIGNERuct pricing based on inadequate specification. Potential impact on finished duct. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 |  |  |  | Residual |  | Contractor Risk
| 5.1 | 2019-01-02 | Contractor | Tender Actions / Procurement | Risk | Cost Estimation | Inadequate Pricing / Below Cost Tendering by Contractor. Delays and cost over-runs. Prolonged traffic disruption. |  | 2 | L | 13% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 10 |  |  |  | Residual |  | Contractor Risk
| 7.13 | 2019-01-02 |  | Construction | Risk | Design / Tender Docs | Existing road pavement requires extensive repair works - noting previous instruction that full depth construction should be removed from the Contract. |  | 3 | M | 35.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 12 |  |  |  | Closed
| 6.8 | 2021-10-22 | XXX CC | Project Design | Risk | Design / Tender Docs | Design of taxi ranks is still to be finalised and may require amendments. | Early engagement with stakeholders to finalise design. | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 | 133774.7657 | 267549.5315 | 401324.2972 | Residual
| 6.7 | 2019-01-02 | XXX CC / NTA | Project Design | Risk | Design / Tender Docs | Design requirements amended for the island bus stops due to request from NTA. | Early engagement with the NTA to minimise end impact. Installation of prototype. | 5 | VH | 90% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 15 | 339147.2934 | 678294.5868 | 1017441.8802 | Residual
| 6.1 | 2019-01-02 | XXX CC / DESIGNER | Project Design | Risk | Design / Tender Docs | Redesign of project required / misinterpretation of scope / client changes. Additional design fees and delays may be incurred. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 |  |  |  | Closed
| 1.2 | 2019-01-02 | XXX CC | Project Scope | Risk | Design / Tender Docs | Extent of works changed post Contract award due to public backlash or avaricious contractor. Delay to programme and associated costs. | Traffic management measures address potential public interaction issues. | 2 | L | 13% | 2 | L | 188415.163 | 282622.7445 | 376830.326 | 4 | 24493.9712 | 36740.9568 | 48987.9424 | Residual
| 1.1 | 2019-01-02 | XXX CC / NTA | Project Scope | Risk | Design / Tender Docs | Design changes due to unforeseen circumstances. Delay to programme and associated costs | Robust change control process to be implemented. | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 | 133774.7657 | 267549.5315 | 401324.2972 | Residual
| 7.20 | 2021-10-22 | Contractor | Construction | Risk | Drainage | There is a risk that construction works cause a sewer collapse due to existing defects in the sewer network. | Close liaison with Irish water regarding the location of existing sewer. | 1 | VL | 2.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 5 |  |  |  | Residual |  | Contractor Risk
| 7.19 | 2021-10-22 | Contractor | Construction | Risk | Drainage | There is a risk that construction works could result in basement flooding. |  | 2 | L | 13% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 8 |  |  |  | Residual |  | Contractor Risk
| 6.3 | 2019-01-02 | DESIGNER | Project Design | Risk | Drainage | Complexity of drainage works |  | 1 | VL | 2.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 5 |  |  |  | Closed
| 4.6 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Drainage | Delayed approval from Drainage Department. Delay to programme and associated costs. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 | 48987.9424 | 97975.8848 | 146963.8271 | Residual |  | Manageable cost impact
| 7.5 | 2019-01-02 | Contractor | Construction | Risk | Earthworks | Unforeseen archaeological find. Delay to programme and associated costs. |  | 1 | VL | 2.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 4 |  |  |  | Residual |  | Contractor Risk
| 7.3 | 2019-01-02 | XXX CC | Construction | Risk | Earthworks | Contaminated material will be encountered while undertaking excavation works. Depending on degree of contamination, disposal may incur significant cost. |  | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 |  |  |  | Closed
| 6.4 | 2019-01-02 | XXX CC | Project Design | Risk | Earthworks | Contaminated Ground - Cost escalation and delays. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 | 48987.9424 | 97975.8848 | 146963.8271 | Residual
| 7.18 | 2021-10-22 | Contractor | construction | Risk | Environmental | Contractor may fail to adequately protect existing trees | contractor to outline plans for tree protection. | 1 | VL | 2.5% | 2 | L | 188415.163 | 282622.7445 | 376830.326 | 2 |  |  |  | Residual |  | Contractor Risk
| 9.3 | 2019-01-02 | Contractor | Construction | Risk | Environmental | Fuel oil spill during re fuelling of equipment. Contamination of ground/ contamination of surface water drains. |  | 1 | VL | 2.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 4 | 28262.2745 | 37683.0326 | 47103.7908 | Residual
| 9.2 | 2019-01-02 | Contractor | Construction | Risk | Environmental | Dust / Airborne Material. Potential Impact - Internal & External Stakeholders including Local Residents. | Review of method statements, monitoring. | 3 | M | 35.5% | 2 | L | 188415.163 | 282622.7445 | 376830.326 | 6 |  |  |  | Residual |  | Contractor Risk
| 9.1 | 2019-01-02 | Contractor | Construction | Risk | Environmental | Mishandling of contaminated materials, Damage Environment, Pollution. |  | 1 | VL | 2.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 3 |  |  |  | Closed
| 7.2 | 2019-01-02 | XXX CC | Construction | Risk | Environmental | Unforeseen Ground Conditions, Hard material / soft areas. Delay to programme and associated costs. |  | 4 | H | 65.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 12 | 246823.8635 | 493647.7271 | 740471.5906 | Residual
| 7.11 | 2019-01-02 | Contractor | Construction | Risk | Environmental | Delay due to breach of environmental restrictions. Impact on Programme, Fines, Imprisonment. | Review of method statements, monitoring. | 1 | VL | 2.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 5 |  |  |  | Residual |  | Contractor Risk
| 7.7 | 2019-01-02 | XXX CC | Construction | Risk | Land / Landowners | Delay to works caused by XXX CC failure to make site available. Delay to programme and associated costs. |  | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 |  |  |  | Closed
| 5.5 | 2019-01-02 | Contractor | Tender Actions / Procurement | Risk | Land / Landowners | Restricted access to the Site due to events, other XXX CC requirements. Delays and cost over-runs. | Early notification of events and timely engagement with the contractor. | 2 | L | 13% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 8 |  |  |  | Residual |  | Contractor Risk
| 3.2 | 2019-01-02 | XXX CC / DESIGNER | Stakeholders | Risk | Land / Landowners | Site Boundaries - Over run on to adjacent lands. Affect Adjacent utilities. |  | 2 | L | 13% | 2 | L | 188415.163 | 282622.7445 | 376830.326 | 4 | 24493.9712 | 36740.9568 | 48987.9424 | Residual
| 4.10 | 2019-01-02 | XXX CC | Consents / Planning | Risk | Planning / Approvals | Planning Conditions- Actual or perceived failure to address planning conditions. |  | 1 | VL | 2.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 5 | 47103.7908 | 70655.6861 | 94207.5815 | Residual |  | Manageable cost impact
| 7.14 | 2021-10-22 | XXX CC | Construction | Risk | Planning / Approvals | Delay in issuing Road Opening Licences. | XXX CC will ensure appropriate resource is in place and that response timelines are adhered to. | 3 | M | 35.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 15 | 668873.8287 | 1003310.743 | 1337747.6573 | Residual
| 7.12 | 2019-01-02 | Contractor | Construction | Risk | Planning / Approvals | Delay in issuing Road Opening Licences. |  | 3 | M | 35.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 15 |  |  |  | Residual |  | Contractor Risk
| 4.9 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Planning / Approvals | Delayed approval from Roadworks Control Department. Delay to programme and associated costs. | Proactive engagement between contractor, TM contractor and XXX CC. - prompting contractor for feedback, progress. Process for control to be established. | 3 | M | 35.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 12 | 401324.2972 | 535099.0629 | 668873.8287 | Residual
| 4.7 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Planning / Approvals | Delayed approval from Road Maintenance Department. Delay to programme and associated costs. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 | 48987.9424 | 97975.8848 | 146963.8271 | Residual |  | Manageable cost impact
| 4.2 | 2019-01-02 | XXX CC | Consents / Planning | Risk | Planning / Approvals | Planning Challenge - Legal challenge to scheme. |  | 1 | VL | 2.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 5 | 47103.7908 | 70655.6861 | 94207.5815 | Residual |  | Manageable cost impact
| 4.15 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Planning / Approvals | Resistance from Consultative Forum. Delay to programme and associated costs. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 | 48987.9424 | 97975.8848 | 146963.8271 | Residual |  | Manageable cost impact
| 4.12 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Planning / Approvals | Delayed approval from Other Department. Delay to programme and associated costs. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 | 48987.9424 | 97975.8848 | 146963.8271 | Residual |  | Manageable cost impact
| 4.11 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Planning / Approvals | Delayed approval from Heritage Department. Delay to programme and associated costs. Note - some lighting columns are protected under the consent. | Currently tied in with the IR licence. Project can continue while issue is resolved | 1 | VL | 2.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 4 | 28262.2745 | 37683.0326 | 47103.7908 | Residual |  | Manageable cost impact
| 4.1 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Planning / Approvals | Delayed approval from Parks Department. Delay to programme and associated costs. |  | 2 | L | 13% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 8 | 146963.8271 | 195951.7695 | 244939.7119 | Residual |  | Manageable cost impact
| 4.16 | 2021-10-22 | Contractor | Consents / Planning | Risk | Public Lighting | Delays caused by Electricity Supply Board | Early programming of new supply applications. Early engagement with contractor and robust programming. | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 |  |  |  | Residual |  | Contractor Risk
| 4.5 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Public Lighting | Delayed internal approval of materials from Public Lighting Department. Delay to programme and associated costs. | Early programming of new supply applications. Early engagement with contractor and robust programming. Increased staffing in XXX CC. | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 | 133774.7657 | 267549.5315 | 401324.2972 | Residual |  | Manageable cost impact
| 2.2 | 2019-01-02 | XXX CC / DESIGNER | Project Organisation | Risk | Staffing | Staffing levels - appointed consultant. Inadequate resourcing by Consultant may impact planned schedule. | Explore temp resource/absence management processes. Gap analysis to ensure that project team will be adequately resourced. Ongoing monitoring of contract admin workload and review of staffing levels. | 3 | M | 35.5% | 2 | L | 188415.163 | 282622.7445 | 376830.326 | 6 | 66887.3829 | 100331.0743 | 133774.7657 | Residual
| 2.1 | 2019-01-02 | XXX CC | Project Organisation | Risk | Staffing | Staffing Levels - Dublin City Council and NTA. Lack of client resources could impact on progress. | Explore temp resource/absence management processes. Gap analysis to ensure that project team will be adequately resourced. Ongoing monitoring of contract admin workload and review of staffing levels. | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 | 133774.7657 | 267549.5315 | 401324.2972 | Residual |  | Manageable cost impact
| 10.2 | 2019-01-02 | XXX CC | Construction | Risk | Traffic | Contractor delays / disrupts city traffic / public transport. Disruption, public and political unrest. |  | 2 | L | 13% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 8 | 146963.8271 | 195951.7695 | 244939.7119 | Residual |  | Manageable cost impact
| 7.9 | 2019-01-02 | XXX CC | Construction | Risk | Traffic | Traffic management Issues - Delay & disruption; Changes to works requirements, delays to programme, significant cost escalation. |  | 4 | H | 65.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 20 |  |  |  | Closed
| 4.4 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Traffic | Delayed approval from Traffic Department. Delay to programme and associated costs. |  | 2 | L | 13% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 6 | 48987.9424 | 97975.8848 | 146963.8271 | Residual |  | Manageable cost impact
| 3.4 | 2019-01-02 | XXX CC | Stakeholders | Risk | Traffic | Traffic Impact - Failure to make roadway available; need to take back traffic lanes; or other disruption to Contractor's activities. | Explore use of charges etc to ensure contractor compliance. | 4 | H | 65.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 20 | 1234119.3177 | 1851178.9765 | 2468238.6353 | Residual
| 7.21 | 2021-10-22 | Contractor | Construction | Risk | Utilities | There is a risk that fibre cables are damaged during construction works. | Engagement with contractor regarding methodology for locating existing services.. | 1 | VL | 2.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 3 |  |  |  | Residual |  | Contractor Risk
| 7.4 | 2019-01-02 | Contractor | Construction | Risk | Utilities | Under performance / availability of service providers to carryout functions required. Delay to programme and associated costs. |  | 5 | VH | 90% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 15 |  |  |  | Residual |  | Contractor Risk
| 7.1 | 2019-01-02 | Contractor | Construction | Risk | Utilities | Potential Damage to existing services during works. Delay to programme and associated costs. | Engagement with contractor regarding methodology for locating existing services. | 3 | M | 35.5% | 5 | VH | 1884151.63 | 2826227.445 | 3768303.26 | 15 | 668873.8287 | 1003310.743 | 1337747.6573 | Residual
| 6.5 | 2019-01-02 | Contractor | Project Design | Risk | Utilities | Unforeseen utilities and services and other underground obstructions. Cost escalation and delays. |  | 5 | VH | 90% | 2 | L | 188415.163 | 282622.7445 | 376830.326 | 10 |  |  |  | Residual |  | Contractor Risk
| 6.2 | 2019-01-02 | XXX CC / DESIGNER | Project Design | Risk | Utilities | Scope of Utility and Services works increases. May require additional design and construction. |  | 3 | M | 35.5% | 3 | M | 376830.326 | 753660.652 | 1130490.978 | 9 | 133774.7657 | 267549.5315 | 401324.2972 | Residual
| 4.8 | 2019-01-02 | XXX CC / DESIGNER | Consents / Planning | Risk | Utilities | Delayed approval from Water Department/Irish Water. | Terms to be agreed with IW and locked into contract through the project term. Identify key IW stakeholders and engagement. | 1 | VL | 2.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 4 | 28262.2745 | 37683.0326 | 47103.7908 | Residual
| 3.3 | 2019-01-02 | Contractor | Stakeholders | Risk | Utilities | Utility Providers - Non attendance to site/Non Support of the works. |  | 4 | H | 65.5% | 4 | H | 1130490.978 | 1507321.304 | 1884151.63 | 16 |  |  |  | Residual |  | Contractor Risk
[17 empty] | Cumulative Risk Value: | 5185185.2858 | 8448064.871 | 11710944.4563
[12 empty] | SA to list risk exposure rank (1-5: 5 been the highest) |  |  |  |  | Average Cumulative Risk: |  | 8448064.871

## RR_Drop Downs
RISK REGISTER DROP DOWN MENUs TAB : Risk Register (RR)
RISK OWNER (Column D) | ROLE | CATEGORY (Column E) | SEVERITY CATEGORY (See TAB : Risk Process_RR Explanation) | RISK OR OPPORTUNITY (Column F) | TECHNICAL DISCIPLINE (Column G) | STATUS (Column AG)
TBC | TBC | Funding | Programme / Budget | Risk | Client | Pending
TBC | TBC | Programme | Programme / Budget | Opportunity | Project Management | Residual
TBC | TBC | Design / Scope Change | Technical |  | Highways | Closed
TBC | TBC | Environmental | Technical |  | Structures
TBC | TBC | Statutory Authorities (inc. Statutory Undertakers) | Technical |  | Environmental
TBC | TBC | Resources | Programme / Budget |  | Geotech
TBC | TBC | Procurement | Programme / Budget |  | Structures
|  | Approvals (Statutory / Overseeing Organisation) | Technical |  | Drainage & Flooding
|  | Products / Materials | Technical |  | Land Services
|  | Construction | Technical |  | Contractor
|  | Client | Programme / Budget
|  | Health & Safety | SHE
|  | Reputation | Reputation