## Cost Estimate
Updated Preliminary Cost Estimate Template | [9 empty] | NTA template - 015_B23 (Word Document) - this is the cover pages for the Updated Preliminary Cost Estimate (016-B23)
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional line etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: For Band 3 Projects the activity cost heads presented are the minimum expected for a linear road project and are to be proposed, discussed and agreed in writing with NTA prior to production of the cost estimate. | [9 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
Project Title: |  |  | Highways Improvement for Urban Environment | [6 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/22/001 5G |  | Prepared By (Individual/Organisation): |  |  | Sally Gate - South Dublin Council |  | SA confirm the project code: SA to confirm who has prepared the document
Approving Authority: |  |  | NTA |  | Date Estimate Prepared: |  |  | 2019-02-10 |  | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin |  | Base Date of Estimate: |  |  | Q1 2019 |  | SA = local authority (or Irish Rail / Bus Éireann etc ...) submitting the application: Base date is the quarter period (Q1 = Jan / Feb / march: Q2 = Apr / May / June: Q3 = July / Aug / Sept: Q4 = Oct / Nov / Dec)
Project Information
SA to confirm cross section type: Overall road width to be confirmed by SA
Mainline Cross-Section Type: |  |  |  | 4 Lane carriageway incorporating bus corridors | Average Link / Side Road Width (m):
Location: |  |  |  | ****** | Cyclepath Included (Y/N): |  |  | N |  | Identify location - include co-ordinates if available: SA to confirm if cycle path included or not (select cell for dropdown)
Total Mainline Length (m): |  |  |  | 2700 | Footway Included (Y/N): |  |  | Y | Y | SA to confirm (select from drop down menu for Y/N section)
N
Total Mainline Width (m): |  |  |  | 6000 | Hardstrip Included (Y/N): |  |  | N |  | SA to confirm (select from drop down menu for Y/N section)
Total Link / Side Road Length (m): |  |  |  |  | Central Reserve Included (Y/N): |  |  | N |  | SA to confirm (select from drop down menu for Y/N section)
Potential Start Date: |  |  |  | Q4 2019 | Anticipated Duration (Months): |  |  | 24 |  | SA to confirm potential start on site (Quarter): SA to confirm estimated construction period
Other Relevant Project Information: | [9 empty] | SA to outline (brief) project scope of works
1 | Construction Costs
| Ref | Description | [5 empty] | Total |  | SA to confirm elemental costs
| 1.1 | Site Clearance | [5 empty] | 827996.18
| 1.2 | Fencing | [5 empty] | 237909.15
| 1.3 | Road Restraint Systems | [5 empty] | 60000
| 1.4 | Drainage & Service Ducts | [5 empty] | 2420747.78
| 1.5 | Earthworks | [5 empty] | 3920854.35
| 1.6 | Pavements | [5 empty] | 6608393.21
| 1.7 | Footways & Kerbing | [5 empty] | 5629130.43
| 1.8 | Traffic Signs & Road Markings | [5 empty] | 442237.3
| 1.9 | Road Lighting | [5 empty] | 1424288.97
| 1.1 | Structural Concrete (Including Structures Generally) | [5 empty] | 517981.06
| 1.11 | Accommodation Works | [5 empty] | 125000
| 1.12 | Works for Statutory Undertakers | [5 empty] | 3764457.1
| 1.13 | Landscaping & Ecology | [5 empty] | 437561.94
| 1.14 | Other Project Costs | [5 empty] | 0
| 1.15 | Preliminaries including site compound costs (excluding traffic management) - % applied to base costs |  |  | 10% | % | 26416557.47 | 2641655.747
| Sub-Total A - Construction Costs | [6 empty] | 29058213.217
2 | Preparation and Administration
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 2.1 | Preparation and Administration Costs | [5 empty] | 4350000 |  | SA to confirm admin costs (design teams etc …) - increase from previous, reason to be confirmed in assumptions tab
| 2.1.1 | Scope & Purpose |  |  | 1 | item | 1000000 | 1000000
| 2.1.2 | Concept, Development & Option Selection |  |  | 1 | item | 1950000 | 1950000
| 2.1.3 | Preliminary Design |  |  | 1 | item | 1000000 | 1000000
| 2.1.4 | Statutory Processes |  |  | 1 | item | 400000 | 400000
| 2.1.5 | Detailed Design & Procurement |  |  | 1 | item |  | 0
| 2.1.6 | Construction & Implementation |  |  | 1 | item |  | 0
| 2.1.7 | Close Out & Review |  |  | 1 | iten |  | 0
| Sub-Total B - Preparation and Administration Costs | [6 empty] | 4350000
3 | Traffic Management Related Costs
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 3.1 | Traffic Management (TM) Related Costs |  |  | 5% | % | 29058213.217 | 1452910.6609 |  | SA to allow costs (estimate) for TM (if applicable to there project)
| Sub-Total C - Traffic Management Related Costs | [6 empty] | 1452910.6609
4 | Land and Property Costs | [8 empty] | SA to confirm type of land take & estimated costs
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 4.1 | Properties |  |  | 1 | Nr | 50000 | 50000
| 4.2 | Garden Ground |  |  |  | Ha |  | 0
| 4.3 | Industrial Development Land |  |  |  | m2 |  | 0 |  | SA to confirm estimate (if agreed value - state in assumptions tab)
| 4.4 | Amenity Land / Open Space |  |  |  | Ha |  | 0
| 4.5 | Residential Development Land / Urban |  |  | 1 | Ha | 125000 | 125000
| 4.6 | Agricultural Land |  |  |  | Ha |  | 0
| Sub-Total D - Land and Property Costs | [6 empty] | 175000
5 | Adjustments
| Add Inflation |  |  |  | 10% | % | 34861123.8779 | 3486112.3878 |  | SA to confirm if inflation needs to be applied - example, if works were not to happen until Q2 2023, NTA would recommend applying % cost - say 5% for example purpose (Inflation calc does not include for Land take). Refer to the NTA bulletin for guidance on inflation allowances
| Add Project Specific Risk (Output From QRA - 013_B23_QRA_CMG) |  |  |  | 1 | Item | 8448064.87 | 8448064.87 | Item | SA to include costs based on QRA assessment (form 013_B23 updated)
| Add Contingency (001_B123_CC_CMG) |  |  |  | 17.5% | % | 46795301.1356 | 8189177.6987 | % | SA to update the contingency calculator (form 013_B123) - total cost is based on Sub-total A+B+Traffic Management
| Per Cent for Art Scheme https://publicart.ie/main/commissioning/funding/per-cent-for-art-scheme/ |  |  |  | 1% | % | 46795301.1356 | 467953.0114 | % | SA to review web link for proposed maximum limits
| Sub-Total E - Adjustments | [6 empty] | 20591307.9679
Total Updated Preliminary Cost Estimate Exclusive of VAT | [7 empty] | 55627431.8457
VAT on Construction, TM and Associated Adjustments Costs |  |  |  |  | 13.5% | % | 51102431.8457 | 6898828.2992 |  | 13.5% VAT is applied to the construction estimate / Traffic MGT / inflation allowance / contingency allowance
VAT on Preparation and Administration Costs and Associated Adjustment Costs |  |  |  |  | 23% | % | 4350000 | 1000500 |  | 23% applies to preparation costs (design teams as an example): No VAT should be applied if design is in-house with the SA
VAT on Land and Property |  |  |  |  | 1 | Item |  | 0
https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [9 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line C54 to determine if VAT is applicable to your project
Total Updated Preliminary Cost Estimate Inclusive of VAT | [7 empty] | 63526760.1449
Mainline Length |  |  | 0 | 2.7 | Km |  | Rate Per Km (Excluding VAT) | 20602752.5355
[7 empty] | Rate Per Km (Including VAT) | 23528429.6833
Source of Cost Data (Please provide a brief narrative on the source of cost data in the box below)
Works of similar nature / agreed professional fees / agreed land take
Revision | Title |  |  |  | Prepared By | Checked By |  | Issue Date
[5 empty] | Sally Gate | Michael Bunny |  | 2019-02-10 |  | SA to sign off (2 parties within their organisation)
NOTE: | Costs are considered to include allowances for overheads and profits. Costs are reflective of costs at the base date stated above. VAT is not applicable to all land and property therefore it is not appropriate to apply a uniform percentage. The value associated with VAT on land and property is to be determined on an individual basis and included as a lump sum.
Note on K14: Estimating Methodology: Period in which prices in the cost estimate relate to (e.g. Q1 2021)
Note on J86: Estimating Methodology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on J87: Estimating Methodology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on J88: Estimating Methodology The applicable VAT rate is to be determined by each user individually. A hyperlink to applicable rules/laws relating to the applicability of VAT is included for reference and assessment purposes.

## PCD Summary
Project Control Document Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document. | [7 empty] | Guidance Notes
Project Title: |  |  | Highways Improvement for Urban Environment |  |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  |  | DLR/22/001 5G | Prepared By (Individual & Organisation) |  |  | Sally Gate - South Dublin Council | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  |  | NTA | Date Estimate Prepared: |  |  | 2019-02-10 | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  |  | South Dublin | Base Date of Estimate: |  |  | Q1 2019 | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | Grant Application Cost Estimate - Summary
| 1.2.1 | Scope & Purpose |  | 1 | Item | 1000000 | 1000000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.2 | Concept, Development & Option Selection |  | 1 | Item | 1950000 | 1950000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.3 | Preliminary Design |  | 1 | Item | 1000000 | 1000000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.4 | Statutory Processes |  | 1 | Item | 400000 | 400000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.5 | Detailed Design & Procurement |  | 1 | Item | 0 | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.6 | Construction & Implementation |  | 1 | Item | 51277431.8457 | 51277431.8457 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.7 | Close Out & Review |  | 1 | Item | 0 | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Total Grant Application Cost Estimate (excluding VAT) | [5 empty] | 55627431.8457 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Add VAT @ 13.5% | [5 empty] | 6898828.2992 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Add VAT @ 23% | [5 empty] | 1000500 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Add VAT on Land (If Applicable) | [5 empty] | 0 | SA to include if applicable pending Revenue rules
| Total Grant Application Cost Estimate (Including VAT) | [5 empty] | 63526760.1449
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.
Note on J14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## Assumptions
Estimate Assumptions, Exclusions and Inclusions
[6 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/22/001 5G |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  | NTA |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  | South Dublin |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Prepared By (Organisation/Individual): |  | Sally Gate - South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | Construction Costs
| Construction cost estimate is based on similar works (recent tender returns). The Local Authroity are satisfied the project can be delivered for the estimated construction cost as outlined and the rated prcing document is included with the preliminary cost estimate. |  |  |  |  | SA to give as much information as possible
2 | Delivery and Construction Programme
| Tender process for construction will be issued in early ******* 20** at the latest. Works on site to commence in early 20** and complete scheme in quarter 2 of 20** (estimated construction time period to be 24 months) |  |  |  |  | SA to give information on the programme
3 | Preparation and Administration Costs
| Scheme has been designed in Q3 of 20**, the lead design team is ********* Ltd. |  |  |  |  | SA on consultants etc …..
4 | Traffic Management Related Costs
| Traffic management (TM) costs are included into the estimate - TM costs will also be included into the tender documents for pricing / inclusion. |  |  |  |  | SA to include for TM if applicable to the project scope
5 | Land and Property Costs
| Land take costs have been fully agreed and agreements are signed off (legals finalised) |  |  |  |  | SA to give as much details as possible on land take / agreements etc … to determine cost accuracy
6 | Other Relevant Information
Any other relevant information, general assumptions, exclusions or inclusions that have been used to develop the cost estimate shall be included in this section.
Revision | Title |  | Prepared By | Checked By | Issue Date
|  |  | Sally Gate | Michael Bunny | 2019-02-10 | SA to sign off (2 parties within their organisation)

## Expenditure Profile
Expenditure Profile
[8 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/22/001 5G | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Preliminary Cost Estimate: |  | 63526760.1449 | [5 empty] | SA to confirm figure from Cost Estimate Tab - Figure is to Include VAT
Anticipated Programme Duration: |  | 24 | Months |  |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
|  | Preliminary Cost Estimate |  | Updated Preliminary Cost Estimate
Year | Quarter | Total Quarterly Expenditure (€) | Cumulative Expenditure (€) | Total Quarterly Expenditure (€) |  | Cumulative Expenditure (€) |  | SA to input figure - example purpose the programme is estimated 4 months with a start estimated in Q1 2023 (example purposes we are assuiming start date of February 2023)
Year 1 | Q1 | 2789414.4312 | 2789414.4312 | 2669718.7754 |  | 2669718.7754
| Q2 | 5388641.5148 | 8178055.946 | 5157411.2706 |  | 7827130.046
| Q3 | 9324943.2844 | 17502999.2304 | 8924803.6747 |  | 16751933.7207
| Q4 | 10489120.3817 | 27992119.6121 | 10039025.1471 |  | 26790958.8677
Year 2 | Q1 | 12033672.1742 | 40025791.7864 | 11517299.1797 |  | 38308258.0474
| Q2 | 9445971.5965 | 49471763.3829 | 9040638.5802 |  | 47348896.6277
| Q3 | 5815122.2336 | 55286885.6165 | 5565591.4139 |  | 52914488.0416
| Q4 | 2345643.9535 | 57632529.57 | 2244990.7884 |  | 55159478.83
Year 3 | Q1 |  | 57632529.57 |  |  | 55159478.83
| Q2 |  | 57632529.57 |  |  | 55159478.83
| Q3 |  | 57632529.57 |  |  | 55159478.83
| Q4 |  | 57632529.57 |  |  | 55159478.83
Year 4 | Q1 |  | 57632529.57 |  |  | 55159478.83
| Q2 |  | 57632529.57 |  |  | 55159478.83
| Q3 |  | 57632529.57 |  |  | 55159478.83
| Q4 |  | 57632529.57 |  |  | 55159478.83
Revision | Title |  |  |  | Prepared by | Checked by | Issue Date
[5 empty] | Sally Gate | M Bunny | 2019-02-10 | SA to sign off (2 parties within their organisation)
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Estimate Comparisons
Estimate Comparisons
[7 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment
Project / Contract Code: |  | DLR/22/001 5G
Estimate Comparison
Ref | Item |  | Preliminary Cost Estimate | Updated Preliminary Cost Estimate | Variance
[5 empty] | € | %
1 | Construction Costs |  | 26551250 | 29058213.217 | 2506963.217 | 9.442% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
2 | Preparation and Administration Costs |  | 3950000 | 4350000 | 400000 | 10.13% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
3 | Traffic Management Related Costs |  | 1327562.5 | 1452910.6609 | 125348.1609 | 9.442% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
4 | Land and Property Costs |  | 175000 | 175000 | 0 | 0% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
5 | Inflation |  | 3819457.5 | 3486112.3878 | -333345.1122 | -8.728% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
6 | Risk |  | 8549829.67 | 8448064.87 | -101764.8 | -1.19% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
7 | Contingency |  | 13259429.9 | 8189177.6987 | -5070252.2013 | -38.24% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
8 | Per Cent Art Scheme |  | 450000 | 467953.0114 | 17953.0114 | 3.99% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
9 | Total Costs (Cumulative) |  | 58082529.57 | 55627431.8457 | -2455097.7243 | -4.227% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
10 | Add VAT @ 13.5% |  | 184090.46 | 6898828.2992 | 6714737.8392 | 3648% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
11 | Add VAT @ 23% |  | 14950 | 1000500 | 985550 | 6592% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
12 | Add VAT on Land (If Applicable) |  | 0 | 0 | 0 | 0% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
13 | Total Costs (Including VAT) |  | 58281570.03 | 63526760.1449 | 5245190.1149 | 9%
Programme Comparison
Ref | Item |  | Previous Estimate | Current Estimate | Variance
[5 empty] | Months | %
1 | Anticipated Programme Duration |  | 24 | 24 | 0 | 0% | SA to confirm (programme)
Commentary on Variances
If costs vary more than 10% or a value advised by NTA from the last cost estimate please provide a commentary in the space below:
If costs are greater than 10% (increase from Preliminary Cost Estimate) - a detailed explanation is required by the SA
Rev | Title |  |  | Prepared by | Checked by | Issue Date
|  |  |  | Sally Gate | Michael Bunny | 2019-02-10 | SA to sign off (2 parties within their organisation)