## Cost Estimate
Total Project Cost - Estimate Template
NOTE: For Band 2 & 3 Projects the activity cost heads presented are the minimum expected for a linear road project and are to be proposed, discussed and agreed in writing with NTA prior to production of the cost estimate.
Project Title:
Project / Contract Code: | [7 empty] | Prepared By (Individual/Organisation):
Approving Authority: | [7 empty] | Date Estimate Prepared:
Sponsoring Agency: | [7 empty] | Base Date of Estimate:
Project Information
Mainline Cross-Section Type: | [6 empty] | Average Link / Side Road Width (m):
Location: | [6 empty] | Cyclepath Included (Y/N): | [5 empty] | Y
N
Total Mainline Length (m): | [6 empty] | Footway Included (Y/N):
Total Mainline Width (m): | [6 empty] | Hardstrip Included (Y/N):
Total Link / Side Road Length (m): | [6 empty] | Central Reserve Included (Y/N):
Potential Construction Works Start Date: | [6 empty] | Anticipated Construction Works Duration (Months):
Other Relevant Project Information:
1 | Construction Costs
| Ref | Description |  |  |  |  | Incurred Costs |  | Forecast Costs To Complete (Including Tender Prices) |  | Total Cost (€)
Enabling Works Costs (Please provide supplementary information giving detail of costs)
| 1.1 | Heritage Contracts | [8 empty] | 0
| 1.2 | Utilities Contracts | [8 empty] | 0
| 1.3 | Archaeological Contracts | [8 empty] | 0
| 1.4 | Site Investigation Contracts | [8 empty] | 0
0
Main Contract(s) Costs (Please provide supplementary information giving detail of costs)
| 1.5 | Site Clearance | [6 empty] | 0 |  | 0
| 1.6 | Fencing | [6 empty] | 0 |  | 0
| 1.7 | Road Restraint Systems | [6 empty] | 0 |  | 0
| 1.8 | Earthworks | [6 empty] | 0 |  | 0
| 1.9 | Drainage | [6 empty] | 0 |  | 0
| 1.10 | Pavements | [6 empty] | 0 |  | 0
| 1.11 | Kerbing & Footways | [6 empty] | 0 |  | 0
| 1.12 | Traffic Signs and Road Marking | [6 empty] | 0 |  | 0
| 1.13 | Road Lighting | [6 empty] | 0 |  | 0
| 1.14 | Structural Concrete (Including Structures Generally) | [6 empty] | 0 |  | 0
| 1.15 | Accommodation Works | [6 empty] | 0 |  | 0
| 1.16 | Works for Statutory Undertakers | [6 empty] | 0 |  | 0
| 1.17 | Landscaping & Ecology | [6 empty] | 0 |  | 0
| 1.18 | Other Project Costs | [6 empty] | 0 |  | 0
| 1.19 | Preliminaries including Site Compound (excluding traffic management) | [6 empty] | 0 |  | 0
| Sub-Total A - Project Base Costs | [5 empty] | 0 |  | 0 |  | 0
2 | Preparation and Administration
| 2.1 | Preparation and Administration Costs | [8 empty] | 0
| 2.1.1 | Scope & Purpose |  |  |  |  | 0 |  | 0 |  | 0
| 2.1.2 | Concept, Development & Option Selection |  |  |  |  | 0 |  | 0 |  | 0
| 2.1.3 | Preliminary Design |  |  |  |  | 0 |  | 0 |  | 0
| 2.1.4 | Statutory Processes |  |  |  |  | 0 |  | 0 |  | 0
| 2.1.5 | Detailed Design & Procurement |  |  |  |  | 0 |  | 0 |  | 0
| 2.1.6 | Construction & Implementation |  |  |  |  | 0 |  | 0 |  | 0
| 2.1.7 | Close Out & Review |  |  |  |  | 0 |  | 0 |  | 0
| Sub-Total B - Preparation and Administration Costs | [5 empty] | 0 |  | 0 |  | 0
3 | Traffic Management Related Costs
| 3.1 | Traffic Management Related Costs | [6 empty] | 0 |  | 0 | %
| Sub-Total C - Traffic Management Related Costs | [5 empty] | 0 |  | 0 |  | 0
4 | Land and Property Costs
| Ref | Description |  | Quantity | Unit | Rate | Incurred Costs |  | Forecast Costs to Complete |  | Total Cost (€)
| 4.1 | Properties |  |  | Nr |  |  |  | 0 |  | 0
| 4.2 | Garden Ground |  |  | Ha |  |  |  | 0 |  | 0
| 4.3 | Industrial Development Land |  |  | m2 |  |  |  | 0 |  | 0
| 4.4 | Amenity Land / Open Space |  |  | Ha |  |  |  | 0 |  | 0
| 4.5 | Residential Development Land / Urban |  |  | Ha |  |  |  | 0 |  | 0
| 4.6 | Agricultural Ground |  |  | Ha |  |  |  | 0 |  | 0
| Sub-Total D - Land and Property Costs | [5 empty] | 0 |  | 0 |  | 0
5 | Adjustments
%
| Add Inflation (Band 2 & 3 Projects Only) | [5 empty] | 0% |  | % | 0 | 0 |  | Item
| Add Project Specific Risk (Output From QRA - 013_B23_QRA_CMG) | [5 empty] | 1 |  | Item | 0 | 0
| Add Contingency (001_B123_CC_CMG) | [5 empty] | 0% |  | % | 0 | 0
| Per Cent for Art Scheme https://publicart.ie/main/commissioning/funding/per-cent-for-art-scheme/ | [5 empty] | 0% |  | % | 0 | 0
| Sub-Total E - Adjustments | [9 empty] | 0
Total Project Cost Estimate Exclusive of VAT | [10 empty] | 0
VAT on Construction Costs, TM and Associated Adjustment Costs | [5 empty] | 13.5% |  | % | 0 |  | 0
VAT on Preparation and Administration Costs and Associated Adjustment Costs | [5 empty] | 23% |  | % | 0 |  | 0
VAT on Land and Property | [5 empty] | 1 |  | Item | 0 |  | 0
https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx
Total Project Cost Estimate Inclusive of VAT | [10 empty] | 0
Mainline Length |  |  | 0 | Km | [5 empty] | Rate Per Km (Excluding VAT) | #DIV/0!
[10 empty] | Rate Per Km (Including VAT) | #DIV/0!
Source of Cost Data (Please provide a brief narrative on the source of cost data in the box below)
Construction costs are based on tender return following a MEAT analysis: Design team & land take costs all agreed
Revision | Title | [5 empty] | Prepared By |  | Checked By |  | Issue Date
[7 empty] | 0 |  | 0 |  | 0
NOTE: | Costs are considered to include allowances for overheads and profit. Costs are reflective of costs at the base date stated above. VAT is not applicable to all land and property therefore it is not appropriate to apply a uniform percentage. The value associated with VAT on land and property is to be determined on an individual basis and included as a lump sum.
Note on O14: Estimating Methodology: Period in which prices in the cost estimate relate to (e.g. Q1 2021)
Note on M92: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on M93: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on M94: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.

## PCD Summary
Project Control Document Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document.
Project Title: |  |  | 0
Project / Contract Code: |  |  | 0 | Prepared By (Individual & Organisation) |  |  | 0
Approving Authority: |  |  | 0 | Date Estimate Prepared: |  |  | 0
Sponsoring Agency: |  |  | 0 | Base Date of Estimate: |  |  | 0
1 | PCD Summary
| 1.1 | Scope & Purpose |  | 1 | Item | 0 | 0
| 1.2 | Concept, Development & Option Selection |  | 1 | Item | 0 | 0
| 1.3 | Preliminary Design |  | 1 | Item | 0 | 0
| 1.4 | Statutory Processes |  | 1 | Item | 0 | 0
| 1.5 | Detailed Design & Procurement |  | 1 | Item | 0 | 0
| 1.6 | Construction & Implementation |  | 1 | Item | 0 | 0
| 1.7 | Close Out & Review |  | 1 | Item | 0 | 0
| 1.8 | Construction Cost |  | 1 | Item | 0 | 0
| 1.9 | Adjustments (inflation / risk / contingency) |  | 1 | Item | 0 | 0
| 1.1 | Land Value (Agreed value if applicable) |  | 1 | Item | 0 | 0
| Total (excluding VAT) | [5 empty] | 0
| Add VAT @ 13.5% | [5 empty] | 0
| Add VAT @ 23% | [5 empty] | 0
| Add VAT on Land (If Applicable) | [5 empty] | 0
| Total Grant Application Cost Estimate (Including VAT) | [5 empty] | 0
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.
Note on J14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## Assumptions
Estimate Assumptions, Exclusions and Inclusions
Project Title: |  | 0
Project / Contract Code: |  | 0
Approving Authority: |  | 0
Sponsoring Agency: |  | 0
Prepared By (Individual/Organisation): |  | 0
1 | Construction Costs
2 | Delivery and Construction Programme
3 | Preparation and Administration Costs
4 | Traffic Management Related Costs
5 | Land and Property Costs
6 | Other Relevant Information
Revision | Title |  | Prepared By | Checked By | Issue Date

## Expenditure Profile
Expenditure Profile
Project Title: |  | 0
Project / Contract Code: |  | 0
Total Tender Project Budget Cost Estimate: |  | 0
Anticipated Programme Duration: |  | 0 |  | Months
|  | Select Previous Cost Estimate |  | Total Project Cost - Estimate
Year | Quarter | Total Quarterly Expenditure (€) | Cumulative Expenditure (€) | Total Quarterly Expenditure (€) |  | Cumulative Expenditure (€)
Year 1 | Q1 | 0 | 0 | 0 |  | 0
| Q2 | 0 | 0 | 0 |  | 0
| Q3 | 0 | 0 | 0 |  | 0
| Q4 | 0 | 0 | 0 |  | 0
Year 2 | Q1 | 0 | 0 | 0 |  | 0
| Q2 | 0 | 0 | 0 |  | 0
| Q3 | 0 | 0 | 0 |  | 0
| Q4 | 0 | 0 | 0 |  | 0
Year 3 | Q1 |  | 0 |  |  | 0
| Q2 |  | 0 |  |  | 0
| Q3 |  | 0 |  |  | 0
| Q4 |  | 0 |  |  | 0
Year 4 | Q1 |  | 0 |  |  | 0
| Q2 |  | 0 |  |  | 0
| Q3 |  | 0 |  |  | 0
| Q4 |  | 0 |  |  | 0
Revision | Title |  |  |  | Prepared by | Checked by | Issue Date
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Comparisons
Estimate Comparisons
Project Title: |  | 0
Project / Contract Code: |  | 0
Estimate Comparison
Ref | Item |  | Select Previous Cost Estimate | Total Project Cost | Variance
[5 empty] | € | %
1 | Construction Costs |  | 0 | 0 | 0 | 0%
2 | Preparation and Administration Costs |  | 0 | 0 | 0 | 0%
3 | Traffic Management Related Costs |  | 0 | 0 | 0 | 0%
4 | Land and Property Costs |  | 0 | 0 | 0 | 0%
5 | Inflation |  | 0 | 0 | 0 | 0%
6 | Risk |  | 0 | 0 | 0 | 0%
7 | Contingency |  | 0 | 0 | 0 | 0%
8 | Per Cent Art Scheme |  | 0 | 0 | 0 | 0%
9 | Total Costs (Cumulative) |  | 0 | 0 | 0 | 0%
10 | Add VAT @ 13.5% |  | 0 | 0 | 0 | 0%
11 | Add VAT @ 23% |  | 0 | 0 | 0 | 0%
12 | Add VAT on Land (If Applicable) |  | 0 |  | 0 | 0%
13 | Total Costs (Including VAT) |  | 0 | 0 | 0 | 0%
Programme Comparison
Ref | Item |  | Select Previous Cost Estimate | Total Project Budget | Variance
[5 empty] | Months | %
1 | Anticipated Programme Duration |  | 0 | 0 | 0 | 0%
Commentary on Variances
If costs vary more than 10% or a value advised by NTA from the last cost estimate please provide a commentary in the space below:
Rev | Title |  |  | Prepared by | Checked by | Issue Date