## Financial Dashboard
Band 2 (€0.5 - €10 Million) & Band 3 (> €10 Million) Construction Phase Monthly Financial Dashboard
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
[6 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
Construction Phase Financial Dashboard
Project Name: | Highways Improvement for Urban Environment |  |  |  |  | Sponsoring Agency (SA) to list out the project title
Report No: | 1 |  |  |  |  | SA to confirm the dash board number (Dash Boards are required on request from NTA)
Date: | **/**/20** |  |  |  |  | SA to confirm the date of issue - Dashboard is a request (NTA) during the construction period
Value of Works Carried Out To Date:
The certified value excluding VAT is:
Total gross amount applied to date |  |  |  | 1200000 |  | Note, example purposes allowing paid to date at €1,200,000
Less Retention |  |  |  | 60000 |  | Note - for example purposes 5% retention is used
Total nett amount certified to date |  |  |  | 1140000
Current Contract Sum:
Original Contract Sum |  |  |  | 35989709.38 |  | Note - main contractor contract sum figure
Value of Agreed Change Orders |  |  |  | 105000 |  | Note - for example purposes, allowing €15,000 for change order (variations) ofr additional scope of works
Value of Agreed Compensation & Delay Events |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Value of Agreed Employer Claims |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Revised Contract Sum (after adjustments) |  |  |  | 36094709.38
Situation Notifications
Situations Notifications raised to date |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Situation Notifications resulting in Compensation Events |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Situations Notifications not agreed as Compensation Events |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Situation Notifications yet to be determined |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Change Orders
Change Orders |  |  |  | 5 | nr | SA to confirm
Change Orders agreed |  |  |  | 3 | nr | SA to confirm
Change Orders yet to be agreed |  |  |  | 2 | nr | SA to confirm
Compensation & Delay Events
Compensation & Delay Events |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Compensation & Delay Events agreed |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Compensation & Delay Events yet to be agreed |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Employer Claims
Employer Claims |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Employer Claims agreed |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Employer Claims yet to be agreed |  |  |  | 0 | nr | Note, if a section is N/A - then leave blank
Forecast Out-turn Cost | [5 empty] | SA to input
Original Contract Sum |  |  |  | 35989709.38
Value of agreed Change Orders |  |  |  | 87500
Estimated value of Change Orders yet to be agreed |  |  |  | 17500
Value of agreed Compensation & Delay Events |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Estimated value of Compensation & Delay Events yet to be agreed |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Value of agreed Employer Claims |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Estimated value of Employer Claims yet to be agreed |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Situation Notifications |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Other liabilities |  |  |  | 0 |  | Note, if a section is N/A - then leave blank
Forecast Final Contract Sum (Out-turn Cost) |  |  |  | 36094709.38
Programme
SA to confirm the dates as outlined below
Contract Date |  |  |  | 25/03/20**
Starting Date |  |  |  | 15/04/20**
Original Date for Substantial Completion of the Works |  |  |  | 05/08/20**
Current Forecast Date for Substantial Completion of the Works |  |  |  | 05/08/20**
Cost and Schedule Performance Indicators
CPI |  | SPI | 1
Key Risks / Opportunities (Please provide a brief summary on the live key project risks and opportunities)
Risk Description |  | Risk Owner |  | Likely Impact
|  |  |  | € | Time
SA to list out any potential risks (encountered during the construction period)

## Progress & Expenditure Matters
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
[9 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
1.0 Progress & Expenditure Matters Template
Project Name: |  | Highways Improvement for Urban Environment | [6 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  | DLR/2/001 5G | [6 empty] | SA confirm the project code: SA to confirm who has prepared the document
Report No: |  | NTA | [6 empty] | SA to confirm who the report is for
Date: |  | **/**/20** | [6 empty] | SA to confirm issue date
Change Orders
Provide details of the change orders raised that have/may give rise to cost and time implications
Reference | Description | Anticipated Impact |  | Status | Current Actions
|  | € | Time (weeks)
1 | Protection to ESB duct | 4500 | 0 | Agreed | Cost agreed - no effect on programme |  |  | Pending | SA to confirm cost : SA to confirm if agreed / pending / rejected (select drop down from cell)
2 | IW - watermain line | 55000 | 0 | Agreed | Cost agreed - no effect on programme |  |  | Agreed | SA to confirm cost : SA to confirm if agreed / pending / rejected (select drop down from cell)
3 | Eircom - chamber alteration | 28000 | 0 | Agreed | Cost agreed - no effect on programme |  |  | Rejected | SA to confirm cost : SA to confirm if agreed / pending / rejected (select drop down from cell)
4 | Re-build wall (boundary collapse) | 15000 | 0 | Pending | Cost agreed - no effect on programme |  |  |  | SA to confirm cost : SA to confirm if agreed / pending / rejected (select drop down from cell)
5 | Investigation works (plant) for the LA | 2500 | 0 | Pending | Cost agreed - no effect on programme |  |  |  | SA to confirm cost : SA to confirm if agreed / pending / rejected (select drop down from cell)
Total Anticipated Impact: |  | 105000 | 0
Compensation & Delay Events
Provide details of any Compensation & Delay Events in the table below
Reference | Description | Anticipated Impact |  | Status | Current Actions |  |  |  | Note, if a section is N/A - then leave blank
|  | € | Time (weeks)
Pending
Agreed
Rejected
Total Anticipated Impact: |  | 0 | 0
Other Potential Liabilities
Provide details of any other potential liabilities that may present cost or time implications to the project
Reference | Description | Anticipated Impact |  | Status | Current Actions |  |  |  | Note, if a section is N/A - then leave blank
|  | € | Time (weeks)
Open
Closed
Total Anticipated Impact: |  | 0 | 0
Revision | Status |  |  | Prepared By | Date | Checked By | Date
|  |  |  | Sally Gate | **/**/20** | M Bunny | **/**/20**

## Forecast Expenditure Profile
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
[6 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
2.0 CONSTRUCTION EXPENDITURE PROFILE
Project Name: | Highways Improvement for Urban Environment |  |  |  |  | Sponsoring Agency (SA) to list out the project title
NTA Approval Year: | 20** |  |  |  |  | SA to confirm year NTA approved (use construction start period/year)
Report No: | 1 |  |  |  |  | SA to confirm the dash board number (Dash Boards are on request from NTA)
Date: | **/**/20** |  |  |  |  | SA to confirm the date of issue - Dashboard is a request (NTA) during the construction period
Contract Sum: | 35989709.38 |  |  |  |  | SA to confirm the contract sum
Agreed Change Orders: | 87500 |  |  |  |  | SA to confirm the agreed change order value
Pending Change Orders (Estimate): | 17500 |  |  |  |  | SA to confirm the estimated costs of change orders yet to be agreed
Agreed Compensation & Delay Events: | [5 empty] | Note, if a section is N/A - then leave blank
Agreed Employer Claims: | [5 empty] | Note, if a section is N/A - then leave blank
Revised Contract Sum: | 36094709.38 |  |  |  |  | No actions required - cell tot is setup
Payment No. | Month | Forecast Payment | Forecasted Cumulative Value | Amount Certified | Cumulative Value
SA to confirm cash flow forecast : SA to confrim actual monies certified as per date of issue of report
1 | Jan | 1499571.22 | 1499571.22 | 480000 | 480000 | (forecast monies illustration only - figures to come from contractor cash flow)
2 | Feb | 1499571.22 | 2999142.44 | 720000 | 1200000
3 | Mar | 1499571.22 | 4498713.66 | 0 | 1200000
4 | Apr | 1499571.22 | 5998284.88 | 0 | 1200000
5 | May | 1499571.22 | 7497856.1 | 0 | 1200000
6 | Jun | 1499571.22 | 8997427.32 | 0 | 1200000
7 | Jul | 1499571.22 | 10496998.54 | 0 | 1200000
8 | Aug | 1499571.22 | 11996569.76 | 0 | 1200000
9 | Sep | 1499571.22 | 13496140.98 | 0 | 1200000
10 | Oct | 1499571.22 | 14995712.2 | 0 | 1200000
11 | Nov | 1499571.22 | 16495283.42 | 0 | 1200000
12 | Dec | 1499571.22 | 17994854.64 | 0 | 1200000
13 | Jan | 1499571.22 | 19494425.86 | 0 | 1200000
14 | Feb | 1499571.22 | 20993997.08 | 0 | 1200000
15 | Mar | 1499571.22 | 22493568.3 | 0 | 1200000
16 | Apr | 1499571.22 | 23993139.52 | 0 | 1200000
17 | May | 1499571.22 | 25492710.74 | 0 | 1200000
18 | Jun | 1499571.22 | 26992281.96 | 0 | 1200000
19 | Jul | 1499571.22 | 28491853.18 | 0 | 1200000
20 | Aug | 1499571.22 | 29991424.4 | 0 | 1200000
21 | Sep | 1499571.22 | 31490995.62 | 0 | 1200000
22 | Oct | 1499571.22 | 32990566.84 | 0 | 1200000
23 | Nov | 1499571.22 | 34490138.06 | 0 | 1200000
24 | Dec | 1499571.22 | 35989709.28 | 0 | 1200000