## Final Account Report
Final Account Report Template
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional line etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
For Band 2 & 3 Projects the activity cost heads presented are the minimum expected for a linear road project and are to be proposed, discussed and agreed in writing with NTA prior to production of the cost estimate. | [10 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
Project Title: |  |  | Highways Improvement for Urban Environment | [7 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/2/001 5G |  |  | Prepared By (Individual/Organisation): |  |  | Sally Gate - South Dublin Council |  | SA confirm the project code: SA to confirm who has prepared the document
Approving Authority: |  |  | NTA |  |  | Date Prepared: |  |  | 01/09/20** |  | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin | [7 empty] | SA = local authority (or Irish Rail / Bus Éireann etc ...) submitting the application: Base date is the quarter period (Q1 = Jan / Feb / march: Q2 = Apr / May / June: Q3 = July / Aug / Sept: Q4 = Oct / Nov / Dec)
Project Information
Mainline Cross-Section Type: |  |  | 4 Lane carriageway incorporating bus corridors |  | Average Link / Side Road Width (m): | [5 empty] | SA to confirm cross section type: Overall road width to be confirmed by SA
Location: |  |  | ***** |  | Cyclepath Included (Y/N): |  |  |  | Y |  | Identify location - include co-ordinates if available: SA to confirm if cycle path included or not (select cell for dropdown)
Total Mainline Length (m): |  |  | 2700 |  | Footway Included (Y/N): |  |  |  | Y | Y | SA to confirm
N
Total Mainline Width (m): |  |  | 6000 |  | Hardstrip Included (Y/N): |  |  |  | Y |  | SA to confirm
Total Link / Side Road Length (m): |  |  | 0 |  | Central Reserve Included (Y/N): |  |  |  | Y |  | SA to confirm
Start Date: |  |  | 14/04/20** |  | Construction Duration (Months): |  |  |  | 24 |  | SA to confirm potential start on site (Quarter): SA to confirm estimated construction period
Other Relevant Project Information: | [10 empty] | SA to outline (brief) project scope of works
1 | Construction Costs
| Ref | Description | [6 empty] | Final Account (€)
| Enabling Works Costs (Please provide supplementary information giving detail of costs) | [7 empty] | 0 |  | If N/A - leave blank
| 1.1 | Heritage Contracts
| 1.2 | Utilities Contracts
| 1.3 | Archaeological Contracts
| 1.4 | Site Investigation Contracts
| Main Contract(s) Costs (Please provide supplementary information giving detail of costs) | [9 empty] | SA to confirm elemental costs - as per contract award
| 1.5 | Site Clearance | [6 empty] | 1003006.2645
| 1.6 | Fencing | [6 empty] | 230283.2
| 1.7 | Safety Barriers | [6 empty] | 66640
| 1.8 | Earthworks | [6 empty] | 5596276.872
| 1.9 | Drainage | [6 empty] | 4989522.14
| 1.10 | Pavements | [6 empty] | 6308939.656
| 1.11 | Kerbing & Footways | [6 empty] | 5166937.728
| 1.12 | Traffic Signs and Road Marking | [6 empty] | 311912.7752
| 1.13 | Road Lighting | [6 empty] | 687930.04
| 1.14 | Structures (Including Structures Generally) | [6 empty] | 592416.1539
| 1.15 | Accommodation Works | [6 empty] | 198920.8
| 1.16 | Works for Statutory Undertakers | [6 empty] | 2820274.688
| 1.17 | Landscaping & Ecology | [6 empty] | 893177.299
| 1.18 | Other Project Costs | [6 empty] | 4851680 |  | SA to include here for Variations / Change Orders - agreed value
| 1.19 | Preliminaries including Site Compounds (excluding traffic management) | [6 empty] | 3271791.7617
| Sub-Total A - Project Base Costs | [7 empty] | 36989709.3784
2 | Preparation and Administration
| 2.1 | Preparation and Administration Costs | [6 empty] | 5906463.36
| 2.1.1 | Scope & Purpose | [6 empty] | 1688137.92
| 2.1.2 | Concept, Development & Option Selection | [6 empty] | 722135.68
| 2.1.3 | Preliminary Design | [6 empty] | 280732.48
| 2.1.4 | Statutory Processes | [6 empty] | 542241.28
| 2.1.5 | Detailed Design & Procurement | [6 empty] | 2382751.84
| 2.1.6 | Construction & Implementation | [6 empty] | 290464.16
| 2.1.7 | Close Out & Review
| Sub-Total B - Preparation and Administration Costs | [7 empty] | 5906463.36
3 | Traffic Management Related Costs
| 3.1 | Traffic Management Related Costs | [6 empty] | 1623107.37 |  | Note, if N/A (included in construction costs) - leave blank
| Sub-Total C - Traffic Management Related Costs | [7 empty] | 1623107.37
4 | Land and Property Costs
| Ref | Description | [6 empty] | Final Account (€)
| 4.1 | Properties | [6 empty] | 50000
| 4.2 | Garden Ground
| 4.3 | Industrial Development Land
| 4.4 | Amenity Land / Open Space
| 4.5 | Residential Development Land / Urban | [6 empty] | 125000
| 4.6 | Agricultural Ground
| Sub-Total D - Land and Property Costs | [7 empty] | 175000
5 | Future Costs
Add Potential Future Costs
| Sub-Total E - Future Costs | [7 empty] | 0
Total Final Account Value Exclusive of VAT | [8 empty] | 44694280.1084
VAT on Construction Costs and Traffic Management Related Costs |  |  |  |  | 13.5% |  | % | 38612816.7484 | 5212730.261 |  | 13.5% VAT is applied to the construction estimate / Traffic MGT / inflation allowance / contingency allowance
VAT on Preparation and Administration Costs |  |  |  |  | 23% |  | % | 5906463.36 | 1358486.5728 |  | 23% applies to preparation costs (design teams as an example): No VAT should be applied if design is in-house with the SA
VAT on Land and Property |  |  |  |  | 1 |  | Item | 0 | 0
https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [10 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line C54 to determine if VAT is applicable to your project
Total Final Account Value Inclusive of VAT | [8 empty] | 51265496.9422
Mainline Length |  |  | 0 | 2.7 | Km |  |  | Rate Per Km (Excluding VAT) | 16553437.0772
[8 empty] | Rate Per Km (Including VAT) | 18987221.0897
Revision | Title |  |  |  | Prepared By |  | Checked By |  | Issue Date
[5 empty] | Sally Gate |  | M Bunny |  | 01/09/20** |  | SA to sign off (2 parties within their organisation)

## PCD Summary
Project Control Document Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document. | [7 empty] | Guidance Notes
Project Title: |  |  | Highways Improvement for Urban Environment |  |  |  |  | No action required - the text is carried forward automatically from the Final Account Report
Project / Contract Code: |  |  | DLR/2/001 5G | Prepared By (Individual & Organisation) |  |  | Sally Gate - South Dublin Council | No action required - the text is carried forward automatically from the Final Account Report
Approving Authority: |  |  | NTA | Date Prepared: |  |  | 01/09/20** | No action required - the text is carried forward automatically from the Final Account Report
Sponsoring Agency: |  |  | South Dublin |  |  |  |  | No action required - the text is carried forward automatically from the Final Account Report
1 | PCD Summary
| 1.1 | Scope & Purpose |  | 1 | Item | 1688137.92 | 1688137.92 | No action required - the text is carried forward automatically from the Final Account Report
| 1.2 | Concept, Development & Option Selection |  | 1 | Item | 722135.68 | 722135.68 | No action required - the text is carried forward automatically from the Final Account Report
| 1.3 | Preliminary Design |  | 1 | Item | 280732.48 | 280732.48 | No action required - the text is carried forward automatically from the Final Account Report
| 1.4 | Statutory Processes |  | 1 | Item | 542241.28 | 542241.28 | No action required - the text is carried forward automatically from the Final Account Report
| 1.5 | Detailed Design & Procurement |  | 1 | Item | 2382751.84 | 2382751.84 | No action required - the text is carried forward automatically from the Final Account Report
| 1.6 | Construction & Implementation |  | 1 | Item | 290464.16 | 290464.16 | No action required - the text is carried forward automatically from the Final Account Report
| 1.7 | Close Out & Review |  | 1 | Item | 0 | 0 | No action required - the text is carried forward automatically from the Final Account Report
| 1.8 | Construction Cost (Agreed Final Account) |  | 1 | Item | 36989709.3784 | 36989709.3784 | No action required - the text is carried forward automatically from the Final Account Report
| 1.9 | Land Value (Agreed value if applicable) |  | 1 | Item | 175000 | 175000 | No action required - the text is carried forward automatically from the Final Account Report
| Total (excluding VAT) | [5 empty] | 43071172.7384 | No action required - the text is carried forward automatically from the Final Account Report
| Add VAT @ 13.5% | [5 empty] | 5212730.261 | No action required - the text is carried forward automatically from the Final Account Report
| Add VAT @ 23% | [5 empty] | 1358486.5728 | No action required - the text is carried forward automatically from the Final Account Report
| Add VAT on Land (If Applicable) | [5 empty] | 0 | SA to include if applicable pending Revenue rules
| Total Grant Application Cost Estimate (Including VAT) | [5 empty] | 49642389.5722
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.

## Expenditure Profile
Expenditure Profile - Actual and Previously Forecasted
[8 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/2/001 5G | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Final Account Value: |  | 51265496.9422 | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Actual Programme Duration: |  | 24 | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
|  | Total Project Cost |  | Final Account
Year | Quarter | Total Quarterly Expenditure (€) | Cumulative Expenditure (€) | Total Quarterly Expenditure (€) |  | Cumulative Expenditure (€)
Year 1 | Q1 | 2947367.0539 | 2947367.0539 | 2647367.0539 |  | 2647367.0539
| Q2 | 5693777.2632 | 8641144.3171 | 4693777.2632 |  | 7341144.3171
| Q3 | 9852974.9859 | 18494119.303 | 6852974.9859 |  | 14194119.303
| Q4 | 11083074.4588 | 29577193.7618 | 9083074.4588 |  | 23277193.7618
Year 2 | Q1 | 12715087.6209 | 42292281.3827 | 8715087.6209 |  | 31992281.3827
| Q2 | 9980856.6143 | 52273137.997 | 7980856.6143 |  | 39973137.997
| Q3 | 6144407.7632 | 58417545.7601 | 3144407.7632 |  | 43117545.7601
| Q4 | 2478467.7499 | 60896013.51 | 1576734.35 |  | 44694280.1101
Year 3 | Q1 |  | 60896013.51 |  |  | 44694280.1101
| Q2 |  | 60896013.51 |  |  | 44694280.1101
| Q3 |  | 60896013.51 |  |  | 44694280.1101
| Q4 |  | 60896013.51 |  |  | 44694280.1101
Year 4 | Q1 |  | 60896013.51 |  |  | 44694280.1101
| Q2 |  | 60896013.51 |  |  | 44694280.1101
| Q3 |  | 60896013.51 |  |  | 44694280.1101
| Q4 |  | 60896013.51 |  |  | 44694280.1101
Revision | Title |  |  |  | Prepared by | Checked by | Issue Date
[5 empty] | Sally Gate | M Bunny | 2023-09-01 | SA to sign off (2 parties within their organisation)
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Comparison
Total Project Cost and Final Account Comparison
[7 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment |  |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/2/001 5G |  |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Estimate Comparison
Ref | Item |  | Total Project Budget (€) | Final Account (€) | Variance
[5 empty] | € | %
1 | Construction Costs |  |  | 36989709.3784 | 36989709.3784 | 0% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
2 | Preparation and Administration Costs |  | 35989709.38 | 5906463.36 | -30083246.02 | -83.59% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
3 | Traffic Management Related Costs |  | 5906463.36 | 1623107.37 | -4283355.99 | -72.52% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
4 | Land and Property Costs |  | 175000 | 175000 | 0 | 0% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
5 | Risk |  | 9921435.15 | 0 | -9921435.15 | -100% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
6 | Contingency |  | 5236876.72 | 0 | -5236876.72 | -100% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
7 | Inflation Allowance |  | 2021301.53 | 0 | -2021301.53 | -100% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
8 | Potential Future Costs |  |  | 0 | 0 | 0% | SA to confirm (figures are from the Total Project Cost Estimate, form 018_B23)
9 | Total Costs (Cumulative): Ex.VAT |  | 59250786.14 | 44694280.1084 | 14556506.0316 | 24.57%
10 | Add VAT @ 13.5% |  | 7998856.1289 | 5212730.261 | -2786125.8679 | -34.83%
11 | Add VAT @ 23% |  | 1358486.5728 | 1358486.5728 | 0 | 0%
12 | Add VAT on Land (If Applicable) |  | 0 | 0 | 0 | 0%
13 | Total Costs (Including VAT) |  | 68608128.8417 | 51265496.9422 | -17342631.8995 | -25.28%
Programme Comparison
Ref | Item |  | Total Project Budget Programme Duration | Actual Programme Duration (months) | Variance
[5 empty] | Months | %
1 | Anticipated Programme Duration |  | 24 | 24 | 0 | 0% | SA to confirm (figures are from the Preliminary Cost Estimate, form 014_B23)
Commentary on Variances
If cost or programme durations vary by more than 10% or a value advised by the NTA from the Tender Project Cost (Phase 5) detailed substantiation justifying the reason for the variance shall be provided.
If costs are greater than 10% (increase from Preliminary Cost Estimate) - a detailed explanation is required by the SA
Revision | Title |  |  | Prepared by | Checked by
|  |  |  | S Gate | M Bunny