## Cost Estimate
Preliminary Cost Estimate Template
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: For Band 1 Projects the activity cost heads presented are indicative for a linear project, if the project being reported (undertaken/developed) is not a linear project, activity cost heads are to be discussed and agreed in writing with NTA prior to the production of the cost estimate. | [8 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures (€) are illustrative only ****
Project Title: |  |  | R2 - Galway Road - Dublin | [5 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/22/0015G |  | Prepared By (Individual/Organisation): |  |  | Sally Gate - SDC | SA confirm the project code
Approving Authority: |  |  | NTA |  | Date Estimate Prepared: |  |  | 2022-10-09 | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin Council |  | Base Date of Estimate: |  |  | Q4 2022 | SA, local authority submitting the application: Base date is the quarter period (Q1 = Jan / Feb / march: Q2 = Apr / May / June: Q3 = July / Aug / Sept: Q4 = Oct / Nov / Dec)
Project Information
Location: |  |  |  | ****** Galway Road (Co-ordinates ***********,***********) |  |  |  |  | SA to identify the location - if co-ordinates are available please include
Potential Construction Works Start Date: |  |  |  | 2023-01-16 |  |  |  |  | SA to indicate estimated start date on site
Anticipated Construction Works Duration (Months): |  |  |  | 2 months |  |  |  |  | SA to include estimated time period
Other Relevant Project Information: |  |  |  | New Footpath & Public lighting |  |  |  |  | SA to outline (brief) project scope of works
1 | Construction Costs
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 1.1 | Construction Costs |  |  | 1 | item | 173500 | 173500 | SA to confirm cost source data in section below / and assumptions tab
| 1.2 | Preliminaries including site compound costs (excluding traffic management) - % applied to base costs |  |  | 9% | % | 173500 | 15615
| Sub-Total A - Construction Costs | [6 empty] | 189115
2 | Preparation and Administration
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 2.1 | Preparation and Administration Costs | [5 empty] | 60000 | SA to confirm admin costs (design teams etc …)
| 2.1.1 | Scope & Purpose |  |  | 1 | item | 7500 | 7500
| 2.1.2 | Concept, Development & Option Selection |  |  | 1 | item | 11000 | 11000
| 2.1.3 | Preliminary Design |  |  | 1 | item | 5000 | 5000
| 2.1.4 | Statutory Processes |  |  | 1 | item | 5000 | 5000
| 2.1.5 | Detailed Design & Procurement |  |  | 1 | item | 14000 | 14000
| 2.1.6 | Construction & Implementation |  |  | 1 | item | 15000 | 15000
| 2.1.7 | Close Out & Review |  |  | 1 | item | 2500 | 2500
| Sub-Total B - Preparation and Administration Costs | [6 empty] | 60000
3 | Traffic Management Related Costs
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 3.1 | Traffic Management (TM) Related Costs |  |  | 10% | % | 189115 | 18911.5 | SA to allow costs for TM (if applicable) - for example purpose we are allowing 10% based on construction cost
| Sub-Total C - Traffic Management Related Costs | [6 empty] | 18911.5
4 | Land and Property Costs
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 4.1 | Land & Property Costs |  |  | 1 | Item | 47750 | 47750 | SA to estimate the costs - confirm in assumptions tab the m2 land take and the estimated rate (if not agreed)
| Sub-Total D - Land and Property Costs | [6 empty] | 47750
5 | Adjustments
| Add Project Specific Risk (Output From 004_B1_QRA_CMG) |  |  |  | 1 | Item | 42567.45 | 42567.45 | SA to include risk value (as completed in form 004_B1 Updated)
| Add Contingency (001_B123_CC_CMG) |  |  |  | 20% | % | 310593.95 | 62118.79 | SA to include costs as per completed form 001 (updated contingency calculation sheet)
| Per Cent for Art Scheme https://publicart.ie/main/commissioning/funding/per-cent-for-art-scheme/ |  |  |  | 1% | % | 310593.95 | 3105.9395 | SA to review web link for proposed maximum limits. Figure to be amended in cell K54 if required.
| Sub-Total E - Adjustments | [6 empty] | 107792.1795
Total Preliminary Cost Estimate Exclusive of VAT | [7 empty] | 423568.6795
VAT on Construction, TM and Associated Adjustments Costs |  |  |  |  | 13.5% | % | 315818.6795 | 42635.5217 | 13.5% VAT is applied to the construction estimate / risk allowance / contingency allowance / arts
VAT on Preparation and Administration Costs and Associated Adjustment Costs |  |  |  |  | 23% | % | 60000 | 13800 | 23% applies to preparation costs (design teams as an example): No VAT should be applied if design is in-house with the SA
VAT on Land and Property |  |  |  |  | 1 | Item |  | 0
https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [8 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line C54 to determine if VAT is applicable
Total Preliminary Cost Estimate Inclusive of VAT | [7 empty] | 480004.2012
Source of Cost Data (Please provide a brief narrative on the source of cost data in the box below)
Cost estimate is based on works of similar nature where we have a contractor on site. Additionally, we also have a cost from a utility supplier for the public lighting works. It will be the sponsoring agencies proposal to use a contractor (framework) to carry out the works based on tender return | [8 empty] | SA need to have this information available - the calc sheet can be used. Working are to be provided (QTY x Rates)
Revision | Title |  |  |  | Prepared By | Checked By |  | Issue Date
[5 empty] | Sally Gates | Michael Bunny |  | 2022-10-09 | SA to sign off (2 parties within their organisation)
NOTE: | Costs are considered to include allowances for overhead and profit. Costs are reflective of costs at the base date stated above. VAT is not applicable to all land and property therefore it is not appropriate to apply a uniform percentage. The value associated with VAT on land and property is to be determined on an individual basis and included as a lump sum.
Note on K14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)
Note on J61: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on J62: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on J63: Estimating Methodology The applicable VAT rate is to be determined by each user individually. A hyperlink to applicable rules/laws relating to the applicability of VAT is included for reference and assessment purposes.

## PCD Summary
Project Control Document Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document. | [9 empty] | Guidance Notes
Project Title: |  |  | R2 - Galway Road - Dublin | [6 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  |  | DLR/22/0015G | Prepared By (Individual & Organisation) |  |  |  |  | Sally Gate - SDC | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  |  | NTA | Date Estimate Prepared: |  |  |  |  | 2022-10-09 | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  |  | South Dublin Council | Base Date of Estimate: |  |  |  |  | Q4 2022 | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | PCD Summary |  |  |  |  | Sub-Total | VAT % | VAT Amount | Total Incl. VAT
| 1.1 | Scope & Purpose |  | 1 | Item | 7500 | 23 | 1725 | 9225 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2 | Concept, Development & Option Selection |  | 1 | Item | 11000 | 23 | 2530 | 13530 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.3 | Preliminary Design |  | 1 | Item | 5000 | 23 | 1150 | 6150 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.4 | Statutory Processes |  | 1 | Item | 5000 | 23 | 1150 | 6150 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.5 | Detailed Design & Procurement |  | 1 | Item | 14000 | 23 | 3220 | 17220 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.6 | Construction & Implementation |  | 1 | Item | 15000 | 23 | 3450 | 18450 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.7 | Close Out & Review |  | 1 | Item | 2500 | 23 | 575 | 3075 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.8 | Traffic Management |  | 1 | Item | 18911.5 | 13.5 | 2553.0525 | 21464.5525 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.9 | Land & Property Costs |  | 1 | Item | 47750 |  |  | 47750 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.1 | Construction Costs (Main Contractor) |  | 1 | Item | 189115 | 13.5 | 25530.525 | 214645.525 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.11 | Risk Allowance (QRA) |  | 1 | Item | 42567.45 | 13.5 | 5746.6057 | 48314.0557 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.12 | Contingency Allowance |  | 1 | Item | 62118.79 | 13.5 | 8386.0367 | 70504.8267 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.13 | Allowance for Arts (%) |  | 1 | Item | 3105.9395 | 13.5 | 419.3018 | 3525.2413 | No action required - the text is carried forward automatically from the Cost Estimate tab
|  |  |  | Sub-Total (Ex.VAT) |  | 423568.6795
| Add VAT on Land (If Applicable) | [7 empty] | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Total Preliminary Cost Estimate (Including VAT) | [7 empty] | 480004.2012 | No action required - tot's automatically
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.
Note on L14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## Assumptions
Estimate Assumptions, Exclusions and Inclusions
[6 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/22/0015G |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  | NTA |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  | South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Prepared By (Individual/Organisation): |  | Sally Gate - SDC |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | Construction Costs
| Construction cost estimate is based on similar works (recent tender returns). The Local Authroity are satisfied the project can be delivered for the estimated construction cost as outlined |  |  |  |  | SA to give as much information as possible
2 | Delivery and Construction Programme
| Tender process for construction will be issued in early November 2022 at the latest. Works on site to commence in early 2023 and complete scheme in quarter 1 of 2023 (estimated construction time period to be 2 months) |  |  |  |  | SA to give information on the programme
3 | Preparation and Administration Costs
| Scheme has been designed in Q3 of 2022, the lead design team is ********* Ltd. |  |  |  |  | SA to input the consultants etc …. On the scheme (or if in house)
(note, no VAT on inhouse (SA) staff costs)
4 | Traffic Management Related Costs
| Traffic management (TM) costs are included into the estimate - TM costs will also be included into the tender documents for pricing / inclusion. |  |  |  |  | SA to inlcude for TM if applicable to the proejct scope
5 | Land and Property Costs
| We confrim there is 45m2 of land take required. Cost has been agreed at €950/m2 with the effected owners: additionally to re-build a stone wall an additional €5,000 is esimated cost. Total cost €47,750 |  |  |  |  | SA to give as much details as possible on land take / agreements etc … to determine cost accuracy
6 | Other Relevant Information
Any other relevant information, general assumptions, exclusions or inclusions that have been used to develop the cost estimate shall be included in this section.
Revision | Title |  | Prepared By | Checked By | Issue Date
|  |  | Sally Gate | Michael Bunny | 2022-10-09 | SA to sign off (2 parties within their organisation)

## Expenditure Profile
Expenditure Profile
|  |  |  | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/22/0015G |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Preliminary Cost Estimate: |  | 480004.2012 |  | No action required - the text is carried forward automatically from the Cost Estimate tab (VAT inclusive figure)
Anticipated Programme Duration: |  | 2 | Months | SA to confirm / imput programme
Preliminary Cost Estimate
Year | Quarter | Total Quarterly Expenditure (€) | Total Cumulative Expenditure (€)
Year 1 | Q1 |  | 0
| Q2 |  | 0
| Q3 |  | 0
| Q4 |  | 0
Year 2 | Q1 | 476478.96 | 476478.96 | SA to input the total cost (VAT inclusive)
| Q2 |  | 476478.96
| Q3 |  | 476478.96
| Q4 |  | 476478.96
Year 3 | Q1 |  | 476478.96
| Q2 |  | 476478.96
| Q3 |  | 476478.96
| Q4 |  | 476478.96
Year 4 | Q1 |  | 476478.96
| Q2 |  | 476478.96
| Q3 |  | 476478.96
| Q4 |  | 476478.96
Revision | Title
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Estimate Comparisons
Estimate Comparisons
[7 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin
Project / Contract Code: |  | DLR/22/0015G
Estimate Comparison
Ref | Item |  | Select Previous Cost Estimate | Preliminary Cost Estimate | Variance
[5 empty] | € | %
1 | Construction Costs |  | 200000 | 189115 | -10885 | -5.442% | SA to confirm
2 | Preparation and Administration Costs |  | 65000 | 60000 | -5000 | -7.692% | SA to confirm
3 | Traffic Management Related Costs |  | 20000 | 18911.5 | -1088.5 | -5.442% | SA to confirm
4 | Land and Property Costs |  | 67500 | 47750 | -19750 | -29.26% | SA to confirm
6 | Risk |  | 14250 | 42567.45 | 28317.45 | 198.7% | SA - to include the inflation amount that was included in the Grant Application cost Estimate (Form 002_B123)
7 | Contingency |  | 29925 | 62118.79 | 32193.79 | 107.6% | SA to confirm
8 | Per Cent for Art Scheme |  | 3000 | 3105.9395 | 105.9395 | 3.531% | SA to confirm
9 | Total Costs (Cumulative) |  | 399675 | 423568.6795 | 23893.6795 | 5.978% | SA to confirm
10 | Add VAT @ 13.5% |  | 35663.63 | 42635.5217 | 6971.8917 | 19.55% | SA to confirm
11 | Add VAT @ 23% |  | 14950 | 13800 | -1150 | -7.692% | SA to confirm
12 | Add VAT on Land (If Applicable) |  | 0 |  | 0 | 0% | SA to confirm
13 | Total Costs (Including VAT) |  | 450288.63 | 480004.2012 | 29715.5712 | 6.599%
Programme Comparison
Ref | Item |  | Select Previous Cost Estimate | Preliminary Cost Estimate | Variance
[5 empty] | Months | %
1 | Anticipated Programme Duration |  | 2 | 2 | 0 | 0% | SA to confirm (programme)
Commentary on Variances
If costs vary more than 10% or a value advised by NTA from the last cost estimate please provide a commentary in the space below:
If costs are greater than 10% (increase from Preliminary Cost Estimate) - a detailed explanation is required by the SA
Rev | Title |  |  | Prepared by | Checked by | Issue Date
|  |  |  | Sally Gates | Michael Bunny | 2022-10-09 | SA to sign off (2 parties within their organisation)

## Calc Sheet
Guidance Notes (If works carried out by direct labour - Example below)
Ref | Description | QTY | Unit | Rate | Total | ** Figures are only illustrative ****
| Labour |  |  |  |  | No VAT (13.5%) to be applied on SA direct labour costs
| - Supervisor (2 months) | 40 | day | 250 | 10000
| - General operative - 5 number (2 months) | 200 | day | 170 | 34000
| - Carpenter 2 number (1 months) | 40 | day | 200 | 8000
52000
Specialist Contractor (******** Utilities Limited)
| Public Lighting Works: -Supply & Installation of * No. 8m Octagonal Public Lighting Columns -Supply & Installation of * No. Fuse Units -Supply & Installation of * No. Urbis Axia LED Lanterns -Supply & Installation of * No. Photocell Units -Supply & Install * No. Unmetered Micro Pillar -* No. ESB Unmetered Connection Fees and Applications Complete -Supply & Install of PL Cable & Accessories as required -Testing and Commissioning included | 1 | item | 35000 | 35000
[5 empty] | 35000 | SA to include for VAT (13.5%) on specialist works contractor
| Materials |  |  |  |  | SA to include VAT on materials at 23%
| - Concrete | 100 | m3 | 135 | 13500
| - Timber 100 x 50mm (110 no 4.8m lengths) | 115 | no | 18 | 2070
| - Mesh A142 - 110 sheets | 110 | no | 50 | 5500
| - Kerbs | 560 | no | 20 | 11200
| - Lean mix | 50 | m3 | 120 | 6000
| - Nails | 1 | item | 3500 | 3500
| - Spray paint | 1 | item | 150 | 150
| - Ancillary hire tools | 1 | item | 1500 | 1500
| - PPE for staff (including signage) | 1 | item | 3500 | 3500
| - Portaloo hire for 2 months | 8 | weeks | 200 | 1600
48520
|  |  |  | 23% | 11159.6
59679.6