## Final Account Report
Final Account Report Template
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: For Band 1 Projects the activity cost heads presented are indicative for a linear project, if the project being reported (undertaken/developed) is not a linear project, activity cost heads are to be discussed and agreed in writing with NTA prior to the production of the Final Account Report. | [8 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are Illustrative ***
Project Title: |  |  | R2 - Galway Road - Dublin | [5 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLD/22/001 5G |  | Prepared By (Individual/Organisation): |  |  | Sally Gate - South Dublin Council | SA confirm the project code
Approving Authority: |  |  | NTA |  | Date Prepared: |  |  | 2023-04-28 | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin Council | [5 empty] | SA = local authority (or Irish Rail / Bus Éireann etc ...)
Project Information
Location: |  |  | ****** Galway Road (Co-ordinates ***********,***********) | [5 empty] | Identify location - include co-ordinates if available
Start Date: |  |  | 2023-02-06 | [5 empty] | SA to confirm when the project started
Other Relevant Project Information: |  |  | New Footpath & Public Lighting | [5 empty] | SA to outline (brief) project scope of works
Total Link / Side Road Length (m): |  |  | 500 | [5 empty] | SA to confirm the total 'm' of works complete
Construction Duration (Months): |  |  | 2 months (finished on site 31/03/2023 and new path opened to the public) | [5 empty] | SA to programme duration
1 | Construction Costs
| Ref | Description | [5 empty] | Final Account (€)
| Main Contract(s) Costs (Please provide supplementary information giving detail of costs) | [7 empty] | SA to give the elemental breakdown (Summary) as per final account agreement
| 1.1 | Preliminaries (Including Traffic Management) | [5 empty] | 18000
| 1.2 | Site Clearance | [5 empty] | 5000
| 1.3 | Fencing | [5 empty] | 3500
| 1.4 | Drainage & Service Ducts | [5 empty] | 15000
| 1.5 | Earth Works | [5 empty] | 35000
| 1.6 | Pavements | [5 empty] | 65000
| 1.7 | Kerbs, Footways & Paved Areas | [5 empty] | 22000
| 1.8 | Traffic Signs & Road Markings | [5 empty] | 3500
| 1.9 | Road Lighting Columns (Civils) | [5 empty] | 9500
| 1.10 | CCTV Survey of Road Drainage Systems | [5 empty] | 4200
| 1.11 | Specialist (Public Lighting Contractor) | [5 empty] | 17500
| 1.12 | Variations to Contract (Agreed Variations for Additional Scope) | [5 empty] | 31500 | If Variations on the job - include into Elemental section (under 'Variations' heading)
1.13
1.14
1.15
| Sub-Total A - Project Base Costs | [6 empty] | 229700
2 | Preparation and Administration
| 2.1 | Preparation and Administration Costs | [5 empty] | 72100 | SA to confirm admin costs (design teams etc …)
| 2.1.1 | Scope & Purpose | [5 empty] | 5500
| 2.1.2 | Concept, Development & Option Selection | [5 empty] | 7100
| 2.1.3 | Preliminary Design | [5 empty] | 12000
| 2.1.4 | Statutory Processes | [5 empty] | 15000
| 2.1.5 | Detailed Design & Procurement | [5 empty] | 15000
| 2.1.6 | Construction & Implementation | [5 empty] | 15000
| 2.1.7 | Close Out & Review | [5 empty] | 2500
| Sub-Total B - Preparation and Administration Costs | [6 empty] | 72100
3 | Traffic Management Related Costs
| 3.1 | Traffic Management Related Costs | [6 empty] | SA note - if included above in contract price leave blank
| Sub-Total C - Traffic Management Related Costs | [6 empty] | 0
4 | Land and Property Costs
| Ref | Description |  | Quantity |  | Unit | Rate | Final Account (€)
| 4.1 | Land & Property Costs | [5 empty] | 47750 | SA to confirm final agreed land value price
| Sub-Total D - Land and Property Costs | [6 empty] | 47750
5 | Future Costs
Add Potential Future Costs
[8 empty] | 15000 | SA to advise on a budget cost if future works were to occur - an example been a raised table / speed ramp for at pedestrian crossing at the end of the footpath
| Sub-Total E - Future Costs | [6 empty] | 15000
Total Final Account Value Exclusive of VAT | [7 empty] | 364550
VAT on Construction Costs and Traffic Management Related Costs |  |  |  | 13.5% |  | % | 244700 | 33034.5 | 13.5% on construction / traffic management / future costs
VAT on Preparation and Administration Costs |  |  |  | 23% |  | % | 72100 | 16583 | 23% on professional services (preparation and administration)
VAT on Land and Property |  |  |  | 1 |  | Item | 0 | 0
https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [8 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line B75 to determine if VAT is applicable
Total Final Account Value Inclusive of VAT | [7 empty] | 414167.5
Revision | Title |  |  | Prepared By |  | Checked By |  | Issue Date
|  |  |  | Sally Gates |  | Michael Bunny |  | 2023-04-28 | SA to sign off (2 parties within their organisation)

## PCD Summary
Project Control Document Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document. | [9 empty] | Guidance Notes
Project Title: |  |  | R2 - Galway Road - Dublin | [6 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  |  | DLD/22/001 5G | Prepared By (Individual & Organisation) |  |  |  |  | Sally Gate - South Dublin Council | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  |  | NTA | Date Prepared: |  |  |  |  | 2023-04-28 | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  |  | South Dublin Council
1 | PCD Summary |  |  |  |  | Sub-Total | VAT % | VAT Amount | Total Incl. VAT
| 1.1 | Scope & Purpose |  | 1 | Item | 5500 | 23 | 1265 | 6765 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2 | Concept, Development & Option Selection |  | 1 | Item | 7100 | 23 | 1633 | 8733 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.3 | Preliminary Design |  | 1 | Item | 12000 | 23 | 2760 | 14760 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.4 | Statutory Processes |  | 1 | Item | 15000 | 23 | 3450 | 18450 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.5 | Detailed Design & Procurement |  | 1 | Item | 15000 | 23 | 3450 | 18450 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.6 | Construction & Implementation |  | 1 | Item | 15000 | 23 | 3450 | 18450 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.7 | Close Out & Review |  | 1 | Item | 2500 | 23 | 575 | 3075 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.8 | Traffic Management |  | 1 | Item | 0 | 13.5 | 0 | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.9 | Land & Property Costs |  | 1 | Item | 47750 |  |  | 47750 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.1 | Construction Costs (Main Contractor) |  | 1 | Item | 229700 | 13.5 | 31009.5 | 260709.5 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.11 | Potential Future Costs |  | 1 | Item | 15000 | 13.5 | 2025 | 17025 | No action required - the text is carried forward automatically from the Cost Estimate tab
|  |  |  | Sub-Total (Ex.VAT) |  | 364550
| Add VAT on Land (If Applicable) | [7 empty] | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Total Final Account Report (Including VAT) | [7 empty] | 414167.5 | No action required - tot's automatically
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.

## Expenditure Profile
Expenditure Profile - Actual and Previously Forecasted
[8 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLD/22/001 5G | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Final Account Value: |  | 414167.5 | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab (Figure Includes VAT)
Actual Programme Duration: |  | 2 Months | [5 empty] | SA to include / confirm
|  | Total Project Cost |  | Final Account
Year | Quarter | Total Quarterly Expenditure (€) | Cumulative Expenditure (€) | Total Quarterly Expenditure (€) |  | Cumulative Expenditure (€)
Year 1 | Q1 |  | 0 |  |  | 0
| Q2 |  | 0 |  |  | 0
| Q3 |  | 0 |  |  | 0
| Q4 |  | 0 |  |  | 0
Year 2 | Q1 | 0 | 0 | 414167.8 |  | 414167.8 |  | SA to include the expenditure per quarter (actual monies spent "Final Account")
| Q2 |  | 0 |  |  | 414167.8
| Q3 |  | 0 |  |  | 414167.8
| Q4 |  | 0 |  |  | 414167.8
Year 3 | Q1 |  | 0 |  |  | 414167.8
| Q2 |  | 0 |  |  | 414167.8
| Q3 |  | 0 |  |  | 414167.8
| Q4 |  | 0 |  |  | 414167.8
Year 4 | Q1 |  | 0 |  |  | 414167.8
| Q2 |  | 0 |  |  | 414167.8
| Q3 |  | 0 |  |  | 414167.8
| Q4 |  | 0 |  |  | 414167.8
Revision | Title |  |  |  | Prepared by | Checked by | Issue Date
[5 empty] | S Gate | M Bunny | 2023-04-28
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Comparison
Total Project Cost and Final Account Comparison
[7 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | R2 - Galway Road - Dublin
Project / Contract Code: |  | DLD/22/001 5G
Estimate Comparison
Ref | Item |  | Total Project Budget (€) | Final Account (€) | Variance
[5 empty] | € | %
1 | Construction Costs |  | 198200 | 229700 | -31500 | -15.89% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
2 | Preparation and Administration Costs |  | 72100 | 72100 | 0 | 0% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
3 | Traffic Management Related Costs |  |  | 0 | 0 | 0% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
4 | Land and Property Costs |  | 47750 | 47750 | 0 | 0% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
5 | Risk |  | 41478.65 | 0 | 41478.65 | 100% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
6 | Contingency |  | 19820 | 0 | 19820 | 100% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
7 | Potential Future Costs |  |  | 15000 | -15000 | 0% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
8 | Total Costs (Cumulative) |  | 379348.65 | 364550 | 14798.65 | 3.901% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
9 | Add VAT @ 13.5% |  | 35032.32 | 33034.5 | 1997.82 | 5.703% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
10 | Add VAT @ 23% |  | 16583 | 16583 | 0 | 0% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
11 | Add VAT on Land (If Applicable) |  | 0 | 0 |  | 0% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
12 | Total Costs (Including VAT) |  | 430963.97 | 414167.5 | 16796.47 | 3.897% | SA to confirm / input (figures from form 006_B1) - Figures in Column F automatically come from the first tab (Final Account Report)
Programme Comparison
Ref | Item |  | Total Project Budget Programme Duration | Actual Programme Duration (months) | Variance
[5 empty] | Months | %
1 | Anticipated Programme Duration |  | 2 | 2 | 0 | 0% | SA to confirm
Commentary on Variances
If cost or programme durations vary by more than 10% or a value advised by the NTA from the Tender Project Cost (Phase 5) detailed substantiation justifying the reason for the variance shall be provided. | [6 empty] | If costs are greater than 10% (increase from Preliminary Cost Estimate) - a detailed explanation is required by the SA
Revision | Title |  |  | Prepared by | Checked by
|  |  |  | Sally Gates | Michael Bunny |  | SA to sign off (2 parties within their organisation)