## Cost Estimate
Preliminary Cost Estimate Template | [11 empty] | NTA template - 015_B23 (Word Document) - this is the cover pages for the Preliminary Cost Estimate (014-B23)
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional line etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: For Band 2 & 3 Projects the activity cost heads presented are the minimum expected for a linear road project and are to be proposed, discussed and agreed in writing with NTA prior to production of the cost estimate. | [11 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
Project Title: |  |  | Highways Improvement for Urban Environment | [8 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/12/0015A |  | Prepared By (Individual/Organisation): |  |  | Sally Gate - South Dublin Council |  |  |  | SA confirm the project code: SA to confirm who has prepared the document
Approving Authority: |  |  | NTA |  | Date Estimate Prepared: |  |  | 2018-06-02 |  |  |  | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin |  | Base Date of Estimate: |  |  | Q4 2022 |  |  |  | SA = local authority (or Irish Rail / Bus Éireann etc ...) submitting the application: Base date is the quarter period (Q1 = Jan / Feb / march: Q2 = Apr / May / June: Q3 = July / Aug / Sept: Q4 = Oct / Nov / Dec)
Project Information
SA to confirm cross section type: Overall road width to be confirmed by SA
Mainline Cross-Section Type: |  |  |  | 4 Lane Carriageway incorportating bus corridor | Average Link / Side Road Width (m):
Location: |  |  |  | XXX City Centre | Cyclepath Included (Y/N): |  |  | Y |  |  |  | Identify location - include co-ordinates if available: SA to confirm if cycle path included or not (select cell for dropdown)
Total Mainline Length (m): |  |  |  | 2700 | Footway Included (Y/N): |  |  | Y | Y |  |  | SA to confirm (select from dropdown menu for Y/N section)
N
Total Mainline Width (m): |  |  |  | 4 | Hardstrip Included (Y/N): |  |  | Y |  |  |  | SA to confirm (select from dropdown menu for Y/N section)
Total Link / Side Road Length (m): |  |  |  |  | Central Reserve Included (Y/N): |  |  | Y |  |  |  | SA to confirm (select from dropdown menu for Y/N section)
Potential Construction Works Start Date: |  |  |  | Q2 2019 | Anticipated Construction Works Duration (Months): |  |  | 24 |  |  |  | SA to confirm potential start on site (Quarter): SA to confirm estimated construction period
Other Relevant Project Information: |  |  |  | New Footpath & Public Lighting | [7 empty] | SA to outline (brief) project scope of works
1 | Construction Costs
| Ref | Description | [5 empty] | Total |  |  |  | SA to confirm elemental costs
| 1.1 | Site Clearance | [5 empty] | 600000
| 1.2 | Fencing | [5 empty] | 150000
| 1.3 | Road Restraint Systems | [5 empty] | 50000
| 1.4 | Drainage & Service Ducts | [5 empty] | 5150000
| 1.5 | Earthworks | [5 empty] | 3658000
| 1.6 | Pavements | [5 empty] | 5150000
| 1.7 | Footways & Kerbing | [5 empty] | 5658000
| 1.8 | Traffic Signs & Road Marking | [5 empty] | 260000
| 1.9 | Road Lighting | [5 empty] | 575000
| 1.1 | Structural Concrete (Including Structures Generally) | [5 empty] | 486500
| 1.11 | Accommodation Works | [5 empty] | 150000
| 1.12 | Works for Statutory Undertakers | [5 empty] | 1600000
| 1.13 | Landscaping & Ecology | [5 empty] | 650000
| 1.14 | Other Project Costs | [5 empty] | 0
| 1.15 | Preliminaries including site compound costs (excluding traffic management) - % applied to base costs |  |  | 10% | % | 24137500 | 2413750
| Sub-Total A - Construction Costs | [6 empty] | 26551250
2 | Preparation and Administration
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 2.1 | Preparation and Administration Costs | [5 empty] | 3100000 |  |  |  | SA to confirm admin costs (design teams etc …)
| 2.1.1 | Scope & Purpose |  |  | 1 | item | 175000 | 175000
| 2.1.2 | Concept, Development & Option Selection |  |  | 1 | item | 650000 | 650000
| 2.1.3 | Preliminary Design |  |  | 1 | item | 450000 | 450000
| 2.1.4 | Statutory Processes |  |  | 1 | item | 75000 | 75000
| 2.1.5 | Detailed Design & Procurement |  |  | 1 | item | 1500000 | 1500000
| 2.1.6 | Construction & Implementation |  |  | 1 | item | 250000 | 250000
| 2.1.7 | Close Out & Review |  |  | 1 | iten |  | 0
| Sub-Total B - Preparation and Administration Costs | [6 empty] | 3100000
3 | Traffic Management Related Costs
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 3.1 | Traffic Management (TM) Related Costs |  |  | 5% | % | 26551250 | 1327562.5 |  |  |  | SA to allow costs (estimate) for TM (if applicable to there project)
| Sub-Total C - Traffic Management Related Costs | [6 empty] | 1327562.5
4 | Land and Property Costs | [10 empty] | SA to confirm type of land take & estimated costs
| Ref | Description |  |  | Quantity | Unit | Rate | Total (€)
| 4.1 | Properties |  |  | 1 | Nr | 50000 | 50000
| 4.2 | Garden Ground |  |  |  | Ha |  | 0 |  |  |  | SA to confirm measure (hectare / m2 / acres)
| 4.3 | Industrial Development Land |  |  |  | m2 |  | 0
| 4.4 | Amenity Land / Open Space |  |  |  | Ha |  | 0
| 4.5 | Residential Development Land / Urban |  |  | 1 | Ha | 125000 | 125000
| 4.6 | Agricultural Land |  |  |  | Ha |  | 0
| Sub-Total D - Land and Property Costs | [6 empty] | 175000
5 | Adjustments
| Add Inflation |  |  |  | 12% | % | 30978812.5 | 3717457.5 | % |  |  | SA to confirm if inflation needs to be applied - example, if works were not to happen until Q2 2023, NTA would recommend applying % cost - say 5% for example purpose (Inflation calc does not include for Land take). Refer to the NTA bulletin for guidance on inflation allowances
| Add Project Specific Risk (013_B23_QRA_CMG) |  |  |  | 1 | Item | 8459829.67 | 8459829.67 | Item | % | % | SA to include costs based on QRA assessment (form 013_B23)
| Add Contingency (001_B123_CC_CMG) |  |  |  | 37.5% | % | 43156099.67 | 16183537.3763 |  | Item | 1 | SA to update the contingency calculator (form 013_B123) - total cost is based on Sub-total A+B+Traffic Management+Inflation+Risk
| Per Cent for Art Scheme https://publicart.ie/main/commissioning/funding/per-cent-for-art-scheme/ |  |  |  | 1% | % | 43156099.67 | 431560.9967 |  |  |  | SA to review web link for proposed maximum limits
| Sub-Total E - Adjustments | [6 empty] | 28792385.543
Total Preliminary Cost Estimate Exclusive of VAT | [7 empty] | 59946198.043
VAT on Construction, TM and Associated Adjustments Costs |  |  |  |  | 13.5% | % | 56671198.043 | 7650611.7358 |  |  |  | 13.5% VAT is applied to the construction estimate / Traffic MGT / inflation allowance / contingency allowance
VAT on Preparation and Administration Costs and Associated Adjustment Costs |  |  |  |  | 23% | % | 3100000 | 713000 |  |  |  | 23% applies to preparation costs (design teams as an example): No VAT should be applied if design is in-house with the SA
VAT on Land and Property |  |  |  |  | 1 | Item |  | 0
https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [11 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line C54 to determine if VAT is applicable to your project
Total Preliminary Cost Estimate Inclusive of VAT | [7 empty] | 68309809.7787
Mainline Length |  |  | 0 | 2.7 | Km |  | Rate Per Km (Excluding VAT) | 22202295.5715
[7 empty] | Rate Per Km (Including VAT) | 25299929.5477
Source of Cost Data (Please provide a brief narrative on the source of cost data in the box below)
Revision | Title |  |  |  | Prepared By | Checked By |  | Issue Date
[5 empty] | Sally Gate | Michael Bunny |  | 2022-10-25 |  |  |  | SA to sign off (2 parties within their organisation)
NOTE: | Costs are considered to include allowances for overhead and profit. Costs are reflective of costs at the base date stated above. VAT is not applicable to all land and property therefore it is not appropriate to apply a uniform percentage. The value associated with VAT on land and property is to be determined on an individual basis and included as a lump sum.
Note on K14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)
Note on J86: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on J87: Estimating Methology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on J88: Estimating Methodology The applicable VAT rate is to be determined by each user individually. A hyperlink to applicable rules/laws relating to the applicability of VAT is included for reference and assessment purposes.

## PCD Summary
Project Control Document Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document. | [9 empty] | Guidance Notes
Project Title: |  |  | Highways Improvement for Urban Environment | [6 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  |  | DLR/2/001 5G | Prepared By (Individual & Organisation) |  |  |  |  | Sally Gate - South Dublin Council | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  |  | NTA | Date Estimate Prepared: |  |  |  |  | 2018-06-02 | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  |  | South Dublin | Base Date of Estimate: |  |  |  |  | Q4 2022 | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | PCD Summary |  |  |  |  | Sub-Total | VAT % | VAT Amount | Total Incl. VAT
| 1.1 | Scope & Purpose |  | 1 | Item | 175000 | 23 | 40250 | 215250 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2 | Concept, Development & Option Selection |  | 1 | Item | 650000 | 23 | 149500 | 799500 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.3 | Preliminary Design |  | 1 | Item | 450000 | 23 | 103500 | 553500 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.4 | Statutory Processes |  | 1 | Item | 75000 | 23 | 17250 | 92250 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.5 | Detailed Design & Procurement |  | 1 | Item | 1500000 | 23 | 345000 | 1845000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.6 | Construction & Implementation |  | 1 | Item | 250000 | 23 | 57500 | 307500 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.7 | Close Out & Review |  | 1 | Item | 0 | 23 | 0 | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.8 | Traffic Management |  | 1 | Item | 1327562.5 | 13.5 | 179220.9375 | 1506783.4375 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.9 | Land & Property Costs |  | 1 | Item | 175000 |  |  | 175000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.1 | Construction Costs (Main Contractor) |  | 1 | Item | 26551250 | 13.5 | 3584418.75 | 30135668.75 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.11 | Inflation Allowance (Band 2/3 Only) |  | 1 | Item | 3717457.5 | 13.5 | 501856.7625 | 4219314.2625 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.12 | Risk Allowance (QRA) |  | 1 | Item | 8459829.67 | 13.5 | 1142077.0055 | 9601906.6755 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.13 | Contingency Allowance |  | 1 | Item | 16183537.3763 | 13.5 | 2184777.5458 | 18368314.922 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.14 | Allowance for Arts (%) |  | 1 | Item | 431560.9967 | 13.5 | 58260.7346 | 489821.7313 | No action required - the text is carried forward automatically from the Cost Estimate tab
|  |  |  | Sub-Total (Ex.VAT) |  | 59946198.043
| Add VAT on Land (If Applicable) | [7 empty] | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Total Preliminary Cost Estimate (Including VAT) | [7 empty] | 68309809.7787 | No action required - tot's automatically
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.
Note on L14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## Assumptions
Estimate Assumptions, Exclusions and Inclusions
[6 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/12/0015A |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  | NTA |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  | South Dublin |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Prepared By (Individual/Organisation): |  | Sally Gate - South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | Construction Costs
| Construction cost estimate is based on similar works (recent tender returns). The Local Authroity are satisfied the project can be delivered for the estimated construction cost as outlined |  |  |  |  | SA to give as much information as possible
2 | Delivery and Construction Programme
| Tender process for construction will be issued in early November 2022 at the latest. Works on site to commence in early 2023 and complete scheme in quarter 2 of 2023 (estimated construction time period to be 24 months) |  |  |  |  | SA to give information on the programme
3 | Preparation and Administration Costs
| Scheme has been designed in Q3 of 2022, the lead design team is ********* Ltd. |  |  |  |  | SA on consultants etc …..
4 | Traffic Management Related Costs
| Traffic management (TM) costs are included into the estimate - TM costs will also be included into the tender documents for pricing / inclusion. |  |  |  |  | SA to inlcude for TM if applicable to the proejct scope
5 | Land and Property Costs
| Area is identified - cost negotiations are still on-going with the relevant parties |  |  |  |  | SA to give as much details as possible on land take / agreements etc … to determine cost accuracy
6 | Other Relevant Information
Any other relevant information, general assumptions, exclusions or inclusions that have been used to develop the cost estimate shall be included in this section.
Revision | Title |  | Prepared By | Checked By | Issue Date
|  |  | Sally Gate | Michael Bunny | 2022-10-25 | SA to sign off (2 parties within their organisation)

## Expenditure Profile
Expenditure Profile
[8 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures & spend per quarter is illustrative only ***
Project Title: |  | Highways Improvement for Urban Environment | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/12/0015A | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Preliminary Cost Estimate: |  | 68309809.7787 | [5 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab - Include figure with VAT
Anticipated Programme Duration: |  | 24 | Months |  |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
|  | Select Previous Cost Estimate |  | Preliminary Cost Estimate
Year | Quarter | Total Quarterly Expenditure (€) | Total Cumulative Expenditure (€) | Total Quarterly Expenditure (€) |  | Total Cumulative Expenditure (€) |  | Note - Year 1 is from the date of the Grant Application submission
Year 1 | Q1 |  | 0 |  |  | 0 |  | SA to include the expenditure per quarter
| Q2 | 80000 | 80000 | 80000 |  | 80000
| Q3 | 175000 | 255000 | 175000 |  | 255000
| Q4 | 175000 | 430000 | 175000 |  | 430000
Year 2 | Q1 | 450000 | 880000 | 2450000 |  | 2880000
| Q2 | 1800000 | 2680000 | 3800000 |  | 6680000
| Q3 | 4500000 | 7180000 | 8500000 |  | 15180000
| Q4 | 4500000 | 11680000 | 6500000 |  | 21680000
Year 3 | Q1 | 6000000 | 17680000 | 8000000 |  | 29680000
| Q2 | 6000000 | 23680000 | 7000000 |  | 36680000
| Q3 | 7500000 | 31180000 | 8500000 |  | 45180000
| Q4 | 7500000 | 38680000 | 7500000 |  | 52680000
Year 4 | Q1 | 7500000 | 46180000 | 7500000 |  | 60180000
| Q2 | 6000000 | 52180000 | 6000000 |  | 66180000
| Q3 | 1309938.21 | 53489938.21 | 1639988.05 |  | 67819988.05
| Q4 |  | 53489938.21 |  |  | 67819988.05
Revision | Title |  |  |  | Prepared by | Checked by | Issue Date
[5 empty] | Sally Gate | M Bunny | 2022-10-25 | SA to sign off (2 parties within their organisation)
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Estimate Comparisons
Estimate Comparisons
[7 empty] | Guidance Notes | * All cells in purple - input is required
Project Title: |  | Highways Improvement for Urban Environment
Project / Contract Code: |  | DLR/12/0015A
Estimate Comparison | [6 empty] | Note, figures to be obtained from "Feasibility Working Cost Estimate"
Ref | Item |  | Select Previous Cost Estimate | Preliminary Cost Estimate | Variance
[5 empty] | € | %
1 | Construction Costs |  | 20016150 | 26551250 | 6535100 | 32.65% | SA to confirm
2 | Preparation and Administration Costs |  | 3000000 | 3100000 | 100000 | 3.333% | SA to confirm
3 | Traffic Management Related Costs |  | 1000807.5 | 1327562.5 | 326755 | 32.65% | SA to confirm
4 | Land and Property Costs |  | 125000 | 175000 | 50000 | 40% | SA to confirm
5 | Inflation |  | 4803391.5 | 3717457.5 | -1085934 | -22.61% | SA to confirm
6 | Risk |  | 0 | 8459829.67 | 8459829.67 | 0% | SA to confirm
7 | Contingency |  | 17946116.38 | 16183537.3763 | -1762579.0037 | -9.822% | SA to confirm
8 | Per Cent for Art Scheme |  | 450000 | 431560.9967 | -18439.0033 | -4.098% | SA to confirm
9 | Total Costs (Cumulative) |  | 47341465.38 | 59946198.043 | 12604732.663 | 26.63% | SA to confirm
10 | Add VAT @ 13.5% |  | 5908472.83 | 7650611.7358 | 1742138.9058 | 29.49% | SA to confirm
11 | Add VAT @ 23% |  | 690000 | 713000 | 23000 | 3.333% | SA to confirm
12 | Add VAT on Land (If Applicable) |  | 0 | 0 | 0 | 0% | SA to confirm
13 | Total Costs (Including VAT) |  | 53939938.21 | 68309809.7787 | 14369871.5687 | 26.64%
Programme Comparison
Ref | Item |  | Select Previous Cost Estimate | Preliminary Cost Estimate | Variance
[5 empty] | Months | %
1 | Anticipated Programme Duration |  | 24 | 24 | 0 | 0% | SA to confirm (programme)
Commentary on Variances
If costs vary more than 10% or a value advised by NTA from the last cost estimate please provide a commentary in the space below:
Large variance at this phase is mainly due to the RISK allowances included into the cost estiamte. The Local Authority in conjunction with the appointed design team and factoring all the identified risks into the designs to eliminate or manage accordingly and capture into the scheme when tendering | [6 empty] | If costs are greater than 10% (increase from Feasibility Working Cost Estimate) - a detailed explanation is required by the SA
Rev | Title |  |  | Prepared by | Checked by | Issue Date
|  |  |  | Sally Gate | Michael Bunny | 2018-06-02 | SA to sign off (2 parties within their organisation)