## Cover Page
| Guidance Notes | *** Figures are illustrative ***
Monthly cost reports is required for all NTA Band 2 / 3 projects: Completed cost reports are to be issued to the NTA Programme Manager
** Financial Reports are required Monthly - submission from the Sponsoring Agency to the NTA PM **
Cost Report No_01 | SA to confirm report number
Construction Phase Financial Report
Band 2 (€0.5-10 Million) & Band 3 (€10 Million+) Projects
Highways Improvement for Urban Environment - Dublin | SA to confirm the project title
Project Code: SDCC-**-**** | SA to confirm the project code
National Transport Authority | SA to confirm the approving authority
South Dublin Council | SA to enter the sponoring agency
If no partnering organisation (leave blank)
XXXX JPMKT Civil Engineering Ltd | SA to enter the main contractor name
2023-08-04 | SA to input the report issue date

## Contents
Highways Improvement for Urban Environment - Dublin
Cost Report No_01
[5 empty] | Guidance Notes | * All cells in purple - input is required | *** Figures are illustrative ***
CONTENTS PAGE
Project Name: | Highways Improvement for Urban Environment - Dublin |  |  |  | SA - no action - carries from cover page
Report No. | Cost Report No_01 |  |  |  | SA - no action - carries from cover page
Date: | 2023-08-04 |  |  |  | SA - no action - carries from cover page
1. Executive Summary
2. Project Control Document Summary (PCD)
3. Change Orders - Agreed
3. Change Orders - To be Agreed
4. Employer Claims - Agreed
1 | 4. Employer Claims - To be Agreed
5. Potential Liabilitites
6. Cash Flow Expenditure (Main Contractor)
3 | Schedule of Payment Certificates
6 | Employer Claims Summary
7 | Situation Notification Summary
8 | Other liabilities Summary
9 | Employer's Comparison Data Sheet
10 | Construction Expenditure Profile
Revision | Status | Prepared by | Checked by | Date
| Interim Cost Report | S Gate | M Bunny | 2023-08-04 | SA to sign off (2 parties within their organisation)
Cost and Schedule Performance Indicators
CPI |  |  | SPI | 1

## Executive Summary
Highways Improvement for Urban Environment - Dublin
Cost Report No_01
[5 empty] | Guidance Notes | *** Figures are illustrative ***
1. PROJECT EXECUTIVE SUMMARY
|  | NTA | Sponsoring Agency
Ref | Description | Approved Budget | Forecast Out-Turn | Comments
1 | CONSTRUCTION WORKS | € | €
1.1 | Main Contractor Contract Sum | 35989709.38 | 35989709.38 |  | SA to confirm contract sum
1.2 | Change Control (Clause 10.3): Agreed | 0 | 99500 |  | SA to confirm - populate from 10.3 register (total automatically carries across)
1.3 | Change Control (Clause 10.3): To be Agreed | 0 | 7500 |  | SA to confirm - populate from 10.3 register (total automatically carries across)
1.4 | Employer Claims (Clause 10.9): Agreed | 0 | 0 |  | SA to confirm - populate from 10.9 register (total automatically carries across)
1.5 | Employer Claims (Clause 10.9): To be Agreed | 0 | -5000 |  | SA to confirm - populate from 10.9 register (total automatically carries across)
1.6 | Potential Liabilities | 0 | 130000 |  | SA to confirm - populate from potential liabilities (total automatically carries across)
1.7 | Ex-Gratia Payments (if applicable) | 0 | 0 | Refer to separate OGP worksheet (if applicable) | SA to confirm - input a figure if applicable (separate OGP worksheet)
| TOTAL CONSTRUCTION WORKS | 35989709.38 | 36221709.38
2 | PREPARATION & ADMINISTRATION
2.1 | Scope & Purpose | 0 | 0 |  | SA to confirm - figures should be from the NTA approval to construction from Phase 5
2.2 | Concept, Development & Option Selection | 1688137.92 | 1688137.92 |  | SA to confirm - figures should be from the NTA approval to construction from Phase 5
2.3 | Preliminary Design | 722135.68 | 722135.68 |  | SA to confirm - figures should be from the NTA approval to construction from Phase 5
2.4 | Statutory Processes | 280732.48 | 280732.48 |  | SA to confirm - figures should be from the NTA approval to construction from Phase 5
2.5 | Detailed Design & Procurement | 542241.28 | 542241.28 |  | SA to confirm - figures should be from the NTA approval to construction from Phase 5
2.6 | Construction & Implementation | 2382751.81 | 2382751.84 |  | SA to confirm - figures should be from the NTA approval to construction from Phase 5
2.7 | Close Out & Review | 290464.16 | 290464.16 |  | SA to confirm - figures should be from the NTA approval to construction from Phase 5
| TOTAL PREPARATION & ADMINISTRATION | 5906463.33 | 5906463.36
3 | LAND & PROPERTY COSTS
3.1 | Land & Property Costs (if applicable) | 175000 | 175000 |  | SA to confirm
| TOTAL LAND & PROPERTY COSTS | 175000 | 175000
4 | ADJUSTMENTS
4.1 | Inflation | 2021301.53 | 0 | No expenditure (incurred costs included in 10.3 register / potential liabilitites) | SA to confirm - figures should be from the NTA approval to construction from Phase 5
4.2 | Project Specific Risk (013_B23_QRA_CMG) | 9921435.15 | 0 | No expenditure (incurred costs included in 10.3 register / potential liabilitites) | SA to confirm - figures should be from the NTA approval to construction from Phase 5
4.3 | Contingency Sum (001_B123_CC_CMG) | 5236876.72 | 0 | No expenditure (incurred costs included in 10.3 register / potential liabilitites) | SA to confirm - figures should be from the NTA approval to construction from Phase 5
4.4 | Per Cent for Art Scheme | 523687.67 | 523687.67 | Including allowance for arts - final scope TBA | SA to confirm - figures should be from the NTA approval to construction from Phase 5
| TOTAL ADJUSTMENTS | 17703301.07 | 523687.67
| OVERALL COST SUMMARY | BUDGET | CURRENT
1 | Construction Works | 35989709.38 | 36221709.38 |  | Tot's automatically from above
2 | Preparation & Administration | 5906463.33 | 5906463.36 |  | Tot's automatically from above
3 | Land & Property | 175000 | 175000 |  | Tot's automatically from above
4 | Adjustments | 17703301.07 | 523687.67 |  | Tot's automatically from above
| OVERALL TOTAL (Excluding VAT): | 59774473.78 | 42826860.41
PROGRAMME |  |  |  | COMMENTS
A | Contract Signing Date | 2023-07-04 |  |  | SA to confirm
B | Contract Start Date On Site | 2023-08-25 |  |  | SA to confirm
C | Original Date for Substantial Completion | 2025-07-25 |  |  | SA to confirm
D | Current delay, days (if any) | 5 days |  | SA and design team are currently reviewing (critical path) | SA to confirm
E | Forecast Substantial Completion Date | 2025-08-01 |  |  | SA to confirm

## PCD Summary
2. Project Control Document Summary | [13 empty] | * NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional line etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the project control document. | [13 empty] | Guidance Notes | *** Figures are illustrative ***
Project Title: |  |  | Highways Improvement for Urban Environment - Dublin
Cost Report No: |  |  | Cost Report No_01 | Prepared By (Individual & Organisation) | [8 empty] | S Gate / SDCC | SA to confirm who prepared the cost report
Approving Authority: |  |  | NTA | Date Prepared: | [8 empty] | Q3 2023 | SA to confirm the submission date
Sponsoring Agency: |  |  | South Dublin Council |  |  | PCD - APPROVED NTA BUDGET |  |  |  | PCD - Current Expenditure - Construction Stage
| Ref | PCD Summary |  | Qty | Unit | Sub-Total | VAT % | VAT Amount | Total Incl. VAT | Sub-Total | VAT % | VAT Amount | Total Incl. VAT
| 1.1 | Main Contractor (Contract Sum) |  | 1 | Item | 35989709.38 | 13.5 | 4858610.7663 | 40848320.1463 | 35989709.38 | 13.5 | 4858610.7663 | 40848320.1463 | Figures carry across from Exective Summary tab
| 1.2 | Change Control (Clause10.3): Agreed |  | 1 | Item | 0 | 13.5 | 0 | 0 | 99500 | 13.5 | 13432.5 | 112932.5 | Figures carry across from Exective Summary tab
| 1.3 | Change Control (Clause 10.3): To be Agreed |  | 1 | Item | 0 | 13.5 | 0 | 0 | 7500 | 13.5 | 1012.5 | 8512.5 | Figures carry across from Exective Summary tab
| 1.4 | Employer Claims (Clause 10.9): Agreed |  | 1 | Item | 0 | 13.5 | 0 | 0 | 0 | 13.5 | 0 | 0 | Figures carry across from Exective Summary tab
| 1.5 | Employer Claims (Clause 10.9): To be Agreed |  | 1 | Item | 0 | 13.5 | 0 | 0 | -5000 | 13.5 | -675 | -5675 | Figures carry across from Exective Summary tab
| 1.6 | Potential Liabilities |  | 1 | Item | 0 | 13.5 | 0 | 0 | 130000 | 13.5 | 17550 | 147550 | Figures carry across from Exective Summary tab
| 1.7 | Ex-Gratia Payments (if applicable) |  | 1 | Item | 0 | 13.5 | 0 |  | 0 | 13.5 | 0 |  | Figures carry across from Exective Summary tab
| 1.8 | Scope & Purpose |  | 1 | Item | 0 | 23 | 0 | 0 | 0 | 23 | 0 | 0 | Figures carry across from Exective Summary tab
| 1.9 | Concept, Development & Option Selection |  | 1 | Item | 1688137.92 | 23 | 388271.7216 | 2076409.6416 | 1688137.92 | 23 | 388271.7216 | 2076409.6416 | Figures carry across from Exective Summary tab
| 1.1 | Preliminary Design |  | 1 | Item | 722135.68 | 23 | 166091.2064 | 888226.8864 | 722135.68 | 23 | 166091.2064 | 888226.8864 | Figures carry across from Exective Summary tab
| 1.11 | Statutory Processes |  | 1 | Item | 280732.48 | 23 | 64568.4704 | 345300.9504 | 280732.48 | 23 | 64568.4704 | 345300.9504 | Figures carry across from Exective Summary tab
| 1.12 | Detailed Design & Procurement |  | 1 | Item | 542241.28 | 23 | 124715.4944 | 666956.7744 | 542241.28 | 23 | 124715.4944 | 666956.7744 | Figures carry across from Exective Summary tab
| 1.13 | Construction & Implementation |  | 1 | Item | 2382751.81 | 23 | 548032.9163 | 2930784.7263 | 2382751.84 | 23 | 548032.9232 | 2930784.7632 | Figures carry across from Exective Summary tab
| 1.14 | Close Out & Review |  | 1 | Item | 290464.16 | 23 | 66806.7568 | 357270.9168 | 290464.16 | 23 | 66806.7568 | 357270.9168 | Figures carry across from Exective Summary tab
| 1.15 | Land & Property Costs |  | 1 | Item | 175000 |  |  | 175000 | 175000 |  |  | 175000 | Figures carry across from Exective Summary tab
| 1.16 | Inflation |  | 1 | Item | 2021301.53 | 13.5 | 272875.7066 | 2294177.2366 | 0 | 13.5 | 0 | 0 | Figures carry across from Exective Summary tab
| 1.17 | Project Specific Risk |  | 1 | Item | 9921435.15 | 13.5 | 1339393.7453 | 11260828.8953 | 0 | 13.5 | 0 | 0 | Figures carry across from Exective Summary tab
| 1.18 | Contingency Sum |  | 1 | Item | 5236876.72 | 13.5 | 706978.3572 | 5943855.0772 | 0 | 13.5 | 0 | 0 | Figures carry across from Exective Summary tab
| 1.19 | Arts (Allowance) |  | 1 | Item | 523687.67 | 13.5 | 70697.8354 | 594385.5054 | 523687.67 | 13.5 | 70697.8354 | 594385.5054 | Figures carry across from Exective Summary tab
|  |  |  | Sub-Total (Ex.VAT) |  | 59774473.78 |  |  |  | 42826860.41
[7 empty] | VAT on Land (if applicable) |  |  | VAT on Land (if applicable) |  |  |  | Figures carry across from Exective Summary tab
[7 empty] | Total Incl.VAT |  | 68381516.7567 | Total Incl. VAT |  |  | 49145975.5846 | Tot's automatically

## Clause 10.3
3. Change Order Summary
[9 empty] | Guidance Notes | *** Figures are illustrative ***
Highways Improvement for Urban Environment - Dublin
Cost Report No_01
Compensation Events (Clause 10.3) - Agreed
|  | Date Received | Open / Closed | Contractor Estimated Impact |  | Employer Estimated Impact |  | Agreed Value (Cost & Time)
Ref | Description |  |  | Cost | Impact | Cost | Impact
1 | Protection to ESB duct | **/08*20** | Closed | 4500 | No effect | 4500 | No effect | 4500 | SA to confirm
2 | IW Watermain line | **/08*20** | Closed | 55000 | 3 days | 50000 | 3 days | 52000 | SA to confirm
3 | Eircom - chamber alteration | **/08*20** | Closed | 28000 | No effect | 25000 | No effect | 26000 | SA to confirm
4 | Re-build wall (boundary collapse) | **/08*20** | Closed | 15000 | No effect | 15000 | No effect | 15000 | SA to confirm
5 | Investigation works (plant) for LA | **/08*20** | Closed | 2500 | No effect | 2000 | No effect | 2000 | SA to confirm
[8 empty] | 99500 | Figure carries into the executive summary
Compensation Events (Clause 10.3) - To be Agreed
|  | Date Received | Open / Closed | Contractor Estimated Impact |  | Employer Estimated Impact |  | Estimated Libility (Worst Case)
Ref | Description |  |  | Cost | Impact | Cost | Impact
1 | Additional tactile paving at pedestrian crossings |  | Open | 7500 | 2 days | 4200 | No effect | 7500 | SA to confirm - Worst case is carried to executive summary
2
3
4
5
6
7
8
9
10
|  |  |  | 7500 |  | 4200 |  | 7500 | Figure carries into the executive summary

## Clause 10.9
4. Employer Claims Summary
[9 empty] | Guidance Notes | *** Figures are illustrative ***
Highways Improvement for Urban Environment - Dublin
Cost Report No_01
Employer Claims (Clause 10.9) - Agreed
|  | Date Received | Open / Closed | Contractor Estimated Impact |  | Employer Estimated Impact |  | Agreed Value (Cost & Time)
Ref | Description |  |  | Cost | Impact | Cost | Impact
SA to confirm
[8 empty] | 0 | Figure carries into the executive summary
Employer Claims (Clause 10.9) - To be Agreed
|  | Date Received | Open / Closed | Contractor Estimated Impact |  | Employer Estimated Impact |  | Estimated Libility (Worst Case)
Ref | Description |  |  | Cost | Impact | Cost | Impact
1 | ESB ducts reduced from 4 number to 3 number |  | Open | -5000 |  | -7500 | No effect | -5000 | SA to confirm - Worst case is carried to executive summary
|  |  |  | -5000 |  | -7500 |  | -5000 | Figure carries into the executive summary

## Potential Liabilitites
5. Potential Liabilitites Summary
|  |  |  | Guidance Notes | *** Figures are illustrative ***
Highways Improvement for Urban Environment - Dublin
Cost Report No_01
Potential Liabilitites
|  | Estimated Impact |  | SA to include potential variations - items that have not yet been received under Clause 10.3
Ref | Description | Cost | Impact (Time)
1 | Badger sett encourtered during site strip - ecologist and vets required for safe removal / re-locating | 10000 | No delay | SA to confirm - when figures are finalised / agreed carry over to Clause 10.3 register
2 | Unknown fibre optic cable located - survey work is underway from the contractor to determine the extent of disruption (diversion will be required by specialist) | 120000 | 15 days | SA to confirm - when figures are finalised / agreed carry over to Clause 10.3 register
130000
| Estimated Total Cost (Including Time) |  |  | Figure carries into the executive summary

## Cash Flow Expenditure
6. Main Contractor - Cash Flow Expenditure
Highways Improvement for Urban Environment - Dublin | [5 empty] | Guidance Notes | *** Figures are illustrative ***
Cost Report No_01
Main Contractor Contract Sum |  |  | 35989709.38 |  |  | Figures carry across from Exective Summary tab
Change Control (Clause 10.3) - Agreed |  |  | 99500 |  |  | Figures carry across from Exective Summary tab
Change Control (Clause 10.3) - TBA |  |  | 7500 |  |  | Figures carry across from Exective Summary tab
Employer Claims (Clause 10.9) - Agreed |  |  | 0 |  |  | Figures carry across from Exective Summary tab
Employer Claims (Clause 10.9) - TBA |  |  | -5000 |  |  | Figures carry across from Exective Summary tab
Potential Liabilitites |  |  | 130000 |  |  | Figures carry across from Exective Summary tab
Ex-Gratia Payments (if applicable) |  |  | 0 |  |  | Figures carry across from Exective Summary tab
Sub-Total (Ex.VAT) |  |  | 36221709.38 |  |  | Sub-total calculates automatically
VAT @ 13.5% |  |  | 4889930.7663 |  |  | VAT @ 13.% calculates automatically
Total (Including VAT) |  |  | 41111640.1463 |  |  | Total calculates automatically
No | Year | Month | Contractor Projected Cash Flow | Certified Amount | Forecast Value
1 | 2023 | July | 1161640.15 | 1161640.15
2 |  | August | 1450000 |  | 1450000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
3 |  | September | 1500000 |  | 1500000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
4 |  | October | 1650000 |  | 1650000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
5 |  | November | 1800000 |  | 1800000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
6 |  | December | 1350000 |  | 1350000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
7 | 2024 | January | 1500000 |  | 1500000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
8 |  | February | 1950000 |  | 1950000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
9 |  | March | 1850000 |  | 1850000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
10 |  | April | 2400000 |  | 2400000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
11 |  | May | 2800000 |  | 2800000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
12 |  | June | 2650000 |  | 2650000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
13 |  | July | 3000000 |  | 3000000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
14 |  | August | 2000000 |  | 2000000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
15 |  | September | 2400000 |  | 2400000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
16 |  | October | 1750000 |  | 1750000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
17 |  | November | 1900000 |  | 1900000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
18 |  | December | 1500000 |  | 1500000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
19 | 2025 | January | 1500000 |  | 1500000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
20 |  | February | 1500000 |  | 1500000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
21 |  | March | 1500000 |  | 1500000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
22 |  | April | 750000 |  | 750000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
23 |  | May | 750000 |  | 750000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
24 |  | June | 500000 |  | 500000 | SA to confirm - if final figures on variation expenditure (month) is not known - SA to include their best estimate
41111640.15
**Exclude Retention Values from Projected Cash Flow

## Summary (hidden)
1 | #REF!
#REF!
| #REF! | Area (Tenant Space Only NIA)
| #REF! | #REF! | m2 | #REF! | sq.ft.
Col. 1 | Col. 2 | Col. 3 | Col. 4 | Col. 5 | Col. 6
Item | Description | Element % | €/m2 | €/sq.ft | Total
A | Builder's Work (CAT A & B)
1 | Main Contractors Preliminaries | #REF! | #REF! | #REF! | #REF!
| Attendances/ Insurances/ Overheads |  |  |  | #REF!
2 | Demolitions & Alterations | #REF! | #REF! | #REF! | #REF!
| Any demolitions and alterations to existing finishes, layout or structure |  |  |  | #REF!
3 | Internal walls | #REF! | #REF! | #REF! | #REF!
| Acoustic/ fire/ moisture resistant rated stud walls, Glazed Partitions |  |  |  | #REF!
4 | Internal wall Completions | #REF! | #REF! | #REF! | #REF!
#REF!
6 | Wall Finishes | #REF! | #REF! | #REF! | #REF!
| General painting of walls throughout |  |  |  | #REF!
7 | Floor Finishes | #REF! | #REF! | #REF! | #REF!
| Carpet finishes throughout, upgrade of finishes to meeting rooms and office |  |  |  | #REF!
8 | Ceilings Finishes | #REF! | #REF! | #REF! | #REF!
| Grid and tile ceiling, upgrade of plasterboard to meeting rooms and office |  |  |  | #REF!
9 | Fixtures, Fittings & Equipment | #REF! | #REF! | #REF! | #REF!
Internal perimeter blinds, Mini-kitchen Joinery,
10 | Ancillary Works | #REF! | #REF! | #REF! | 0
(Fire safety signage, cleaning)
11 | Provisional Sums | #REF! | #REF! | #REF! | 0
(Provisional Sum of €2,000 for cleaning and painting of existing office/bathroom area; Provisional Sum of €5,000 for Signage).
12 | Design Development | #REF! | #REF! | #REF! |  | Checks
| (Allowance of 5%) |  |  |  |  | % | cost/m2 | cost/ft2 | total
13 | TOTAL BUILDERS WORKS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B | Services (CAT A & B)
1 | Mechanical Installations | #REF! | #REF! | #REF! | #REF!
(See Metec Consulting Engineers Budget - Refer to Appendix A); 6.5% added for BWIC & MCD
2 | Electrical Installations | #REF! | #REF! | #REF! | #REF!
| (See Metec Consulting Engineers Budget - Refer to Appendix A); 6.5% added for BWIC & MCD |  |  |  | #REF!
3 | Security Installations | 0% | 0 | 0 | #REF!
| (Scope to be confirmed by client if required) |  |  |  | #REF!
4 | Audio Visual & Video Conferencing | 0% | 0 | 0 | #REF! | Checks
| (Scope to be confirmed by client if required) |  |  |  |  | % | cost/m2 | cost/ft2 | total
5 | TOTAL SERVICES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
C | TOTAL BUILDERS WORKS & SERVICES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
D | Direct Orders
1 | Furniture Supply, Fitting and Delivery | #REF! | #REF! | #REF! | #REF!
| (Budget allowance for fixed Herman Miller 'Ratio' desks, Herman Miller 'Mirra' chairs, 2 drawer pedistals, monitor arms, armchairs, sofas, etc) |  |  |  | #REF!
2 | Client Direct IT Budget | 0% | 0 | 0 | #REF!
3 | Client Direct AV/ VC | 0% | 0 | 0 | TBC
4 | Move Management | 0% | 0 | 0 | TBC | Checks
[6 empty] | % | cost/m2 | cost/ft2 | total
5 | TOTAL DIRECT ORDERS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E | Contingency
1 | Client Contingency @ 5% of Section C & D | #REF! | #REF! | #REF! | #REF!
(Reserve for Unforeseen Costs)
2 | TOTAL CONTINGENCY | #REF! | #REF! | #REF! | #REF!
F | TOTAL OF SECTION C, D AND E | 0% | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
G | Professional Fees
1 | Professional Fees for CBRE | #REF! | #REF! | #REF! | #REF!
(Project and Cost Management, Architect)
2 | Professional Fees for Mechanical & Electrical Services | #REF! | #REF! | #REF! | 0
(Metec)
F | TOTAL OF SECTION C, D AND E | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
G | Professional Fees
1 | Professional Fees for CBRE | #REF! | #REF! | #REF! | 0
(Project and Cost Management, Architect)
2 | Professional Fees for Mechanical & Electrical Services | #REF! | #REF! | #REF! | 0
(Metec)
3 | Professional Fees for Fire Consultant/DAC | #REF! | #REF! | #REF! | 0
(G Sexton)
4 | Professional Fees for Structural Engineer | #REF! | #REF! | #REF! | 0
(CS Consulting)
5 | Professional Fees for Assigned Certifier/DAC | #REF! | #REF! | #REF! | 0
(ORS)
5 | Professional Fees for PSDP | 0% | 0 | 0 | 0
7 | TOTAL PROFESSIONAL FEES | #REF! | #REF! | #REF! | 0
H | OVERALL TOTAL EXCLUDING VAT |  | #REF! | #REF! | #REF!

## Breakdown (hidden)
DO NOT ISSUE THIS SHEET TO CLIENT; TOTAL SUMMARY SHEET FOR ISSUE ONLY
HUB | Ireland
Owner | Mags de Búrca
COUNTRY | IRELAND
CITY | Dublin
Country Information and Statistics | #REF!
Total Local Currency/m2 Cat B fit out
Total Local Currency/sqft Cat B fit out
Typical Local Currency/sqft Cat A cost
Typical Local Currency/sqft Dilaps refurb
Typical Procurement | TBC
Typical Contract | TBC
Typical Build time (on site) | TBC
Typical professional fees | TBC% of construction cost
Construction inflation prediction over next 12 months | 0-1%
| Quantity | Unit | Rate | Total
Architectural Packages
Demolitions & Alterations |  |  |  | 0
Internal walls |  |  |  | 0 | 3.755
#REF! |  |  |  | 0
Wall Finishes |  |  |  | 0
Floor Finishes |  |  |  | 0
Ceilings Finishes |  |  |  | 0
Fixtures, Fittings & Equipment |  |  |  | 0
Ancillary Works |  |  |  | 0
Provisional Sums |  |  |  | 0
Services Packages
Mechanical Installations |  |  |  | 0
Electrical Installations |  |  |  | 0
Security Installations |  |  |  | 0
Audio Visual & Video Conferencing |  |  |  | 0
Total |  |  |  | 0
2.1 Shell & Core
These include fully finished landlord areas comprising Main Entrance and Reception, Lift and Stair Cores, Lobbies and Toilets. These areas are not part of the space rented to the tenant. The office floor areas are left as a shell, ready for category A fit-out (See Note 2.2)
2.2 Category A Fit-Out (Warm Shell)
Typically what the developer provides as part of the rentable office space and usually comprises the following:
• Raised Floors
• Suspended Ceilings
• Extension of the Mechanical and Electrical services above the Ceiling from the riser across the lettable space
• Finishes to the internal face of the external and core walls
2.3 Category B Fit-Out (Tenant Fit out)
Category B completes the fit-out to the occupier’s specific requirements, typically comprising the following:
• Installation of cellular offices
• enhanced finishes
• Conference/meeting room facilities
• Reception area
• enhanced services / specialist lighting
• IT and AV installations
• tea point/kitchen fit-out
• furniture
• blinds